## State Compiled
Typical Procurement Schedule for Civil Works (Spill Over) under SSA for the year 2017-18
Name of District : State All District
Sl.No. | Description of Goods | Quantity in Numbers | Method of Procurement | Estimated Cost (Rs. In Lakh) | Procurement Action 2017-18
[5 empty] | April | May | June | July | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March
1 | Primary School
| a. New Primary School (Rural) | 0 | Community Construction | 484.75 | Procurement Action 2017-18 April: please refer relevant districts sheet for Procurement Actions
| b. Primary schools sanctioned 2006-07 (deferred liability of 2008-09) | 0 | Community Construction | 2252.2801
| c. Buildings for Primary Schools sanctioned over and above 15000 primary schools sanctioned in 2006-07 for which land is now available | 0 | Community Construction | 441.88
| d. New school buildings sanctioned in 2006-07 (deferred liability of 2011-12) | 0 | Community Construction | 3217.851
| e. Building Less (Pry) | 0 | Community Construction | 0
| f. Deffered Liability of NSB 2014-15 | 0 | Community Construction | 0
| g. Funds sanctioned for NSBs of previous years | 0 | Community Construction | 0
| Sub Total of Primary Schools | 0 |  | 6396.7611
2 | Upper Primary
| a. Upper Primary (new) | 0 | Community Construction | 0 | Procurement Action 2017-18 April: please refer relevant districts sheet for Procurement Actions
| b. ACR for new UPS Rural | 0 | Community Construction | 8249.45
| c. Building Less (UP) | 0 | Community Construction | 17.46
| Sub Total of Upper Primary Schools | 0 |  | 8266.91
3 | Additional Class Room (without stairs) | 0 | Community Construction | 15406.97 | Procurement Action 2017-18 April: please refer relevant districts sheet for Procurement Actions
4 | Additional Class Room (with stairs) | 0 | Community Construction | 13673.4
5 | ACR sanctioned Last Year | 0 | Community Construction | 0
| Sub-total of ACRs | 0 |  | 29080.37
6 | Toilet/Urinals (Urban) | 0 | Community Construction | 0 | Procurement Action 2017-18 April: please refer relevant districts sheet for Procurement Actions
7 | Separate Girls Toilet | 0 | Community Construction | 0
8 | Toilet, drinking water, child friendly elements and kitchen sheds for new UPS | 0 | Community Construction | 0
9 | Drinking Water Facility(Urban) | 0 | Community Construction | 0
10 | Construction of Building of residential schools for specific category of children | 0 | Community Construction | 97.32
11 | Ramps | 0 | Community Construction | 0
12 | Head Master's Room (Deffered Liability 2014-15) | 0 | Community Construction | 0
13 | Toilet - Boys (Special PAB) | 0 | Community Construction | 0
14 | Toilet - Girls (Special PAB) | 0 | Community Construction | 0
15 | Construction of KGBV Buildings | 0 | Open Tender | 307.54
| Sub Total | 0 |  | 404.86
TOTAL |  | 0 |  | 44148.9011
43841.3611
Method of Procurement |  |  |  |  | Procurement Action 2017-18 Aug.: Procurement Actions
Community Construction |  |  |  |  | Procurement Action 2017-18 Aug.: 1. Preparation of Specifications and bids document
Open Tender |  |  |  |  | Procurement Action 2017-18 Aug.: 2. Issue of Invitation to bid
3. Open bids
4. Evaluation of bids
5. Award Contracts
6. Construction 25% complete
7. Construction 50% complete
8. Construction 75% complete
9. Construction 100% complete

## West Champaran
Typical Procurement Schedule for Civil Works (Spill Over) under SSA for the year 2017-18
Name of District : WEST CHAMPARAN
Sl.No. | Description of Goods | Quantity in Numbers | Method of Procurement | Estimated Cost (Rs. In Lakh) | Procurement Action 2017-18
[5 empty] | April | May | June | July | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March
1 | Primary School
| a. New Primary School (Rural) | 0 | Community Construction | 12.23 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| b. Primary schools sanctioned 2006-07 (deferred liability of 2008-09) | 0 | Community Construction | 0
| c. Buildings for Primary Schools sanctioned over and above 15000 primary schools sanctioned in 2006-07 for which land is now available | 0 | Community Construction | 0
| d. New school buildings sanctioned in 2006-07 (deferred liability of 2011-12) | 0 | Community Construction | 20.02 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| e. Building Less (Pry) | 0 | Community Construction | 0
| f. Deffered Liability of NSB 2014-15 | 0 | Community Construction | 0
| g. Funds sanctioned for NSBs of previous years | 0 | Community Construction | 0
| Sub Total of Primary Schools | 0 |  | 32.25
2 | Upper Primary
| a. Upper Primary (new) | 0 | Community Construction | 0
| b. ACR for new UPS Rural | 0 | Community Construction | 8.56 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| c. Building Less (UP) | 0 | Community Construction | 0
| Sub Total of Upper Primary Schools | 0 |  | 8.56
3 | Additional Class Room (without stairs) | 0 | Community Construction | 19.76 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
4 | Additional Class Room (with stairs) | 0 | Community Construction | 28.74 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
5 | ACR sanctioned Last Year | 0 | Community Construction | 0
| Sub-total of ACRs | 0 |  | 48.5
6 | Toilet/Urinals (Urban) | 0 | Community Construction | 0
7 | Separate Girls Toilet | 0 | Community Construction | 0
8 | Toilet, drinking water, child friendly elements and kitchen sheds for new UPS | 0 | Community Construction | 0
9 | Drinking Water Facility(Urban) | 0 | Community Construction | 0
10 | Construction of Building of residential schools for specific category of children | 0 | Community Construction | 0
11 | Ramps | 0 | Community Construction | 0
12 | Head Master's Room (Deffered Liability 2014-15) | 0 | Community Construction | 0
13 | Toilet - Boys (Special PAB) |  | Community Construction | 0
14 | Toilet - Girls (Special PAB) |  | Community Construction | 0
15 | Construction of KGBV Buildings | 0 | Open Tender | 0 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| Sub Total | 0 |  | 0
TOTAL |  | 0 | 89.31 | 89.31
Method of Procurement |  |  |  |  | Procurement Action 2017-18 Aug.: Procurement Actions
Community Construction |  |  |  |  | Procurement Action 2017-18 Aug.: 1. Preparation of Specifications and bids document
Open Tender |  |  |  |  | Procurement Action 2017-18 Aug.: 2. Issue of Invitation to bid
3. Open bids
4. Evaluation of bids
5. Award Contracts
6. Construction 25% complete
7. Construction 50% complete
8. Construction 75% complete
9. Construction 100% complete

## Vaishali
Typical Procurement Schedule for Civil Works (Spill Over) under SSA for the year 2017-18
Name of District : VAISHALI
Sl.No. | Description of Goods | Quantity in Numbers | Method of Procurement | Estimated Cost (Rs. In Lakh) | Procurement Action 2017-18
[5 empty] | April | May | June | July | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March
1 | Primary School
| a. New Primary School (Rural) | 0 | Community Construction | 0
| b. Primary schools sanctioned 2006-07 (deferred liability of 2008-09) | 0 | Community Construction | 0.02 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| c. Buildings for Primary Schools sanctioned over and above 15000 primary schools sanctioned in 2006-07 for which land is now available | 0 | Community Construction | 0
| d. New school buildings sanctioned in 2006-07 (deferred liability of 2011-12) | 0 | Community Construction | 0
| e. Building Less (Pry) | 0 | Community Construction | 0
| f. Deffered Liability of NSB 2014-15 | 0 | Community Construction | 0
| g. Funds sanctioned for NSBs of previous years | 0 | Community Construction | 0
| Sub Total of Primary Schools | 0 |  | 0.02
2 | Upper Primary
| a. Upper Primary (new) |  | Community Construction | 0
| b. ACR for new UPS Rural |  | Community Construction | 2.85 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| c. Building Less (UP) |  | Community Construction | 0
| Sub Total of Upper Primary Schools | 0 |  | 2.85
3 | Additional Class Room (without stairs) | 0 | Community Construction | 866.72 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
4 | Additional Class Room (with stairs) | 0 | Community Construction | 306.38 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
5 | ACR sanctioned Last Year | 0 | Community Construction | 0
| Sub-total of ACRs | 0 |  | 1173.1
6 | Toilet/Urinals (Urban) |  | Community Construction | 0
7 | Separate Girls Toilet |  | Community Construction | 0
8 | Toilet, drinking water, child friendly elements and kitchen sheds for new UPS |  | Community Construction | 0
9 | Drinking Water Facility(Urban) | 0 | Community Construction | 0
10 | Construction of Building of residential schools for specific category of children | 0 | Community Construction | 0
11 | Ramps | 0 | Community Construction | 0
12 | Head Master's Room (Deffered Liability 2014-15) | 0 | Community Construction | 0
13 | Toilet - Boys (Special PAB) |  | Community Construction | 0
14 | Toilet - Girls (Special PAB) |  | Community Construction | 0
15 | Construction of KGBV Buildings |  | Open Tender | 28.51 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| Sub Total | 0 |  | 28.51
TOTAL |  | 0 | 1175.97 | 1204.48
Method of Procurement |  |  |  |  | Procurement Action 2017-18 Aug.: Procurement Actions
Community Construction |  |  |  |  | Procurement Action 2017-18 Aug.: 1. Preparation of Specifications and bids document
Open Tender |  |  |  |  | Procurement Action 2017-18 Aug.: 2. Issue of Invitation to bid
3. Open bids
4. Evaluation of bids
5. Award Contracts
6. Construction 25% complete
7. Construction 50% complete
8. Construction 75% complete
9. Construction 100% complete

## Supaul
Typical Procurement Schedule for Civil Works (Spill Over) under SSA for the year 2017-18
Name of District : SUPAUL
Sl.No. | Description of Goods | Quantity in Numbers | Method of Procurement | Estimated Cost (Rs. In Lakh) | Procurement Action 2017-18
[5 empty] | April | May | June | July | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March
1 | Primary School
| a. New Primary School (Rural) | 0 | Community Construction | 0
| b. Primary schools sanctioned 2006-07 (deferred liability of 2008-09) | 0 | Community Construction | 0 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| c. Buildings for Primary Schools sanctioned over and above 15000 primary schools sanctioned in 2006-07 for which land is now available | 0 | Community Construction | 0
| d. New school buildings sanctioned in 2006-07 (deferred liability of 2011-12) | 0 | Community Construction | 64.82 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| e. Building Less (Pry) | 0 | Community Construction | 0
| f. Deffered Liability of NSB 2014-15 | 0 | Community Construction | 0
| g. Funds sanctioned for NSBs of previous years | 0 | Community Construction | 0
| Sub Total of Primary Schools | 0 |  | 64.82
2 | Upper Primary
| a. Upper Primary (new) | 0 | Community Construction | 0
| b. ACR for new UPS Rural | 0 | Community Construction | 190.98 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| c. Building Less (UP) | 0 | Community Construction | 0
| Sub Total of Upper Primary Schools | 0 |  | 190.98
3 | Additional Class Room (without stairs) | 0 | Community Construction | 159.74 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
4 | Additional Class Room (with stairs) | 0 | Community Construction | 819.47 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
5 | ACR sanctioned Last Year | 0 | Community Construction | 0
| Sub-total of ACRs | 0 |  | 979.21
6 | Toilet/Urinals (Urban) | 0 | Community Construction | 0
7 | Separate Girls Toilet | 0 | Community Construction | 0
8 | Toilet, drinking water, child friendly elements and kitchen sheds for new UPS | 0 | Community Construction | 0
9 | Drinking Water Facility(Urban) | 0 | Community Construction | 0
10 | Construction of Building of residential schools for specific category of children | 0 | Community Construction | 0
11 | Ramps | 0 | Community Construction | 0
12 | Head Master's Room (Deffered Liability 2014-15) | 0 | Community Construction | 0
13 | Toilet - Boys (Special PAB) | 0 | Community Construction | 0
14 | Toilet - Girls (Special PAB) | 0 | Community Construction | 0
15 | Construction of KGBV Buildings | 0 | Open Tender | 2.44 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| Sub Total | 0 |  | 2.44
TOTAL |  | 0 | 1235.01 | 1237.45
Method of Procurement |  |  |  |  | Procurement Action 2017-18 Aug.: Procurement Actions
Community Construction |  |  |  |  | Procurement Action 2017-18 Aug.: 1. Preparation of Specifications and bids document
Open Tender |  |  |  |  | Procurement Action 2017-18 Aug.: 2. Issue of Invitation to bid
3. Open bids
4. Evaluation of bids
5. Award Contracts
6. Construction 25% complete
7. Construction 50% complete
8. Construction 75% complete
9. Construction 100% complete

## Siwan
Typical Procurement Schedule for Civil Works (Spill Over) under SSA for the year 2017-18
Name of District : SIWAN
Sl.No. | Description of Goods | Quantity in Numbers | Method of Procurement | Estimated Cost (Rs. In Lakh) | Procurement Action 2017-18
[5 empty] | April | May | June | July | April | May | June | July | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March
1 | Primary School
| a. New Primary School (Rural) | 0 | Community Construction | 0 |  |  |  |  | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| b. Primary schools sanctioned 2006-07 (deferred liability of 2008-09) | 0 | Community Construction | 622.52 |  |  |  |  | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| c. Buildings for Primary Schools sanctioned over and above 15000 primary schools sanctioned in 2006-07 for which land is now available | 0 | Community Construction | 0
| d. New school buildings sanctioned in 2006-07 (deferred liability of 2011-12) | 0 | Community Construction | 57.09 |  |  |  |  | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| e. Building Less (Pry) | 0 | Community Construction | 0
| f. Deffered Liability of NSB 2014-15 | 0 | Community Construction | 0
| g. Funds sanctioned for NSBs of previous years | 0 | Community Construction | 0
| Sub Total of Primary Schools | 0 |  | 679.61
2 | Upper Primary
| a. Upper Primary (new) |  | Community Construction | 0
| b. ACR for new UPS Rural |  | Community Construction | 2433.23 |  |  |  |  | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| c. Building Less (UP) |  | Community Construction | 0
| Sub Total of Upper Primary Schools | 0 |  | 2433.23
3 | Additional Class Room (without stairs) | 0 | Community Construction | 852.79 |  |  |  |  | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
4 | Additional Class Room (with stairs) | 0 | Community Construction | 265.33 |  |  |  |  | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
5 | ACR sanctioned Last Year |  | Community Construction | 0
| Sub-total of ACRs | 0 |  | 1118.12
6 | Toilet/Urinals (Urban) |  | Community Construction | 0
7 | Separate Girls Toilet |  | Community Construction | 0
8 | Toilet, drinking water, child friendly elements and kitchen sheds for new UPS | 0 | Community Construction | 0
9 | Drinking Water Facility(Urban) | 0 | Community Construction | 0
10 | Construction of Building of residential schools for specific category of children | 0 | Community Construction
11 | Ramps | 0 | Community Construction | 0
12 | Head Master's Room (Deffered Liability 2014-15) |  | Community Construction | 0
13 | Toilet - Boys (Special PAB) | 0 | Community Construction | 0 | Procurement Action 2017-18 April: 1-6; Procurement Action 2017-18 May: 1-6; Procurement Action 2017-18 June: 1-6; Procurement Action 2017-18 July: 1-7
14 | Toilet - Girls (Special PAB) | 0 | Community Construction | 0 | Procurement Action 2017-18 April: 1-6; Procurement Action 2017-18 May: 1-6; Procurement Action 2017-18 June: 1-6; Procurement Action 2017-18 July: 1-7
15 | Construction of KGBV Buildings |  | Open Tender | 7 |  |  |  |  | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| Sub Total | 0 |  | 7
TOTAL |  | 0 | 4230.96 | 4237.96
Method of Procurement |  |  |  |  | Procurement Action 2017-18 Aug.: Procurement Actions
Community Construction |  |  |  |  | Procurement Action 2017-18 Aug.: 1. Preparation of Specifications and bids document
Open Tender |  |  |  |  | Procurement Action 2017-18 Aug.: 2. Issue of Invitation to bid
3. Open bids
4. Evaluation of bids
5. Award Contracts
6. Construction 25% complete
7. Construction 50% complete
8. Construction 75% complete
9. Construction 100% complete

## Sitamarhi
Typical Procurement Schedule for Civil Works (Spill Over) under SSA for the year 2017-18
Name of District : SITAMARHI
Sl.No. | Description of Goods | Quantity in Numbers | Method of Procurement | Estimated Cost (Rs. In Lakh) | Procurement Action 2017-18
[5 empty] | April | May | June | July | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March
1 | Primary School
| a. New Primary School (Rural) | 0 | Community Construction | 0
| b. Primary schools sanctioned 2006-07 (deferred liability of 2008-09) | 0 | Community Construction | 0
| c. Buildings for Primary Schools sanctioned over and above 15000 primary schools sanctioned in 2006-07 for which land is now available | 0 | Community Construction | 11.89 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| d. New school buildings sanctioned in 2006-07 (deferred liability of 2011-12) | 0 | Community Construction | 0
| e. Building Less (Pry) | 0 | Community Construction | 0
| f. Deffered Liability of NSB 2014-15 | 0 | Community Construction | 0
| g. Funds sanctioned for NSBs of previous years | 0 | Community Construction | 0
| Sub Total of Primary Schools | 0 |  | 11.89
2 | Upper Primary
| a. Upper Primary (new) |  | Community Construction | 0
| b. ACR for new UPS Rural |  | Community Construction | 29.54 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| c. Building Less (UP) |  | Community Construction | 0
| Sub Total of Upper Primary Schools | 0 |  | 29.54
3 | Additional Class Room (without stairs) | 0 | Community Construction | 193.73 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
4 | Additional Class Room (with stairs) | 0 | Community Construction | 129.15 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
5 | ACR sanctioned Last Year | 0 | Community Construction | 0
| Sub-total of ACRs | 0 |  | 322.88
6 | Toilet/Urinals (Urban) | 0 | Community Construction | 0
7 | Separate Girls Toilet |  | Community Construction | 0
8 | Toilet, drinking water, child friendly elements and kitchen sheds for new UPS |  | Community Construction | 0
9 | Drinking Water Facility(Urban) | 0 | Community Construction | 0
10 | Construction of Building of residential schools for specific category of children | 0 | Community Construction | 0
11 | Ramps | 0 | Community Construction | 0
12 | Head Master's Room (Deffered Liability 2014-15) | 0 | Community Construction | 0
13 | Toilet - Boys (Special PAB) | 0 | Community Construction | 0
14 | Toilet - Girls (Special PAB) | 0 | Community Construction | 0
15 | Construction of KGBV Buildings | 0 | Open Tender | 0 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| Sub Total | 0 |  | 0
TOTAL |  | 0 | 364.31 | 364.31
Method of Procurement |  |  |  |  | Procurement Action 2017-18 Aug.: Procurement Actions
Community Construction |  |  |  |  | Procurement Action 2017-18 Aug.: 1. Preparation of Specifications and bids document
Open Tender |  |  |  |  | Procurement Action 2017-18 Aug.: 2. Issue of Invitation to bid
3. Open bids
4. Evaluation of bids
5. Award Contracts
6. Construction 25% complete
7. Construction 50% complete
8. Construction 75% complete
9. Construction 100% complete

## Sheohar
Typical Procurement Schedule for Civil Works (Spill Over) under SSA for the year 2017-18
Name of District : Sheohar
Sl.No. | Description of Goods | Quantity in Numbers | Method of Procurement | Estimated Cost (Rs. In Lakh) | Procurement Action 2017-18
[5 empty] | April | May | June | July | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March
1 | Primary School
| a. New Primary School (Rural) | 0 | Community Construction | 0 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| b. Primary schools sanctioned 2006-07 (deferred liability of 2008-09) | 0 | Community Construction | 0
| c. Buildings for Primary Schools sanctioned over and above 15000 primary schools sanctioned in 2006-07 for which land is now available | 0 | Community Construction | 0
| d. New school buildings sanctioned in 2006-07 (deferred liability of 2011-12) | 0 | Community Construction | 8.48 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| e. Building Less (Pry) | 0 | Community Construction | 0
| f. Deffered Liability of NSB 2014-15 | 0 | Community Construction | 0
| g. Funds sanctioned for NSBs of previous years | 0 | Community Construction | 0
| Sub Total of Primary Schools | 0 |  | 8.48
2 | Upper Primary
| a. Upper Primary (new) |  | Community Construction | 0
| b. ACR for new UPS Rural | 0 | Community Construction | 111.99 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| c. Building Less (UP) |  | Community Construction | 0
| Sub Total of Upper Primary Schools | 0 |  | 111.99
3 | Additional Class Room (without stairs) | 0 | Community Construction | 142.11 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
4 | Additional Class Room (with stairs) | 0 | Community Construction | 94.72 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
5 | ACR sanctioned Last Year | 0 | Community Construction | 0
| Sub-total of ACRs | 0 |  | 236.83
6 | Toilet/Urinals (Urban) |  | Community Construction | 0
7 | Separate Girls Toilet |  | Community Construction | 0
8 | Toilet, drinking water, child friendly elements and kitchen sheds for new UPS |  | Community Construction | 0
9 | Drinking Water Facility(Urban) | 0 | Community Construction | 0
10 | Toilets , drinking water, kitchen sheds etc for new UPS | 0 | Community Construction | 0
11 | Construction of Building of residential schools for specific category of children | 0 | Community Construction
12 | Ramps | 0 | Community Construction | 0
13 | Head Master's Room (Deffered Liability 2014-15) | 0 | Community Construction | 0
14 | Toilet - Boys (Special PAB) | 0 | Community Construction | 0
15 | Toilet - Girls (Special PAB) | 0 | Community Construction | 0
| Sub Total | 0 |  | 0
14 | Construction of KGBV Buildings | 0 | Community Construction/ Open Tender | 34.66 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
TOTAL |  | 0 | 357.3 | 391.96
Method of Procurement |  |  |  |  | Procurement Action 2017-18 Aug.: Procurement Actions
Community Construction |  |  |  |  | Procurement Action 2017-18 Aug.: 1. Preparation of Specifications and bids document
Open Tender |  |  |  |  | Procurement Action 2017-18 Aug.: 2. Issue of Invitation to bid
3. Open bids
4. Evaluation of bids
5. Award Contracts
6. Construction 25% complete
7. Construction 50% complete
8. Construction 75% complete
9. Construction 100% complete

## Sheikhpura
Typical Procurement Schedule for Civil Works (Spill Over) under SSA for the year 2017-18
Name of District : Sheikhpura
Sl.No. | Description of Goods | Quantity in Numbers | Method of Procurement | Estimated Cost (Rs. In Lakh) | Procurement Action 2017-18
[5 empty] | April | May | June | July | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March
1 | Primary School
| a. New Primary School (Rural) | 0 | Community Construction | 0
| b. Primary schools sanctioned 2006-07 (deferred liability of 2008-09) | 0 | Community Construction | 32.11 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| c. Buildings for Primary Schools sanctioned over and above 15000 primary schools sanctioned in 2006-07 for which land is now available | 0 | Community Construction | 8.99 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| d. New school buildings sanctioned in 2006-07 (deferred liability of 2011-12) | 0 | Community Construction | 0
| e. Building Less (Pry) | 0 | Community Construction | 0
| f. Deffered Liability of NSB 2014-15 | 0 | Community Construction | 0
| g. Funds sanctioned for NSBs of previous years | 0 | Community Construction | 0
| Sub Total of Primary Schools | 0 |  | 41.1
2 | Upper Primary
| a. Upper Primary (new) | 0 | Community Construction | 0
| b. ACR for new UPS Rural | 0 | Community Construction | 5.22 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| c. Building Less (UP) | 0 | Community Construction | 0
| Sub Total of Upper Primary Schools | 0 |  | 5.22
3 | Additional Class Room (without stairs) | 0 | Community Construction | 2.64 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
4 | Additional Class Room (with stairs) | 0 | Community Construction | 6.39 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
5 | ACR sanctioned Last Year | 0 | Community Construction | 0
| Sub-total of ACRs | 0 |  | 9.03
6 | Toilet/Urinals (Urban) |  | Community Construction | 0
7 | Separate Girls Toilet | 0 | Community Construction | 0
8 | Toilet, drinking water, child friendly elements and kitchen sheds for new UPS | 0 | Community Construction | 0
9 | Drinking Water Facility(Urban) | 0 | Community Construction | 0
10 | Construction of Building of residential schools for specific category of children | 0 | Community Construction | 0
11 | Ramps | 0 | Community Construction | 0
12 | Head Master's Room (Deffered Liability 2014-15) | 0 | Community Construction | 0
13 | Toilet - Boys (Special PAB) | 0 | Community Construction | 0
14 | Toilet - Girls (Special PAB) |  | Community Construction | 0
15 | Construction of KGBV Buildings | 0 | Open Tender | 0 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| Sub Total | 0 |  | 0
TOTAL |  | 0 | 55.35 | 55.35
Method of Procurement |  |  |  |  | Procurement Action 2017-18 Aug.: Procurement Actions
Community Construction |  |  |  |  | Procurement Action 2017-18 Aug.: 1. Preparation of Specifications and bids document
Open Tender |  |  |  |  | Procurement Action 2017-18 Aug.: 2. Issue of Invitation to bid
3. Open bids
4. Evaluation of bids
5. Award Contracts
6. Construction 25% complete
7. Construction 50% complete
8. Construction 75% complete
9. Construction 100% complete

## Saran
Typical Procurement Schedule for Civil Works (Spill Over) under SSA for the year 2017-18
Name of District : SARAN
Sl.No. | Deiscription of Goods | Quantity in Numbers | Method of Procurement | Estimated Cost (Rs. In Lakh) | Procurement Action 2017-18
[5 empty] | April | May | June | July | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March
1 | Primary School
| a. New Primary School (Rural) | 0 | Community Construction | 32.22 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| b. Primary schools sanctioned 2006-07 (deferred liability of 2008-09) | 0 | Community Construction | 186.89 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| c. Buildings for Primary Schools sanctioned over and above 15000 primary schools sanctioned in 2006-07 for which land is now available | 0 | Community Construction | 0
| d. New school buildings sanctioned in 2006-07 (deferred liability of 2011-12) | 0 | Community Construction | 208.83 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| e. Building Less (Pry) | 0 | Community Construction | 0
| f. Deffered Liability of NSB 2014-15 | 0 | Community Construction | 0
| g. Funds sanctioned for NSBs of previous years | 0 | Community Construction | 0
| Sub Total of Primary Schools | 0 |  | 427.94
2 | Upper Primary
| a. Upper Primary (new) |  | Community Construction | 0
| b. ACR for new UPS Rural |  | Community Construction | 186.55 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| c. Building Less (UP) |  | Community Construction | 0
| Sub Total of Upper Primary Schools | 0 |  | 186.55
3 | Additional Class Room (without stairs) | 0 | Community Construction | 1009.47 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
4 | Additional Class Room (with stairs) | 0 | Community Construction | 443.76 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
5 | ACR sanctioned Last Year | 0 | Community Construction | 0
| Sub-total of ACRs | 0 |  | 1453.23
6 | Toilet/Urinals (Urban) | 0 | Community Construction | 0
7 | Separate Girls Toilet | 0 | Community Construction | 0
8 | Toilet, drinking water, child friendly elements and kitchen sheds for new UPS |  | Community Construction | 0
9 | Drinking Water Facility(Urban) | 0 | Community Construction | 0
10 | Construction of Building of residential schools for specific category of children | 0 | Community Construction | 0
11 | Ramps | 0 | Community Construction | 0
12 | Head Master's Room (Deffered Liability 2014-15) | 0 | Community Construction | 0
13 | Toilet - Boys (Special PAB) |  | Community Construction | 0
14 | Toilet - Girls (Special PAB) |  | Community Construction | 0
15 | Construction of KGBV Buildings |  | Community Construction | 2.72 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| Sub Total | 0 |  | 2.72
TOTAL |  | 0 | 2067.72 | 2070.44
Method of Procurement |  |  |  |  | Procurement Action 2017-18 Aug.: Procurement Actions
Community Construction |  |  |  |  | Procurement Action 2017-18 Aug.: 1. Preparation of Specifications and bids document
Open Tender |  |  |  |  | Procurement Action 2017-18 Aug.: 2. Issue of Invitation to bid
3. Open bids
4. Evaluation of bids
5. Award Contracts
6. Construction 25% complete
7. Construction 50% complete
8. Construction 75% complete
9. Construction 100% complete

## Samastipur
Typical Procurement Schedule for Civil Works (Spill Over) under SSA for the year 2017-18
Name of District : Samastipur
Sl.No. | Description of Goods | Quantity in Numbers | Method of Procurement | Estimated Cost (Rs. In Lakh) | Procurement Action 2017-18
[5 empty] | April | May | June | July | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March
1 | Primary School
| a. New Primary School (Rural) | 0 | Community Construction | 0
| b. Primary schools sanctioned 2006-07 (deferred liability of 2008-09) | 0 | Community Construction | 0 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| c. Buildings for Primary Schools sanctioned over and above 15000 primary schools sanctioned in 2006-07 for which land is now available | 0 | Community Construction | 0
| d. New school buildings sanctioned in 2006-07 (deferred liability of 2011-12) | 0 | Community Construction | 4.29 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| e. Building Less (Pry) | 0 | Community Construction | 0
| f. Deffered Liability of NSB 2014-15 | 0 | Community Construction | 0
| g. Funds sanctioned for NSBs of previous years | 0 | Community Construction | 0
| Sub Total of Primary Schools | 0 |  | 4.29
2 | Upper Primary
| a. Upper Primary (new) |  | Community Construction | 0
| b. ACR for new UPS Rural | 0 | Community Construction | 29.94 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| c. Building Less (UP) |  | Community Construction | 0 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| Sub Total of Upper Primary Schools | 0 |  | 29.94
3 | Additional Class Room (without stairs) | 0 | Community Construction | 2233.25 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
4 | Additional Class Room (with stairs) | 0 | Community Construction | 1195.46 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
5 | ACR sanctioned Last Year | 0 | Community Construction | 0
| Sub-total of ACRs | 0 |  | 3428.71
6 | Toilet/Urinals (Urban) |  | Community Construction | 0
7 | Separate Girls Toilet | 0 | Community Construction | 0
8 | Toilet, drinking water, child friendly elements and kitchen sheds for new UPS |  | Community Construction | 0
9 | Drinking Water Facility(Urban) | 0 | Community Construction | 0
10 | Construction of Building of residential schools for specific category of children | 0 | Community Construction | 0
11 | Ramps | 0 | Community Construction | 0
12 | Head Master's Room (Deffered Liability 2014-15) | 0 | Community Construction | 0
13 | Toilet - Boys (Special PAB) | 0 | Community Construction | 0
14 | Toilet - Girls (Special PAB) | 0 | Community Construction | 0
15 | Construction of KGBV Buildings |  | Open Tender | 9.7 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| Sub Total | 0 |  | 9.7
TOTAL |  | 0 | 3462.94 | 3472.64
Method of Procurement |  |  |  |  | Procurement Action 2017-18 Aug.: Procurement Actions
Community Construction |  |  |  |  | Procurement Action 2017-18 Aug.: 1. Preparation of Specifications and bids document
Open Tender |  |  |  |  | Procurement Action 2017-18 Aug.: 2. Issue of Invitation to bid
3. Open bids
4. Evaluation of bids
5. Award Contracts
6. Construction 25% complete
7. Construction 50% complete
8. Construction 75% complete
9. Construction 100% complete

## Saharsa
Typical Procurement Schedule for Civil Works (Spill Over) under SSA for the year 2017-18
Name of District : SAHARSA
Sl.No. | Description of Goods | Quantity in Numbers | Method of Procurement | Estimated Cost (Rs. In Lakh) | Procurement Action 2017-18
[5 empty] | April | May | June | July | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March
1 | Primary School
| a. New Primary School (Rural) | 0 | Community Construction | 0
| b. Primary schools sanctioned 2006-07 (deferred liability of 2008-09) | 0 | Community Construction | 376.3 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| c. Buildings for Primary Schools sanctioned over and above 15000 primary schools sanctioned in 2006-07 for which land is now available | 0 | Community Construction | 0
| d. New school buildings sanctioned in 2006-07 (deferred liability of 2011-12) | 0 | Community Construction | 1761.71 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| e. Building Less (Pry) | 0 | Community Construction | 0
| f. Deffered Liability of NSB 2014-15 | 0 | Community Construction | 0
| g. Funds sanctioned for NSBs of previous years | 0 | Community Construction | 0
| Sub Total of Primary Schools | 0 |  | 2138.01
2 | Upper Primary
| a. Upper Primary (new) | 0 | Community Construction | 0
| b. ACR for new UPS Rural | 0 | Community Construction | 1.55 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| c. Building Less (UP) | 0 | Community Construction | 0
| Sub Total of Upper Primary Schools | 0 |  | 1.55
3 | Additional Class Room (without stairs) | 0 | Community Construction | 1067.04 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
4 | Additional Class Room (with stairs) | 0 | Community Construction | 944.68 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
5 | ACR sanctioned Last Year | 0 | Community Construction | 0
| Sub-total of ACRs | 0 |  | 2011.72
6 | Toilet/Urinals (Urban) | 0 | Community Construction | 0
7 | Separate Girls Toilet | 0 | Community Construction | 0
8 | Toilet, drinking water, child friendly elements and kitchen sheds for new UPS | 0 | Community Construction | 0
9 | Drinking Water Facility(Urban) | 0 | Community Construction | 0
10 | Construction of Building of residential schools for specific category of children | 0 | Community Construction | 0
11 | Ramps | 0 | Community Construction | 0
12 | Head Master's Room (Deffered Liability 2014-15) | 0 | Community Construction | 0
13 | Toilet - Boys (Special PAB) | 0 | Community Construction | 0
14 | Toilet - Girls (Special PAB) | 0 | Community Construction | 0
15 | Construction of KGBV Buildings | 0 | Open Tender | 17 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| Sub Total | 0 |  | 17
TOTAL |  | 0 | 4151.28 | 4168.28
Method of Procurement |  |  |  |  | Procurement Action 2017-18 Aug.: Procurement Actions
Community Construction |  |  |  |  | Procurement Action 2017-18 Aug.: 1. Preparation of Specifications and bids document
Open Tender |  |  |  |  | Procurement Action 2017-18 Aug.: 2. Issue of Invitation to bid
3. Open bids
4. Evaluation of bids
5. Award Contracts
6. Construction 25% complete
7. Construction 50% complete
8. Construction 75% complete
9. Construction 100% complete

## Rohtas
Typical Procurement Schedule for Civil Works (Spill Over) under SSA for the year 2017-18
Name of District : ROHTAS
Sl.No. | Description of Goods | Quantity in Numbers | Method of Procurement | Estimated Cost (Rs. In Lakh) | Procurement Action 2017-18
[5 empty] | April | May | June | July | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March
1 | Primary School
| a. New Primary School (Rural) | 0 | Community Construction | 0
| b. Primary schools sanctioned 2006-07 (deferred liability of 2008-09) | 0 | Community Construction | 0
| c. Buildings for Primary Schools sanctioned over and above 15000 primary schools sanctioned in 2006-07 for which land is now available | 0 | Community Construction | 13.91 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| d. New school buildings sanctioned in 2006-07 (deferred liability of 2011-12) | 0 | Community Construction | 6.9 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| e. Building Less (Pry) | 0 | Community Construction | 0
| f. Deffered Liability of NSB 2014-15 | 0 | Community Construction | 0
| g. Funds sanctioned for NSBs of previous years | 0 | Community Construction | 0
| Sub Total of Primary Schools | 0 |  | 20.81
2 | Upper Primary
| a. Upper Primary (new) |  | Community Construction | 0
| b. ACR for new UPS Rural |  | Community Construction | 10.29 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| c. Building Less (UP) |  | Community Construction | 0
| Sub Total of Upper Primary Schools | 0 |  | 10.29
3 | Additional Class Room (without stairs) | 0 | Community Construction | 13.12 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
4 | Additional Class Room (with stairs) | 0 | Community Construction | 143.94 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
5 | ACR sanctioned Last Year | 0 | Community Construction | 0
| Sub-total of ACRs | 0 |  | 157.06
6 | Toilet/Urinals (Urban) |  | Community Construction | 0
7 | Separate Girls Toilet | 0 | Community Construction | 0
8 | Toilet, drinking water, child friendly elements and kitchen sheds for new UPS |  | Community Construction | 0
9 | Drinking Water Facility(Urban) | 0 | Community Construction | 0
10 | Construction of Building of residential schools for specific category of children | 0 | Community Construction | 0
11 | Ramps | 0 | Community Construction | 0
12 | Head Master's Room (Deffered Liability 2014-15) | 0 | Community Construction | 0
13 | Toilet - Boys (Special PAB) |  | Community Construction | 0
14 | Toilet - Girls (Special PAB) |  | Community Construction | 0
15 | Construction of KGBV Buildings |  | Open Tender | 6.78 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| Sub Total | 0 |  | 6.78
TOTAL |  | 0 | 188.16 | 194.94
Method of Procurement |  |  |  |  | Procurement Action 2017-18 Aug.: Procurement Actions
Community Construction |  |  |  |  | Procurement Action 2017-18 Aug.: 1. Preparation of Specifications and bids document
Open Tender |  |  |  |  | Procurement Action 2017-18 Aug.: 2. Issue of Invitation to bid
3. Open bids
4. Evaluation of bids
5. Award Contracts
6. Construction 25% complete
7. Construction 50% complete
8. Construction 75% complete
9. Construction 100% complete

## Purnia
Typical Procurement Schedule for Civil Works (Spill Over) under SSA for the year 2017-18
Name of District : Purnea
Sl.No. | Description of Goods | Quantity in Numbers | Method of Procurement | Estimated Cost (Rs. In Lakh) | Procurement Action 2017-18
[5 empty] | April | May | June | July | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March
1 | Primary School
| a. New Primary School (Rural) | 0 | Community Construction | 130.62 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| b. Primary schools sanctioned 2006-07 (deferred liability of 2008-09) | 0 | Community Construction | 0
| c. Buildings for Primary Schools sanctioned over and above 15000 primary schools sanctioned in 2006-07 for which land is now available | 0 | Community Construction | 28.65 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| d. New school buildings sanctioned in 2006-07 (deferred liability of 2011-12) | 0 | Community Construction | 37.33 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| e. Building Less (Pry) | 0 | Community Construction | 0
| f. Deffered Liability of NSB 2014-15 | 0 | Community Construction | 0
| g. Funds sanctioned for NSBs of previous years | 0 | Community Construction | 0
| Sub Total of Primary Schools | 0 |  | 196.6
2 | Upper Primary
| a. Upper Primary (new) | 0 | Community Construction | 0
| b. ACR for new UPS Rural | 0 | Community Construction | 377.08 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| c. Building Less (UP) | 0 | Community Construction | 0
| Sub Total of Upper Primary Schools | 0 |  | 377.08
3 | Additional Class Room (without stairs) | 0 | Community Construction | 519.49 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
4 | Additional Class Room (with stairs) | 0 | Community Construction | 125.2 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
5 | ACR sanctioned Last Year | 0 | Community Construction | 0
| Sub-total of ACRs | 0 |  | 644.69
6 | Toilet/Urinals (Urban) | 0 | Community Construction | 0
7 | Separate Girls Toilet | 0 | Community Construction | 0
8 | Toilet, drinking water, child friendly elements and kitchen sheds for new UPS | 0 | Community Construction | 0
9 | Drinking Water Facility(Urban) | 0 | Community Construction | 0
10 | Construction of Building of residential schools for specific category of children | 0 | Community Construction | 0
11 | Ramps | 0 | Community Construction | 0
12 | Head Master's Room (Deffered Liability 2014-15) | 0 | Community Construction | 0
13 | Toilet - Boys (Special PAB) |  | Community Construction | 0
14 | Toilet - Girls (Special PAB) |  | Community Construction | 0
15 | Construction of KGBV Buildings | 0 | Community Construction | 0 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| Sub Total | 0 |  | 0
TOTAL |  | 0 | 1218.37 | 1218.37
Method of Procurement |  |  |  |  | Procurement Action 2017-18 Aug.: Procurement Actions
Community Construction |  |  |  |  | Procurement Action 2017-18 Aug.: 1. Preparation of Specifications and bids document
Open Tender |  |  |  |  | Procurement Action 2017-18 Aug.: 2. Issue of Invitation to bid
3. Open bids
4. Evaluation of bids
5. Award Contracts
6. Construction 25% complete
7. Construction 50% complete
8. Construction 75% complete
9. Construction 100% complete

## Patna (U)
Typical Procurement Schedule for Civil Works (Spill Over) under SSA for the year 2017-18
Name of District : Patna (Urban)
Sl.No. | Description of Goods | Quantity in Numbers | Method of Procurement | Estimated Cost (Rs. In Lakh) | Procurement Action 2017-18
[5 empty] | April | May | June | July | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March
1 | Primary School
| a. New Primary School (Rural) | 0 | Community Construction | 0
| b. Primary schools sanctioned 2006-07 (deferred liability of 2008-09) | 0 | Community Construction | 0
| c. Buildings for Primary Schools sanctioned over and above 15000 primary schools sanctioned in 2006-07 for which land is now available | 0 | Community Construction | 0
| d. New school buildings sanctioned in 2006-07 (deferred liability of 201-12) | 0 | Community Construction | 0
| e. Building Less (Pry) | 0 | Community Construction | 0
| f. Deffered Liability of NSB 2014-15 | 0 | Community Construction | 0
| g. Funds sanctioned for NSBs of previous years | 0 | Community Construction | 0
| Sub Total of Primary Schools | 0 |  | 0
2 | Upper Primary
| a. Upper Primary (new) |  | Community Construction | 0
| b. ACR for new UPS Rural |  | Community Construction | 0
| c. Building Less (UP) |  | Community Construction | 0
| Sub Total of Upper Primary Schools | 0 |  | 0
3 | Additional Class Room (without stairs) | 0 | Community Construction | 62.43 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
4 | Additional Class Room (with stairs) | 0 | Community Construction | 15.75 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
5 | ACR sanctioned Last Year | 0 | Community Construction | 0
| Sub-total of ACRs | 0 |  | 78.18 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
6 | Toilet/Urinals (Urban) |  | Community Construction
7 | Separate Girls Toilet |  | Community Construction | 0
8 | Toilet, drinking water, child friendly elements and kitchen sheds for new UPS |  | Community Construction | 0
9 | Drinking Water Facility(Urban) | 0 | Community Construction | 0
10 | Construction of Building of residential schools for specific category of children | 0 | Community Construction | 97.32 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
11 | Ramps | 0 | Community Construction | 0
12 | d. Head Master's Room sanctioned (deferred liability of 2014-15) | 0 | Community Construction | 0
13 | Toilet - Boys (Special PAB) |  | Community Construction | 0
14 | Toilet - Girls (Special PAB) |  | Community Construction | 0
15 | Construction of KGBV Buildings |  | Community Construction/ Open Tender | 0
| Sub Total | 0 |  | 97.32
TOTAL |  | 0 | 175.5 | 175.5
Method of Procurement |  |  |  |  | Procurement Action 2017-18 Aug.: Procurement Actions
Community Construction |  |  |  |  | Procurement Action 2017-18 Aug.: 1. Preparation of Specifications and bids document
Open Tender |  |  |  |  | Procurement Action 2017-18 Aug.: 2. Issue of Invitation to bid
3. Open bids
4. Evaluation of bids
5. Award Contracts
6. Construction 25% complete
7. Construction 50% complete
8. Construction 75% complete
9. Construction 100% complete

## Patna (R)
Typical Procurement Schedule for Civil Works (Spill Over) under SSA for the year 2017-18
Name of District : Patna (Rural)
Sl.No. | Description of Goods | Quantity in Numbers | Method of Procurement | Estimated Cost (Rs. In Lakh) | Procurement Action 2017-18
[5 empty] | April | May | June | July | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March
1 | Primary School
| a. New Primary School (Rural) | 0 | Community Construction | 0
| b. Primary schools sanctioned 2006-07 (deferred liability of 2008-09) | 0 | Community Construction | 0
| c. Buildings for Primary Schools sanctioned over and above 15000 primary schools sanctioned in 2006-07 for which land is now available | 0 | Community Construction | 0
| d. New school buildings sanctioned in 2006-07 (deferred liability of 2011-12) | 0 | Community Construction | 0
| e. Building Less (Pry) | 0 | Community Construction | 0
| f. Deffered Liability of NSB 2014-15 | 0 | Community Construction | 0
| g. Funds sanctioned for NSBs of previous years | 0 | Community Construction | 0
| Sub Total of Primary Schools | 0 |  | 0
2 | Upper Primary
| a. Upper Primary (new) |  | Community Construction | 0
| b. ACR for new UPS Rural |  | Community Construction | 1612.32 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| c. Building Less (UP) |  | Community Construction | 0
| Sub Total of Upper Primary Schools | 0 |  | 1612.32
3 | Additional Class Room (without stairs) | 0 | Community Construction | 144.36 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
4 | Additional Class Room (with stairs) | 0 | Community Construction | 98.45 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
5 | ACR sanctioned Last Year | 0 | Community Construction | 0
| Sub-total of ACRs | 0 |  | 242.81
6 | Toilet/Urinals (Urban) |  | Community Construction | 0
7 | Separate Girls Toilet |  | Community Construction | 0
8 | Toilet, drinking water, child friendly elements and kitchen sheds for new UPS |  | Community Construction | 0
9 | Drinking Water Facility(Urban) | 0 | Community Construction | 0
10 | Construction of Building of residential schools for specific category of children | 0 | Community Construction | 0
11 | Ramps | 0 | Community Construction | 0
12 | Head Master's Room sanctioned (deferred liability of 2014-15) | 0 |  | 0
13 | Toilet - Boys (Special PAB) |  | Community Construction | 0
14 | Toilet - Girls (Special PAB) |  | Community Construction | 0
15 | Construction of KGBV Buildings |  | Community Construction/ Open Tender | 20.65 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| Sub Total | 0 |  | 20.65
TOTAL |  | 0 | 1855.13 | 1875.78
Method of Procurement |  |  |  |  | Procurement Action 2017-18 Aug.: Procurement Actions
Community Construction |  |  |  |  | Procurement Action 2017-18 Aug.: 1. Preparation of Specifications and bids document
Open Tender |  |  |  |  | Procurement Action 2017-18 Aug.: 2. Issue of Invitation to bid
3. Open bids
4. Evaluation of bids
5. Award Contracts
6. Construction 25% complete
7. Construction 50% complete
8. Construction 75% complete
9. Construction 100% complete

## Nawada
Typical Procurement Schedule for Civil Works (Spill Over) under SSA for the year 2017-18
Name of District : Nawada
Sl.No. | Description of Goods | Quantity in Numbers | Method of Procurement | Estimated Cost (Rs. In Lakh) | Procurement Action 2017-18
[5 empty] | April | May | June | July | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March
1 | Primary School
| a. New Primary School (Rural) | 0 | Community Construction | 0
| b. Primary schools sanctioned 2006-07 (deferred liability of 2008-09) | 0 | Community Construction | 0 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| c. Buildings for Primary Schools sanctioned over and above 15000 primary schools sanctioned in 2006-07 for which land is now available | 0 | Community Construction | 0
| d. New school buildings sanctioned in 2006-07 (deferred liability of 2011-12) | 0 | Community Construction | 81.73 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| e. Building Less (Pry) | 0 | Community Construction | 0
| f. Deffered Liability of NSB 2014-15 | 0 | Community Construction | 0
| g. Funds sanctioned for NSBs of previous years | 0 | Community Construction | 0
| Sub Total of Primary Schools | 0 |  | 81.73
2 | Upper Primary
| a. Upper Primary (new) | 0 | Community Construction | 0
| b. ACR for new UPS Rural |  | Community Construction | 772.65 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| c. Building Less (UP) |  | Community Construction | 0
| Sub Total of Upper Primary Schools | 0 |  | 772.65
3 | Additional Class Room (without stairs) | 0 | Community Construction | 636.38 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
4 | Additional Class Room (with stairs) | 0 | Community Construction | 286.72 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
5 | ACR sanctioned Last Year | 0 | Community Construction | 0
| Sub-total of ACRs | 0 |  | 923.1
6 | Toilet/Urinals (Urban) | 0 | Community Construction | 0
7 | Separate Girls Toilet |  | Community Construction | 0
8 | Toilet, drinking water, child friendly elements and kitchen sheds for new UPS |  | Community Construction | 0
9 | Drinking Water Facility(Urban) | 0 | Community Construction | 0
10 | Construction of Building of residential schools for specific category of children | 0 | Community Construction | 0
11 | Ramps | 0 | Community Construction | 0
12 | Head Master's Room (Deffered Liability 2014-15) | 0 | Community Construction | 0
13 | Toilet - Boys (Special PAB) |  | Community Construction | 0
14 | Toilet - Girls (Special PAB) |  | Community Construction | 0
15 | Construction of KGBV Buildings |  | Open Tender | 0 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| Sub Total | 0 |  | 0
TOTAL |  | 0 | 1777.48 | 1777.48
Method of Procurement |  |  |  |  | Procurement Action 2017-18 Aug.: Procurement Actions
Community Construction |  |  |  |  | Procurement Action 2017-18 Aug.: 1. Preparation of Specifications and bids document
Open Tender |  |  |  |  | Procurement Action 2017-18 Aug.: 2. Issue of Invitation to bid
3. Open bids
4. Evaluation of bids
5. Award Contracts
6. Construction 25% complete
7. Construction 50% complete
8. Construction 75% complete
9. Construction 100% complete

## Nalanda
Typical Procurement Schedule for Civil Works (Spill Over) under SSA for the year 2017-18
Name of District : Nalanda
Sl.No. | Description of Goods | Quantity in Numbers | Method of Procurement | Estimated Cost (Rs. In Lakh) | Procurement Action 2017-18
[5 empty] | April | May | June | July | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March
1 | Primary School
| a. New Primary School (Rural) | 0 | Community Construction | 24.92 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| b. Primary schools sanctioned 2006-07 (deferred liability of 2008-09) | 0 | Community Construction | 0
| c. Buildings for Primary Schools sanctioned over and above 15000 primary schools sanctioned in 2006-07 for which land is now available | 0 | Community Construction | 5.31 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| d. New school buildings sanctioned in 2006-07 (deferred liability of 2011-12) | 0 | Community Construction | 27.62 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| e. Building Less (Pry) | 0 | Community Construction | 0
| f. Deffered Liability of NSB 2014-15 | 0 | Community Construction | 0
| g. Funds sanctioned for NSBs of previous years | 0 | Community Construction | 0
| Sub Total of Primary Schools | 0 |  | 57.85
2 | Upper Primary
| a. Upper Primary (new) |  | Community Construction | 0
| b. ACR for new UPS Rural |  | Community Construction | 20.55 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| c. Building Less (UP) |  | Community Construction | 0
| Sub Total of Upper Primary Schools | 0 |  | 20.55
3 | Additional Class Room (without stairs) | 0 | Community Construction | 24.32 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
4 | Additional Class Room (with stairs) | 0 | Community Construction | 338.42 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
5 | ACR sanctioned Last Year | 0 | Community Construction | 0
| Sub-total of ACRs | 0 |  | 362.74
6 | Toilet/Urinals (Urban) |  | Community Construction | 0
7 | Separate Girls Toilet |  | Community Construction | 0
8 | Toilet, drinking water, child friendly elements and kitchen sheds for new UPS |  | Community Construction | 0
9 | Drinking Water Facility(Urban) | 0 | Community Construction | 0
10 | Construction of Building of residential schools for specific category of children | 0 | Community Construction | 0
11 | Ramps | 0 | Community Construction | 0
12 | Head Master's Room (Deffered Liability 2014-15) | 0 | Community Construction | 0
13 | Toilet - Boys (Special PAB) |  | Community Construction | 0
14 | Toilet - Girls (Special PAB) |  | Community Construction | 0
15 | Construction of KGBV Buildings |  | Open Tender | 0 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| Sub Total | 0 |  | 0
TOTAL |  | 0 | 441.14 | 441.14
Method of Procurement |  |  |  |  | Procurement Action 2017-18 Aug.: Procurement Actions
Community Construction |  |  |  |  | Procurement Action 2017-18 Aug.: 1. Preparation of Specifications and bids document
Open Tender |  |  |  |  | Procurement Action 2017-18 Aug.: 2. Issue of Invitation to bid
3. Open bids
4. Evaluation of bids
5. Award Contracts
6. Construction 25% complete
7. Construction 50% complete
8. Construction 75% complete
9. Construction 100% complete

## Muzafferpur
Typical Procurement Schedule for Civil Works (Spill Over) under SSA for the year 2017-18
Name of District : Muzaffarpur
Sl.No. | Description of Goods | Quantity in Numbers | Method of Procurement | Estimated Cost (Rs. In Lakh) | Procurement Action 2017-18
[5 empty] | April | May | June | July | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March
1 | Primary School
| a. New Primary School (Rural) | 0 | Community Construction | 0
| b. Primary schools sanctioned 2006-07 (deferred liability of 2008-09) | 0 | Community Construction | 0 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| c. Buildings for Primary Schools sanctioned over and above 15000 primary schools sanctioned in 2006-07 for which land is now available | 0 | Community Construction | 0
| d. New school buildings sanctioned in 2006-07 (deferred liability of 2011-12) | 0 | Community Construction | 0
| e. Building Less (Pry) | 0 | Community Construction | 0
| f. Deffered Liability of NSB 2014-15 | 0 | Community Construction | 0
| g. Funds sanctioned for NSBs of previous years | 0 | Community Construction | 0
| Sub Total of Primary Schools | 0 |  | 0
2 | Upper Primary
| a. Upper Primary (new) |  | Community Construction | 0
| b. ACR for new UPS Rural |  | Community Construction | 70.41 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| c. Building Less (UP) |  | Community Construction | 0
| Sub Total of Upper Primary Schools | 0 |  | 70.41
3 | Additional Class Room (without stairs) | 0 | Community Construction | 205.23 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
4 | Additional Class Room (with stairs) | 0 | Community Construction | 70 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
5 | ACR sanctioned Last Year | 0 | Community Construction | 0
| Sub-total of ACRs | 0 |  | 275.23
6 | Toilet/Urinals (Urban) |  | Community Construction | 0
7 | Separate Girls Toilet |  | Community Construction | 0
8 | Toilet, drinking water, child friendly elements and kitchen sheds for new UPS |  | Community Construction | 0
9 | Drinking Water Facility(Urban) | 0 | Community Construction | 0
10 | Construction of Building of residential schools for specific category of children | 0 | Community Construction | 0
11 | Ramps | 0 | Community Construction | 0
12 | Head Master's Room (Deffered Liability 2014-15) | 0 | Community Construction | 0
13 | Toilet - Boys (Special PAB) |  | Community Construction | 0
14 | Toilet - Girls (Special PAB) |  | Community Construction | 0
15 | Construction of KGBV Buildings |  | Open Tender | 0 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| Sub Total | 0 |  | 0
TOTAL |  | 0 | 345.64 | 345.64
Method of Procurement |  |  |  |  | Procurement Action 2017-18 Aug.: Procurement Actions
Community Construction |  |  |  |  | Procurement Action 2017-18 Aug.: 1. Preparation of Specifications and bids document
Open Tender |  |  |  |  | Procurement Action 2017-18 Aug.: 2. Issue of Invitation to bid
3. Open bids
4. Evaluation of bids
5. Award Contracts
6. Construction 25% complete
7. Construction 50% complete
8. Construction 75% complete
9. Construction 100% complete

## Munger
Typical Procurement Schedule for Civil Works (Spill Over) under SSA for the year 2017-18
Typical Procurement Schedule for Civil Works under SSA for the year 2016-17
Name of District : Munger
Procurement Action 2017-18
Sl.No. | Description of Goods | Quantity in Numbers | Method of Procurement | Estimated Cost (Rs. In Lakh) | Procurement Action 2016-17
[5 empty] | April | May | June | July | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March
1 | Primary School | 0
| a. New Primary School (Rural) | 0 | Community Construction | 0
| b. Primary schools sanctioned 2006-07 (deferred liability of 2008-09) | 0 | Community Construction | 0
| c. Buildings for Primary Schools sanctioned over and above 15000 primary schools sanctioned in 2006-07 for which land is now available | 0 | Community Construction | 0
| d. New school buildings sanctioned in 2006-07 (deferred liability of 2011-12) | 0 | Community Construction | 0.41 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| f. Deffered Liability of NSB 2014-15 | 0 | Community Construction | 0
| g. Funds sanctioned for NSBs of previous years | 0 | Community Construction | 0
| Sub Total of Primary Schools | 0 |  | 0.41
2 | Upper Primary
| a. Upper Primary (new) |  | Community Construction | 0
| b. ACR for new UPS Rural |  | Community Construction | 15.67 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| b. ACR for new UPS Rural |  | Community Construction | 0
| Sub Total of Upper Primary Schools | 0 |  | 15.67
3 | Additional Class Room (without stairs) | 0 | Community Construction | 139.91 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
4 | Additional Class Room (with stairs) | 0 | Community Construction | 190.61 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
5 | ACR sanctioned Last Year |  | Community Construction | 0
| Sub-total of ACRs | 0 |  | 330.52
6 | Toilet/Urinals (Urban) |  | Community Construction | 0
7 | Separate Girls Toilet | 0 | Community Construction | 0
8 | Toilet, drinking water, child friendly elements and kitchen sheds for new UPS | 0 | Community Construction | 0
9 | Drinking Water Facility(Urban) | 0 | Community Construction | 0
10 | Construction of Building of residential schools for specific category of children | 0 | Community Construction
11 | Ramps | 0 | Community Construction | 0
12 | Head Master's Room (Deffered Liability 2014-15) |  | Community Construction | 0
13 | Toilet - Boys (Special PAB) |  | Community Construction | 0
14 | Toilet - Girls (Special PAB) |  | Community Construction | 0
15 | Construction of KGBV Buildings |  | Open Tender | 0
| Sub Total | 0 |  | 0
TOTAL |  | 0 | 346.6 | 346.6
Method of Procurement |  |  |  |  | Procurement Action 2016-17 Aug.: Procurement Actions
Community Construction |  |  |  |  | Procurement Action 2016-17 Aug.: 1. Preparation of Specifications and bids document
Open Tender |  |  |  |  | Procurement Action 2016-17 Aug.: 2. Issue of Invitation to bid
3. Open bids
4. Evaluation of bids
5. Award Contracts
6. Construction 25% complete
7. Construction 50% complete
8. Construction 75% complete
9. Construction 100% complete

## Madhubani
Typical Procurement Schedule for Civil Works (Spill Over) under SSA for the year 2017-18
Name of District : Madhubani
Sl.No. | Description of Goods | Quantity in Numbers | Method of Procurement | Estimated Cost (Rs. In Lakh) | Procurement Action 2017-18
[5 empty] | April | May | June | July | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March
1 | Primary School
| a. New Primary School (Rural) | 0 | Community Construction | 11.5 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| b. Primary schools sanctioned 2006-07 (deferred liability of 2008-09) | 0 | Community Construction | 28 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| c. Buildings for Primary Schools sanctioned over and above 15000 primary schools sanctioned in 2006-07 for which land is now available | 0 | Community Construction | 0
| d. New school buildings sanctioned in 2006-07 (deferred liability of 2011-12) | 0 | Community Construction | 359.98 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| e. Building Less (Pry) | 0 | Community Construction | 0
| f. Deffered Liability of NSB 2014-15 | 0 | Community Construction | 0
| g. Funds sanctioned for NSBs of previous years | 0 | Community Construction | 0
| Sub Total of Primary Schools | 0 |  | 399.48
2 | Upper Primary
| a. Upper Primary (new) | 0 | Community Construction | 0
| b. ACR for new UPS Rural | 0 | Community Construction | 306.33 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| c. Building Less (UP) | 0 | Community Construction | 0
| Sub Total of Upper Primary Schools | 0 |  | 306.33
3 | Additional Class Room (without stairs) | 0 | Community Construction | 867.26 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
4 | Additional Class Room (with stairs) | 0 | Community Construction | 454.63 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
5 | ACR sanctioned Last Year | 0 | Community Construction | 0
| Sub-total of ACRs | 0 |  | 1321.89
6 | Toilet/Urinals (Urban) | 0 | Community Construction | 0
7 | Separate Girls Toilet | 0 | Community Construction | 0
8 | Toilet, drinking water, child friendly elements and kitchen sheds for new UPS | 0 | Community Construction | 0
9 | Drinking Water Facility(Urban) | 0 | Community Construction | 0
10 | Construction of Building of residential schools for specific category of children | 0 | Community Construction | 0
11 | Ramps | 0 | Community Construction | 0
12 | Head Master's Room (Deffered Liability 2014-15) | 0 | Community Construction | 0
13 | Toilet - Boys (Special PAB) |  | Community Construction | 0
14 | Toilet - Girls (Special PAB) |  | Community Construction | 0
15 | Construction of KGBV Buildings | 0 | Open Tender | 6.96 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| Sub Total | 0 |  | 6.96
TOTAL |  | 0 | 2027.7 | 2034.66
Method of Procurement |  |  |  |  | Procurement Action 2017-18 Aug.: Procurement Actions
Community Construction |  |  |  |  | Procurement Action 2017-18 Aug.: 1. Preparation of Specifications and bids document
Open Tender |  |  |  |  | Procurement Action 2017-18 Aug.: 2. Issue of Invitation to bid
3. Open bids
4. Evaluation of bids
5. Award Contracts
6. Construction 25% complete
7. Construction 50% complete
8. Construction 75% complete
9. Construction 100% complete

## Madhepura
Typical Procurement Schedule for Civil Works (Spill Over) under SSA for the year 2017-18
Name of District : MADHEPURA
Sl.No. | Description of Goods | Quantity in Numbers | Method of Procurement | Estimated Cost (Rs. In Lakh) | Procurement Action 2017-18
[5 empty] | April | May | June | July | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March
1 | Primary School
| a. New Primary School (Rural) | 0 | Community Construction | 23 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| b. Primary schools sanctioned 2006-07 (deferred liability of 2008-09) | 0 | Community Construction | 12.1 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| c. Buildings for Primary Schools sanctioned over and above 15000 primary schools sanctioned in 2006-07 for which land is now available | 0 | Community Construction | 0
| d. New school buildings sanctioned in 2006-07 (deferred liability of 2011-12) | 0 | Community Construction | 34.29 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| e. Building Less (Pry) | 0 | Community Construction | 0
| f. Deffered Liability of NSB 2014-15 | 0 | Community Construction | 0
| g. Funds sanctioned for NSBs of previous years | 0 | Community Construction | 0
| Sub Total of Primary Schools | 0 |  | 69.39
2 | Upper Primary
| a. Upper Primary (new) | 0 | Community Construction | 0
| b. ACR for new UPS Rural | 0 | Community Construction | 547.4 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| c. Building Less (UP) | 0 | Community Construction | 12.25 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| Sub Total of Upper Primary Schools | 0 |  | 559.65
3 | Additional Class Room (without stairs) | 0 | Community Construction | 10.49 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
4 | Additional Class Room (with stairs) | 0 | Community Construction | 1123.58 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
5 | ACR sanctioned Last Year | 0 | Community Construction | 0
| Sub-total of ACRs | 0 |  | 1134.07
6 | Toilet/Urinals (Urban) |  | Community Construction | 0
7 | Separate Girls Toilet | 0 | Community Construction | 0
8 | Toilet, drinking water, child friendly elements and kitchen sheds for new UPS | 0 | Community Construction | 0
9 | Drinking Water Facility(Urban) | 0 | Community Construction | 0
10 | Construction of Building of residential schools for specific category of children | 0 | Community Construction | 0
11 | Ramps | 0 | Community Construction | 0
12 | Head Master's Room (Deffered Liability 2014-15) | 0 | Community Construction | 0
13 | Toilet - Boys (Special PAB) | 0 | Community Construction | 0
14 | Toilet - Girls (Special PAB) | 0 | Community Construction | 0
15 | Construction of KGBV Buildings | 0 | Open Tender | 0 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| Sub Total | 0 |  | 0
TOTAL |  | 0 | 1763.11 | 1763.11
Method of Procurement |  |  |  |  | Procurement Action 2017-18 Aug.: Procurement Actions
Community Construction |  |  |  |  | Procurement Action 2017-18 Aug.: 1. Preparation of Specifications and bids document
Open Tender |  |  |  |  | Procurement Action 2017-18 Aug.: 2. Issue of Invitation to bid
3. Open bids
4. Evaluation of bids
5. Award Contracts
6. Construction 25% complete
7. Construction 50% complete
8. Construction 75% complete
9. Construction 100% complete

## Lakhisarai
Typical Procurement Schedule for Civil Works (Spill Over) under SSA for the year 2017-18
Name of District : Lakhisarai
Sl.No. | Description of Goods | Quantity in Numbers | Method of Procurement | Estimated Cost (Rs. In Lakh) | Procurement Action 2017-18
[5 empty] | April | May | June | July | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March
1 | Primary School
| a. Primary School (new) | 0 | Community Construction | 0
| b. Primary schools sanctioned 2006-07 (deferred liability of 2008-09) | 0 | Community Construction | 0 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| c. Buildings for Primary Schools sanctioned over and above 15000 primary schools sanctioned in 2006-07 for which land is now available | 0 | Community Construction | 1.25 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| d. New school buildings sanctioned in 2006-07 (deferred liability of 2011-12) | 0 | Community Construction | 0
| e. Building Less (Pry) | 0 | Community Construction | 0
| f. Deffered Liability of NSB 2014-15 | 0 | Community Construction | 0
| g. Funds sanctioned for NSBs of previous years | 0 | Community Construction | 0
| Sub Total of Primary Schools | 0 |  | 1.25
2 | Upper Primary
| a. Upper Primary (new) |  | Community Construction | 0
| b. ACR for new UPS Rural | 0 | Community Construction | 162.72 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| c. Building Less (UP) |  | Community Construction | 0
| Sub Total of Upper Primary Schools | 0 |  | 162.72
3 | Additional Class Room (without stairs) | 0 | Community Construction | 130.92 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
4 | Additional Class Room (with stairs) | 0 | Community Construction | 403.4 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
5 | ACR sanctioned Last Year | 0 | Community Construction | 0
| Sub-total of ACRs | 0 |  | 534.32
6 | Toilet/Urinals (Urban) |  | Community Construction | 0
7 | Separate Girls Toilet | 0 | Community Construction | 0
8 | Toilet, drinking water, child friendly elements and kitchen sheds for new UPS |  | Community Construction | 0
9 | Drinking Water Facility(Urban) | 0 | Community Construction | 0
10 | Construction of Building of residential schools for specific category of children | 0 | Community Construction | 0
11 | Ramps | 0 | Community Construction | 0
12 | Head Master's Room (Deffered Liability 2014-15) | 0 | Community Construction | 0
13 | Toilet - Boys (Special PAB) |  | Community Construction | 0
14 | Toilet - Girls (Special PAB) |  | Community Construction | 0
15 | Construction of KGBV Buildings | 0 | Open Tender | 6.92 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| Sub Total | 0 |  | 6.92
TOTAL |  | 0 | 698.29 | 705.21
Method of Procurement |  |  |  |  | Procurement Action 2017-18 Aug.: Procurement Actions
Community Construction |  |  |  |  | Procurement Action 2017-18 Aug.: 1. Preparation of Specifications and bids document
Open Tender |  |  |  |  | Procurement Action 2017-18 Aug.: 2. Issue of Invitation to bid
3. Open bids
4. Evaluation of bids
5. Award Contracts
6. Construction 25% complete
7. Construction 50% complete
8. Construction 75% complete
9. Construction 100% complete

## Kishanganj
Typical Procurement Schedule for Civil Works (Spill Over) under SSA for the year 2017-18
Name of District : KISHANGANJ
Sl.No. | Description of Goods | Quantity in Numbers | Method of Procurement | Estimated Cost (Rs. In Lakh) | Procurement Action 2017-18
[5 empty] | April | May | June | July | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March
1 | Primary School
| a. New Primary School (Rural) | 0 | Community Construction | 37.95 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| b. Primary schools sanctioned 2006-07 (deferred liability of 2008-09) | 0 | Community Construction | 15.52 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| c. Buildings for Primary Schools sanctioned over and above 15000 primary schools sanctioned in 2006-07 for which land is now available | 0 | Community Construction | 41.59 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| d. New school buildings sanctioned in 2006-07 (deferred liability of 2011-12) | 0 | Community Construction | 25.65 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| e. Building Less (Pry) | 0 | Community Construction | 0
| f. Deffered Liability of NSB 2014-15 | 0 | Community Construction | 0
| g. Funds sanctioned for NSBs of previous years | 0 | Community Construction | 0
| Sub Total of Primary Schools | 0 |  | 120.71
2 | Upper Primary
| a. Upper Primary (new) |  | Community Construction | 0
| b. ACR for new UPS | 0 | Community Construction | 0
| c. Building Less (UP) |  | Community Construction | 0
| Sub Total of Upper Primary Schools | 0 |  | 0
3 | Additional Class Room (without stairs) | 0 | Community Construction | 383.21 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
4 | Additional Class Room (with stairs) | 0 | Community Construction | 198.06 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
5 | ACR sanctioned Last Year | 0 | Community Construction | 0
| Sub-total of ACRs | 0 |  | 581.27
6 | Toilet/Urinals (Urban) |  | Community Construction | 0
7 | Separate Girls Toilet | 0 | Community Construction | 0
8 | Toilet, drinking water, child friendly elements and kitchen sheds for new UPS | 0 | Community Construction | 0
9 | Drinking Water Facility(Urban) | 0 | Community Construction | 0
10 | Construction of Building of residential schools for specific category of children | 0 | Community Construction | 0
11 | Ramps | 0 | Community Construction | 0
12 | Head Master's Room (Deffered Liability 2014-15) | 0 | Community Construction | 0
13 | Toilet - Boys (Special PAB) |  | Community Construction | 0
14 | Toilet - Girls (Special PAB) |  | Community Construction | 0
15 | Construction of KGBV Buildings |  | Community Construction/ Open Tender | 0 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| Sub Total | 0 |  | 0
TOTAL |  | 0 | 701.98 | 701.98
Method of Procurement |  |  |  |  | Procurement Action 2017-18 Aug.: Procurement Actions
Community Construction |  |  |  |  | Procurement Action 2017-18 Aug.: 1. Preparation of Specifications and bids document
Open Tender |  |  |  |  | Procurement Action 2017-18 Aug.: 2. Issue of Invitation to bid
3. Open bids
4. Evaluation of bids
5. Award Contracts
6. Construction 25% complete
7. Construction 50% complete
8. Construction 75% complete
9. Construction 100% complete
Primary School
a. Primary School (new)
b. Primary schools sanctioned 2006-07 (deferred liability of 2008-09)
c. New school buildings sanctioned in 2006-07 (deferred liability of 2010-11)
d. New school buildings sanctioned in 2006-07 (deferred liability of 201-12)
c. Building Less (Pry)
Sub Total of Primary Schools
Upper Primary
a. Upper Primary (new)
b. ACR for new UPS
c. Building Less (UP)
Sub Total of Upper Primary Schools
Additional Class Room (without stairs)
Additional Class Room (with stairs)
ACR sanctioned Last Year
Sub-total of ACRs
Toilet/Urinals (Urban)
Separate Girls Toilet
Disabled friendly toilet
Drinking Water Facility(Urban)
Toilets , drinking water, kitchen sheds etc for new UPS
Construction of Building of residential schools for specific category of children
Ramps
Total

## Khagaria
Typical Procurement Schedule for Civil Works (Spill Over) under SSA for the year 2017-18
Name of District : KHAGARIA
Sl.No. | Description of Goods | Quantity in Numbers | Method of Procurement | Estimated Cost (Rs. In Lakh) | Procurement Action 2017-18
[5 empty] | April | May | June | July | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March
1 | Primary School
| a. Primary School (new) | 0 | Community Construction | 0
| b. Primary schools sanctioned 2006-07 (deferred liability of 2008-09) | 0 | Community Construction | 8e-05
| c. Buildings for Primary Schools sanctioned over and above 15000 primary schools sanctioned in 2006-07 for which land is now available | 0 | Community Construction | 0
| d. New school buildings sanctioned in 2006-07 (deferred liability of 2011-12) | 0 | Community Construction | 0 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| e. Building Less (Pry) | 0 | Community Construction | 0
| f. Deffered Liability of NSB 2014-15 | 0 | Community Construction | 0
| g. Funds sanctioned for NSBs of previous years | 0 | Community Construction | 0
| Sub Total of Primary Schools | 0 |  | 8e-05
2 | Upper Primary
| a. Upper Primary (new) | 0 | Community Construction | 0
| b. ACR for new UPS Rural | 0 | Community Construction | 85.6 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| c. Building Less (UP) | 0 | Community Construction | 0
| Sub Total of Upper Primary Schools | 0 |  | 85.6
3 | Additional Class Room (without stairs) | 0 | Community Construction | 177.18 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
4 | Additional Class Room (with stairs) | 0 | Community Construction | 656.93 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
5 | ACR sanctioned Last Year | 0 | Community Construction | 0
| Sub-total of ACRs | 0 |  | 834.11
6 | Toilet/Urinals (Urban) | 0 | Community Construction | 0
7 | Separate Girls Toilet | 0 | Community Construction | 0
8 | Toilet, drinking water, child friendly elements and kitchen sheds for new UPS | 0 | Community Construction | 0
9 | Drinking Water Facility(Urban) | 0 | Community Construction | 0
10 | Construction of Building of residential schools for specific category of children | 0 | Community Construction | 0
11 | Ramps | 0 | Community Construction | 0
12 | Head Master's Room (Deffered Liability 2014-15) | 0 | Community Construction | 0
13 | Toilet - Boys (Special PAB) |  | Community Construction | 0
14 | Toilet - Girls (Special PAB) |  | Community Construction | 0
15 | Construction of KGBV Buildings | 0 | Open Tender | 3.9 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| Sub Total | 0 |  | 3.9
TOTAL |  | 0 | 919.7101 | 923.6101
Method of Procurement |  |  |  |  | Procurement Action 2017-18 Aug.: Procurement Actions
Community Construction |  |  |  |  | Procurement Action 2017-18 Aug.: 1. Preparation of Specifications and bids document
Open Tender |  |  |  |  | Procurement Action 2017-18 Aug.: 2. Issue of Invitation to bid
3. Open bids
4. Evaluation of bids
5. Award Contracts
6. Construction 25% complete
7. Construction 50% complete
8. Construction 75% complete
9. Construction 100% complete

## Katihar
Typical Procurement Schedule for Civil Works (Spill Over) under SSA for the year 2017-18
Name of District : KATIHAR
Sl.No. | Description of Goods | Quantity in Numbers | Method of Procurement | Estimated Cost (Rs. In Lakh) | Procurement Action 2017-18
[5 empty] | April | May | June | July | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March
1 | Primary School
| a. Primary School (new) | 0 | Community Construction | 0
| b. Primary schools sanctioned 2006-07 (deferred liability of 2008-09) | 0 | Community Construction | 157.57 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| c. Buildings for Primary Schools sanctioned over and above 15000 primary schools sanctioned in 2006-07 for which land is now available | 0 | Community Construction | 0
| d. New school buildings sanctioned in 2006-07 (deferred liability of 2011-12) | 0 | Community Construction | 63.61 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| e. Building Less (Pry) | 0 | Community Construction | 0
| f. Deffered Liability of NSB 2014-15 | 0 | Community Construction | 0
| g. Funds sanctioned for NSBs of previous years | 0 | Community Construction | 0
| Sub Total of Primary Schools | 0 |  | 221.18
2 | Upper Primary
| a. Upper Primary (new) |  | Community Construction | 0
| b. ACR for new UPS Rural |  | Community Construction | 63.75 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| c. Building Less (UP) |  | Community Construction | 0
| Sub Total of Upper Primary Schools | 0 |  | 63.75
3 | Additional Class Room (without stairs) | 0 | Community Construction | 172.6 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
4 | Additional Class Room (with stairs) | 0 | Community Construction | 801.69 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
5 | ACR sanctioned Last Year | 0 | Community Construction | 0
| Sub-total of ACRs | 0 |  | 974.29
6 | Toilet/Urinals (Urban) |  | Community Construction | 0
7 | Separate Girls Toilet |  | Community Construction | 0
8 | Toilet, drinking water, child friendly elements and kitchen sheds for new UPS |  | Community Construction | 0
9 | Drinking Water Facility(Urban) | 0 | Community Construction | 0
10 | Construction of Building of residential schools for specific category of children | 0 | Community Construction | 0
11 | Ramps | 0 | Community Construction | 0
12 | Head Master's Room (Deffered Liability 2014-15) | 0 | Community Construction | 0
13 | Toilet - Boys (Special PAB) | 0 | Community Construction | 0
14 | Toilet - Girls (Special PAB) | 0 | Community Construction | 0
15 | Construction of KGBV Buildings |  | Open Tender | 2.71 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| Sub Total | 0 |  | 2.71
TOTAL |  | 0 | 1259.22 | 1261.93
Method of Procurement |  |  |  |  | Procurement Action 2017-18 Aug.: Procurement Actions
Community Construction |  |  |  |  | Procurement Action 2017-18 Aug.: 1. Preparation of Specifications and bids document
Open Tender |  |  |  |  | Procurement Action 2017-18 Aug.: 2. Issue of Invitation to bid
3. Open bids
4. Evaluation of bids
5. Award Contracts
6. Construction 25% complete
7. Construction 50% complete
8. Construction 75% complete
9. Construction 100% complete

## Kaimur
Typical Procurement Schedule for Civil Works (Spill Over) under SSA for the year 2017-18
Name of District : Kaimur
Sl.No. | Description of Goods | Quantity in Numbers | Method of Procurement | Estimated Cost (Rs. In Lakh) | Procurement Action 2017-18
[5 empty] | April | May | June | July | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March
1 | Primary School
| a. Primary School (new) | 0 | Community Construction | 0
| b. Primary schools sanctioned 2006-07 (deferred liability of 2008-09) | 0 | Community Construction | 0
| c. Buildings for Primary Schools sanctioned over and above 15000 primary schools sanctioned in 2006-07 for which land is now available | 0 | Community Construction | 16.11 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| d. New school buildings sanctioned in 2006-07 (deferred liability of 2011-12) | 0 | Community Construction | 37.85 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| e. Building Less (Pry) | 0 | Community Construction | 0
| f. Deffered Liability of NSB 2014-15 | 0 | Community Construction | 0
| g. Funds sanctioned for NSBs of previous years | 0 | Community Construction | 0
| Sub Total of Primary Schools | 0 |  | 53.96
2 | Upper Primary
| a. Upper Primary (new) |  | Community Construction | 0
| b. ACR for new UPS Rural |  | Community Construction | 29.58 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| c. Building Less (UP) |  | Community Construction | 0
| Sub Total of Upper Primary Schools | 0 |  | 29.58
3 | Additional Class Room (without stairs) | 0 | Community Construction | 32.93 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
4 | Additional Class Room (with stairs) | 0 | Community Construction | 26.94 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
5 | ACR sanctioned Last Year | 0 | Community Construction | 0
| Sub-total of ACRs | 0 |  | 59.87
6 | Toilet/Urinals (Urban) | 0 | Community Construction | 0
7 | Separate Girls Toilet | 0 | Community Construction | 0
8 | Toilet, drinking water, child friendly elements and kitchen sheds for new UPS | 0 | Community Construction | 0
9 | Drinking Water Facility(Urban) | 0 | Community Construction | 0
10 | Construction of Building of residential schools for specific category of children | 0 | Community Construction | 0
11 | Ramps | 0 | Community Construction | 0
12 | Head Master's Room sanctioned (deferred liability of 2014-15) | 0 | Community Construction | 0
13 | Toilet - Boys (Special PAB) | 0 | Community Construction | 0
14 | Toilet - Girls (Special PAB) | 0 | Community Construction | 0
15 | Construction of KGBV Buildings | 0 | Community Construction/ Open Tender |  | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| Sub Total | 0 |  | 0
TOTAL |  | 0 | 143.41 | 143.41
Method of Procurement |  |  |  |  | Procurement Action 2017-18 Aug.: Procurement Actions
Community Construction |  |  |  |  | Procurement Action 2017-18 Aug.: 1. Preparation of Specifications and bids document
Open Tender |  |  |  |  | Procurement Action 2017-18 Aug.: 2. Issue of Invitation to bid
3. Open bids
4. Evaluation of bids
5. Award Contracts
6. Construction 25% complete
7. Construction 50% complete
8. Construction 75% complete
9. Construction 100% complete

## Jehanabad
Typical Procurement Schedule for Civil Works (Spill Over) under SSA for the year 2017-18
Name of District : Jehanabad
Sl.No. | Description of Goods | Quantity in Numbers | Method of Procurement | Estimated Cost (Rs. In Lakh) | Procurement Action 2017-18
[5 empty] | April | May | June | July | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March
1 | Primary School
| a. New Primary School (Rural) | 0 | Community Construction | 4.38 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| b. Primary schools sanctioned 2006-07 (deferred liability of 2008-09) | 0 | Community Construction | 0
| c. Buildings for Primary Schools sanctioned over and above 15000 primary schools sanctioned in 2006-07 for which land is now available | 0 | Community Construction | 19.91 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| d. New school buildings sanctioned in 2006-07 (deferred liability of 2011-12) | 0 | Community Construction | 0
| e. Building Less (Pry) | 0 | Community Construction | 0
| f. Deffered Liability of NSB 2014-15 | 0 | Community Construction | 0
| g. Funds sanctioned for NSBs of previous years | 0 | Community Construction | 0
| Sub Total of Primary Schools | 0 |  | 24.29
2 | Upper Primary
| a. Upper Primary (new) |  | Community Construction | 0
| b. ACR for new UPS Rural |  | Community Construction | 26.44 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| c. Building Less (UP) |  | Community Construction | 0
| Sub Total of Upper Primary Schools | 0 |  | 26.44
3 | Additional Class Room (without stairs) | 0 | Community Construction | 263.28 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
4 | Additional Class Room (with stairs) | 0 | Community Construction | 576.46 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
5 | ACR sanctioned Last Year | 0 | Community Construction | 0
| Sub-total of ACRs | 0 |  | 839.74
6 | Toilet/Urinals (Urban) | 0 | Community Construction | 0
7 | Separate Girls Toilet | 0 | Community Construction | 0
8 | Toilet, drinking water, child friendly elements and kitchen sheds for new UPS |  | Community Construction | 0
9 | Drinking Water Facility(Urban) | 0 | Community Construction | 0
10 | Construction of Building of residential schools for specific category of children | 0 | Community Construction | 0
11 | Ramps | 0 | Community Construction | 0
12 | Head Master's Room (Deffered Liability 2014-15) | 0 | Community Construction | 0
13 | Toilet - Boys (Special PAB) |  | Community Construction | 0
14 | Toilet - Girls (Special PAB) |  | Community Construction | 0
15 | Construction of KGBV Buildings |  | Open Tender | 11.25 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| Sub Total | 0 |  | 11.25
TOTAL |  | 0 | 890.47 | 901.72
Method of Procurement |  |  |  |  | Procurement Action 2017-18 Aug.: Procurement Actions
Community Construction |  |  |  |  | Procurement Action 2017-18 Aug.: 1. Preparation of Specifications and bids document
Open Tender |  |  |  |  | Procurement Action 2017-18 Aug.: 2. Issue of Invitation to bid
3. Open bids
4. Evaluation of bids
5. Award Contracts
6. Construction 25% complete
7. Construction 50% complete
8. Construction 75% complete
9. Construction 100% complete

## Jamui
Typical Procurement Schedule for Civil Works (Spill Over) under SSA for the year 2017-18
Name of District : JAMUI
Sl.No. | Description of Goods | Quantity in Numbers | Method of Procurement | Estimated Cost (Rs. In Lakh) | Procurement Action 2017-18
[5 empty] | April | May | June | July | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March
1 | Primary School
| a. New Primary School (Rural) | 0 | Community Construction | 95.31 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| b. Primary schools sanctioned 2006-07 (deferred liability of 2008-09) | 0 | Community Construction | 133.55 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| c. Buildings for Primary Schools sanctioned over and above 15000 primary schools sanctioned in 2006-07 for which land is now available | 0 | Community Construction | 84.08 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| d. New school buildings sanctioned in 2006-07 (deferred liability of 2011-12) | 0 | Community Construction | 15.68 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| e. Building Less (Pry) | 0 | Community Construction | 0
| f. Deffered Liability of NSB 2014-15 | 0 | Community Construction | 0
| g. Funds sanctioned for NSBs of previous years | 0 | Community Construction | 0
| Sub Total of Primary Schools | 0 |  | 328.62
2 | Upper Primary
| a. Upper Primary (new) | 0 | Community Construction | 0
| b. ACR for new UPS Rural | 0 | Community Construction | 15.12 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| c. Building Less (UP) | 0 | Community Construction | 0
| Sub Total of Upper Primary Schools | 0 |  | 15.12
3 | Additional Class Room (without stairs) | 0 | Community Construction | 120.06 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
4 | Additional Class Room (with stairs) | 0 | Community Construction | 58.01 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
5 | ACR sanctioned Last Year | 0 | Community Construction | 0
| Sub-total of ACRs | 0 |  | 178.07
6 | Toilet/Urinals (Urban) | 0 | Community Construction | 0
7 | Separate Girls Toilet | 0 | Community Construction | 0
8 | Toilet, drinking water, child friendly elements and kitchen sheds for new UPS | 0 | Community Construction | 0
9 | Drinking Water Facility(Urban) | 0 | Community Construction | 0
10 | Construction of Building of residential schools for specific category of children | 0 | Community Construction | 0
11 | Ramps | 0 | Community Construction | 0
12 | Head Master's Room (Deffered Liability 2014-15) | 0 | Community Construction | 0
13 | Toilet - Boys (Special PAB) |  | Community Construction | 0
14 | Toilet - Girls (Special PAB) |  | Community Construction | 0
15 | Construction of KGBV Buildings | 0 | Open Tender | 0 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| Sub Total | 0 |  | 0
TOTAL |  | 0 | 521.81 | 521.81
Method of Procurement |  |  |  |  | Procurement Action 2017-18 Aug.: Procurement Actions
Community Construction |  |  |  |  | Procurement Action 2017-18 Aug.: 1. Preparation of Specifications and bids document
Open Tender |  |  |  |  | Procurement Action 2017-18 Aug.: 2. Issue of Invitation to bid
3. Open bids
4. Evaluation of bids
5. Award Contracts
6. Construction 25% complete
7. Construction 50% complete
8. Construction 75% complete
9. Construction 100% complete

## Gopalganj
Typical Procurement Schedule for Civil Works (Spill Over) under SSA for the year 2017-18
Name of District : GOPALGANJ
Sl.No. | Description of Goods | Quantity in Numbers | Method of Procurement | Estimated Cost (Rs. In Lakh) | Procurement Action 2017-18
[5 empty] | April | May | June | July | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March
1 | Primary School
| a. Primary School (new) | 0 | Community Construction | 0
| b. Primary schools sanctioned 2006-07 (deferred liability of 2008-09) | 0 | Community Construction | 0
| c. Buildings for Primary Schools sanctioned over and above 15000 primary schools sanctioned in 2006-07 for which land is now available | 0 | Community Construction | 0
| d. New school buildings sanctioned in 2006-07 (deferred liability of 2011-12) | 0 | Community Construction | 0
| e. Building Less (Pry) | 0 | Community Construction | 0
| f. Deffered Liability of NSB 2014-15 | 0 | Community Construction | 0
| g. Funds sanctioned for NSBs of previous years | 0 | Community Construction | 0
| Sub Total of Primary Schools | 0 |  | 0
2 | Upper Primary
| a. Upper Primary (new) |  | Community Construction | 0
| b. ACR for new UPS (Rural) |  | Community Construction | 217.32 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| c. Building Less (UP) |  | Community Construction | 0
| Sub Total of Upper Primary Schools | 0 |  | 217.32
3 | Additional Class Room (without stairs) | 0 | Community Construction | 628.82 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
4 | Additional Class Room (with stairs) | 0 | Community Construction | 424.13 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
5 | ACR sanctioned Last Year | 0 | Community Construction | 0
| Sub-total of ACRs | 0 |  | 1052.95
6 | Toilet/Urinals (Urban) |  | Community Construction | 0
7 | Separate Girls Toilet |  | Community Construction | 0
8 | Toilet, drinking water, child friendly elements and kitchen sheds for new UPS |  | Community Construction | 0
9 | Drinking Water Facility(Urban) | 0 | Community Construction | 0
10 | Construction of Building of residential schools for specific category of children | 0 | Community Construction | 0
11 | Ramps | 0 | Community Construction | 0
12 | Head Master's Room (Deffered Liability 2014-15) | 0 | Community Construction | 0
13 | Toilet - Boys (Special PAB) |  | Community Construction
14 | Toilet - Girls (Special PAB) |  | Community Construction
15 | Construction of KGBV Buildings |  | Open Tender | 0 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| Sub Total | 0 |  | 0
TOTAL |  | 0 | 1270.27 | 1270.27
Method of Procurement |  |  |  |  | Procurement Action 2017-18 Aug.: Procurement Actions
Community Construction |  |  |  |  | Procurement Action 2017-18 Aug.: 1. Preparation of Specifications and bids document
Open Tender |  |  |  |  | Procurement Action 2017-18 Aug.: 2. Issue of Invitation to bid
3. Open bids
4. Evaluation of bids
5. Award Contracts
6. Construction 25% complete
7. Construction 50% complete
8. Construction 75% complete
9. Construction 100% complete

## Gaya
Typical Procurement Schedule for Civil Works (Spill Over) under SSA for the year 2017-18
Name of District : GAYA
Sl.No. | Description of Goods | Quantity in Numbers | Method of Procurement | Estimated Cost (Rs. In Lakh) | Procurement Action 2017-18
[5 empty] | April | May | June | July | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March
1 | Primary School
| a. Primary School (new) | 0 | Community Construction | 0
| b. Primary schools sanctioned 2006-07 (deferred liability of 2008-09) | 0 | Community Construction | 4.88 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| c. Buildings for Primary Schools sanctioned over and above 15000 primary schools sanctioned in 2006-07 for which land is now available | 0 | Community Construction | 99.09 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| d. New school buildings sanctioned in 2006-07 (deferred liability of 2011-12) | 0 | Community Construction | 19.101 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| e. Building Less (Pry) | 0 | Community Construction | 0
| f. Deffered Liability of NSB 2014-15 | 0 | Community Construction | 0
| g. Funds sanctioned for NSBs of previous years | 0 | Community Construction | 0
| Sub Total of Primary Schools | 0 |  | 123.071
2 | Upper Primary
| a. Upper Primary (new) |  | Community Construction | 0
| b. ACR for new UPS (Rural) | 0 | Community Construction | 148.16 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| c. Building Less (UP) | 0 | Community Construction | 0
| Sub Total of Upper Primary Schools | 0 |  | 148.16
3 | Additional Class Room (without stairs) | 0 | Community Construction | 617.93 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
4 | Additional Class Room (with stairs) | 0 | Community Construction | 442.22 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
5 | ACR sanctioned Last Year | 0 | Community Construction | 0
| Sub-total of ACRs | 0 |  | 1060.15
6 | Toilet/Urinals (Urban) | 0 | Community Construction | 0
7 | Separate Girls Toilet | 0 | Community Construction | 0
8 | Toilet, drinking water, child friendly elements and kitchen sheds for new UPS | 0 | Community Construction | 0
9 | Drinking Water Facility(Urban) | 0 | Community Construction | 0
10 | Construction of Building of residential schools for specific category of children | 0 | Community Construction | 0
11 | Ramps | 0 | Community Construction | 0
12 | Head Master's Room (Deffered Liability 2014-15) | 0 | Community Construction | 0
13 | Toilet - Boys (Special PAB) |  | Community Construction
14 | Toilet - Girls (Special PAB) |  | Community Construction
15 | Construction of KGBV Buildings | 0 | Open Tender | 12.21 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| Sub Total | 0 |  | 12.21
TOTAL |  | 0 | 1331.381 | 1343.591
Method of Procurement |  |  |  |  | Procurement Action 2017-18 Aug.: Procurement Actions
Community Construction |  |  |  |  | Procurement Action 2017-18 Aug.: 1. Preparation of Specifications and bids document
Open Tender |  |  |  |  | Procurement Action 2017-18 Aug.: 2. Issue of Invitation to bid
3. Open bids
4. Evaluation of bids
5. Award Contracts
6. Construction 25% complete
7. Construction 50% complete
8. Construction 75% complete
9. Construction 100% complete

## East Champaran
Typical Procurement Schedule for Civil Works (Spill Over) under SSA for the year 2017-18
Name of District : East Champaran
Sl.No. | Description of Goods | Quantity in Numbers | Method of Procurement | Estimated Cost (Rs. In Lakh) | Procurement Action 2017-18
[5 empty] | April | May | June | July | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March
1 | Primary School
| a.New Primary School (new) - Rural | 0 | Community Construction | 0
| b. Primary schools sanctioned 2006-07 (deferred liability of 2008-09) | 0 | Community Construction | 343.03 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| c. Buildings for Primary Schools sanctioned over and above 15000 primary schools sanctioned in 2006-07 for which land is now available | 0 | Community Construction | 0
| d. New school buildings sanctioned in 2006-07 (deferred liability of 2011-12) | 0 | Community Construction | 0 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| e. Building Less (Pry) | 0 | Community Construction | 0
| f. Deffered Liability of NSB 2014-15 | 0 | Community Construction | 0
| g. Funds sanctioned for NSBs of previous years | 0 | Community Construction | 0
| Sub Total of Primary Schools | 0 |  | 343.03
2 | Upper Primary
| a. Upper Primary (new) |  | Community Construction | 0
| b. ACR for new UPS (Rural) |  | Community Construction | 108.19 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| c. Building Less (UP) |  | Community Construction | 0
| Sub Total of Upper Primary Schools | 0 |  | 108.19
3 | Additional Class Room (without stairs) | 0 | Community Construction | 400.31 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
4 | Additional Class Room (with stairs) | 0 | Community Construction | 207.67 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
5 | ACR sanctioned Last Year | 0 | Community Construction | 0
| Sub-total of ACRs | 0 |  | 607.98
6 | Toilet/Urinals (Urban) |  | Community Construction | 0
7 | Separate Girls Toilet |  | Community Construction | 0
8 | Toilet, drinking water, child friendly elements and kitchen sheds for new UPS |  | Community Construction | 0
9 | Drinking Water Facility(Urban) | 0 | Community Construction | 0
10 | Construction of Building of residential schools for specific category of children | 0 | Community Construction | 0
11 | Ramps | 0 | Community Construction | 0
12 | Head Master's Room (Deffered Liability 2014-15) | 0 | Community Construction | 0
13 | Toilet - Boys (Special PAB) | 0 | Community Construction | 0
14 | Toilet - Girls (Special PAB) |  | Community Construction | 0
15 | Construction of KGBV Buildings |  | Open Tender | 18.12 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| Sub Total | 0 |  | 18.12
TOTAL |  | 0 | 1059.2 | 1077.32
Method of Procurement |  |  |  |  | Procurement Action 2017-18 Aug.: Procurement Actions
Community Construction |  |  |  |  | Procurement Action 2017-18 Aug.: 1. Preparation of Specifications and bids document
Open Tender |  |  |  |  | Procurement Action 2017-18 Aug.: 2. Issue of Invitation to bid
3. Open bids
4. Evaluation of bids
5. Award Contracts
6. Construction 25% complete
7. Construction 50% complete
8. Construction 75% complete
9. Construction 100% complete

## Darbhanga
Typical Procurement Schedule for Civil Works (Spill Over) under SSA for the year 2017-18
Name of District : Darbhanga
Sl.No. | Description of Goods | Quantity in Numbers | Method of Procurement | Estimated Cost (Rs. In Lakh) | Procurement Action 2017-18
[5 empty] | April | May | June | July | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March
1 | Primary School
| a. Primary School (new) | 0 | Community Construction | 0
| b. Primary schools sanctioned 2006-07 (deferred liability of 2008-09) | 0 | Community Construction | 3.33 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| c. Buildings for Primary Schools sanctioned over and above 15000 primary schools sanctioned in 2006-07 for which land is now available | 0 | Community Construction | 20.23 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| d. New school buildings sanctioned in 2006-07 (deferred liability of 2011-12) | 0 | Community Construction | 49.39 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| e. Building Less (Pry) | 0 | Community Construction | 0
| f. Deffered Liability of NSB 2014-15 (primary school sanctioned in 2006-07) | 0 | Community Construction | 0
| g. Funds sanctioned for NSBs of previous years | 0 | Community Construction | 0
| Sub Total of Primary Schools | 0 |  | 72.95
2 | Upper Primary
| a. Upper Primary (new) |  | Community Construction | 0
| b. ACR for new UPS (Rural) |  | Community Construction | 51.82 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| c. Building Less (UP) |  | Community Construction | 0
| Sub Total of Upper Primary Schools | 0 |  | 51.82
3 | Additional Class Room (without stairs) | 0 | Community Construction | 509.52 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
4 | Additional Class Room (with stairs) | 0 | Community Construction | 478.99 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
5 | ACR sanctioned Last Year | 0 | Community Construction | 0
| Sub-total of ACRs | 0 |  | 988.51
6 | Toilet/Urinals (Urban) |  | Community Construction | 0
7 | Separate Girls Toilet |  | Community Construction | 0
8 | Toilet, drinking water, child friendly elements and kitchen sheds for new UPS |  | Community Construction | 0
9 | Drinking Water Facility(Urban) | 0 | Community Construction | 0
10 | Construction of Building of residential schools for specific category of children | 0 | Community Construction | 0
11 | Ramps | 0 | Community Construction | 0
12 | Head Master's Room (Deffered Liability 2014-15) | 0 | Community Construction | 0
13 | Toilet - Boys (Special PAB) | 0 | Community Construction | 0
14 | Toilet - Girls (Special PAB) | 0 | Community Construction | 0
15 | Construction of KGBV Buildings |  | Open Tender | 0 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| Sub Total | 0 |  | 0
TOTAL |  | 0 | 1113.28 | 1113.28
Method of Procurement |  |  |  |  | Procurement Action 2017-18 Aug.: Procurement Actions
Community Construction |  |  |  |  | Procurement Action 2017-18 Aug.: 1. Preparation of Specifications and bids document
Open Tender |  |  |  |  | Procurement Action 2017-18 Aug.: 2. Issue of Invitation to bid
3. Open bids
4. Evaluation of bids
5. Award Contracts
6. Construction 25% complete
7. Construction 50% complete
8. Construction 75% complete
9. Construction 100% complete

## Buxar
Typical Procurement Schedule for Civil Works (Spill Over) under SSA for the year 2017-18
Name of District : Buxar
Sl.No. | Description of Goods | Quantity in Numbers | Method of Procurement | Estimated Cost (Rs. In Lakh) | Procurement Action 2017-18
[5 empty] | April | May | June | July | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March
1 | Primary School
| a. Primary School Rural (new) | 0 | Community Construction | 0
| b. Primary schools sanctioned 2006-07 (deferred liability of 2008-09) | 0 | Community Construction | 26.57 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| c. Buildings for Primary Schools sanctioned over and above 15000 primary schools sanctioned in 2006-07 for which land is now available | 0 | Community Construction | 90.87 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| d. New school buildings sanctioned in 2006-07 (deferred liability of 2011-12) | 0 | Community Construction | 8.01 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| e. Building Less (Pry) | 0 | Community Construction | 0
| f. Deffered Liability of NSB 2014-15 (primary school sanctioned in 06-07) | 0 | Community Construction | 0
| g. Funds sanctioned for NSBs of previous years | 0 | Community Construction | 0
| Sub Total of Primary Schools | 0 | 0 | 125.45
2 | Upper Primary
| a. Upper Primary (new) |  | Community Construction | 0
| b. ACR for new UPS (Rural) |  | Community Construction | 24.79 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| c. Building Less (UP) |  | Community Construction | 0
| Sub Total of Upper Primary Schools | 0 |  | 24.79
3 | Additional Class Room (without stairs) |  | Community Construction | 236.47 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
4 | Additional Class Room (with stairs) |  | Community Construction | 107.76 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
5 | ACR sanctioned Last Year | 0 | Community Construction | 0
| Sub-total of ACRs | 0 |  | 344.23
6 | Toilet/Urinals (Urban) | 0 | Community Construction | 0
7 | Separate Girls Toilet |  | Community Construction | 0
8 | Toilet, drinking water, child friendly elements and kitchen sheds for new UPS |  | Community Construction | 0
9 | Drinking Water Facility(Urban) | 0 | Community Construction | 0
10 | Construction of Building of residential schools for specific category of children | 0 | Community Construction | 0
11 | Ramps | 0 | Community Construction | 0
12 | Head Master's Room (Deffered Liability 2014-15) | 0 | Community Construction | 0
13 | Toilet - Boys (Special PAB) |  | Community Construction | 0
14 | Toilet - Girls (Special PAB) |  | Community Construction | 0
15 | Construction of KGBV Buildings | 0 | Open Tender | 21.21 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| Sub Total | 0 |  | 21.21
TOTAL |  | 0 | 494.47 | 515.68
Method of Procurement |  |  |  |  | Procurement Action 2017-18 Aug.: Procurement Actions
Community Construction |  |  |  |  | Procurement Action 2017-18 Aug.: 1. Preparation of Specifications and bids document
Open Tender |  |  |  |  | Procurement Action 2017-18 Aug.: 2. Issue of Invitation to bid
3. Open bids
4. Evaluation of bids
5. Award Contracts
6. Construction 25% complete
7. Construction 50% complete
8. Construction 75% complete
9. Construction 100% complete

## Bhojpur
Typical Procurement Schedule for Civil Works (Spill Over) under SSA for the year 2017-18
Name of District : Bhojpur
Sl.No. | Description of Goods | Quantity in Numbers | Method of Procurement | Estimated Cost (Rs. In Lakh) | Procurement Action 2017-18
[5 empty] | April | May | June | July | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March
1 | Primary School
| a. Primary School Rural (new) | 0 | Community Construction | 43.81 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| b. Primary schools sanctioned 2006-07 (deferred liability of 2008-09) | 0 | Community Construction | 47.04 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| c. Buildings for Primary Schools sanctioned over and above 15000 primary schools sanctioned in 2006-07 for which land is now available | 0 | Community Construction | 0
| d. New school buildings sanctioned in 2006-07 (deferred liability of 2011-12) | 0 | Community Construction | 44.51 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| e. Building Less (Pry) | 0 | Community Construction | 0
| f. Deffered Liability of NSB 2014-15 | 0 | Community Construction | 0
| g. Funds sanctioned for NSBs of previous years | 0 | Community Construction | 0
| Sub Total of Primary Schools | 0 |  | 135.36
2 | Upper Primary
| a. Upper Primary (new) |  | Community Construction | 0
| b. ACR for new UPS (Rural) |  | Community Construction | 245.67 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| c. Building Less (UP) |  | Community Construction | 0
| Sub Total of Upper Primary Schools | 0 |  | 245.67
3 | Additional Class Room (without stairs) |  | Community Construction | 144.61 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
4 | Additional Class Room (with stairs) |  | Community Construction | 275.94 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
5 | ACR sanctioned Last Year | 0 | Community Construction | 0
| Sub-total of ACRs | 0 |  | 420.55
6 | Toilet/Urinals (Urban) |  | Community Construction | 0
7 | Separate Girls Toilet |  | Community Construction | 0
8 | Toilet, drinking water, child friendly elements and kitchen sheds for new UPS |  | Community Construction | 0
9 | Drinking Water Facility(Urban) | 0 | Community Construction | 0
10 | Construction of Building of residential schools for specific category of children | 0 | Community Construction | 0
11 | Ramps | 0 | Community Construction | 0
12 | Head Master's Room (Deffered Liability 2014-15) | 0 | Community Construction | 0
13 | Toilet - Boys (Special PAB) | 0 | Community Construction | 0
14 | Toilet - Girls (Special PAB) | 0 | Community Construction | 0
15 | Construction of KGBV Buildings |  | Open Tender | 36.61 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| Sub Total | 0 |  | 36.61
TOTAL |  | 0 | 801.58 | 838.19
Method of Procurement |  |  |  |  | Procurement Action 2017-18 Aug.: Procurement Actions
Community Construction |  |  |  |  | Procurement Action 2017-18 Aug.: 1. Preparation of Specifications and bids document
Open Tender |  |  |  |  | Procurement Action 2017-18 Aug.: 2. Issue of Invitation to bid
3. Open bids
4. Evaluation of bids
5. Award Contracts
6. Construction 25% complete
7. Construction 50% complete
8. Construction 75% complete
9. Construction 100% complete

## Bhagalpur
Typical Procurement Schedule for Civil Works (Spill Over) under SSA for the year 2017-18
Name of District : Bhagalpur |  | Spillover
Sl.No. | Description of Goods | Quantity in Numbers | Method of Procurement | Estimated Cost (Rs. In Lakh) | Procurement Action 2017-18
[5 empty] | April | May | June | July | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March
1 | Primary School
| a. Primary School (new) | 0 | Community Construction | 0
| b. Primary schools sanctioned 2006-07 (deferred liability of 2008-09) | 0 | Community Construction | 30.71 |  |  |  |  | 8-9 | 8-9 | 8-9 | 8-9 | 8-9 | 8-9 | 8-9 | 8-9
| c. Buildings for Primary Schools sanctioned over and above 15000 primary schools sanctioned in 2006-07 for which land is now available | 0 | Community Construction | 0
| d. New school buildings sanctioned in 2006-07 (deferred liability of 2011-12) | 0 | Community Construction | 80.77 |  |  |  |  | 8-9 | 8-9 | 8-9 | 8-9 | 8-9 | 8-9 | 8-9 | 8-9
| e. Building Less (Pry) | 0 | Community Construction | 0
| f. Deffered Liability of NSB 2014-15 | 0 | Community Construction | 0
| g. Funds sanctioned for NSBs of previous years | 0 | Community Construction | 0
| Sub Total of Primary Schools | 0 |  | 111.48
2 | Upper Primary
| a. Upper Primary (new) |  | Community Construction | 0
| b. ACR for new UPS (Rural) |  | Community Construction | 2.09 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| c. Building Less (UP) |  | Community Construction | 0
| Sub Total of Upper Primary Schools | 0 |  | 2.09
3 | Additional Class Room (without stairs) | 0 | Community Construction | 462.26 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
4 | Additional Class Room (with stairs) | 0 | Community Construction | 511.78 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
5 | ACR sanctioned Last Year | 0 | Community Construction | 0
| Sub-total of ACRs | 0 |  | 974.04
6 | Toilet/Urinals (Urban) |  | Community Construction | 0
7 | Separate Girls Toilet |  | Community Construction | 0
8 | Toilet, drinking water, child friendly elements and kitchen sheds for new UPS |  | Community Construction | 0
9 | Drinking Water Facility(Urban) | 0 | Community Construction | 0
10 | Construction of Building of residential schools for specific category of children | 0 | Community Construction | 0
11 | Ramps | 0 | Community Construction | 0
12 | Head Master's Room (Deffered Liability 2014-15) | 0 | Community Construction | 0
13 | Toilet - Boys (Special PAB) |  | Community Construction | 0
14 | Toilet - Girls (Special PAB) |  | Community Construction | 0
15 | Construction of KGBV Buildings |  | Community Construction | 2.87 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| Sub Total | 0 |  | 2.87
TOTAL |  | 0 | 1087.61 | 1090.48
Method of Procurement |  |  |  |  | Procurement Action 2017-18 Aug.: Procurement Actions
Community Construction |  |  |  |  | Procurement Action 2017-18 Aug.: 1. Preparation of Specifications and bids document
Open Tender |  |  |  |  | Procurement Action 2017-18 Aug.: 2. Issue of Invitation to bid
3. Open bids
4. Evaluation of bids
5. Award Contracts
6. Construction 25% complete
7. Construction 50% complete
8. Construction 75% complete
9. Construction 100% complete

## Begusarai
Typical Procurement Schedule for Civil Works (Spill Over) under SSA for the year 2017-18
Name of District : Begusarai
Sl.No. | Description of Goods | Quantity in Numbers | Method of Procurement | Estimated Cost (Rs. In Lakh) | Procurement Action 2017-18
[5 empty] | April | May | June | July | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March
1 | Primary School
| a. Primary School Rural (new) | 0 | Community Construction | 5.9 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| b. Primary schools sanctioned 2006-07 (deferred liability of 2008-09) | 0 | Community Construction | 127.07 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| c. Buildings for Primary Schools sanctioned over and above 15000 primary schools sanctioned in 2006-07 for which land is now available | 0 | Community Construction | 0
| d. New school buildings sanctioned in 2006-07 (deferred liability of 2011-12) | 0 | Community Construction | 50 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| e. Building Less (Pry) | 0 | Community Construction | 0
| f. Deffered Liability of NSB 2014-15 | 0 | Community Construction | 0
| g. Funds sanctioned for NSBs of previous years | 0 | Community Construction | 0
| Sub Total of Primary Schools | 0 |  | 182.97
2 | Upper Primary
| a. Upper Primary (new) |  | Community Construction | 0
| b. ACR for new UPS (Rural) |  | Community Construction | 303.29 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| c. Building Less (UP) |  | Community Construction | 0
| Sub Total of Upper Primary Schools | 0 |  | 303.29
3 | Additional Class Room (without stairs) | 0 | Community Construction | 875.18 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
4 | Additional Class Room (with stairs) | 0 | Community Construction | 297.93 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
5 | ACR sanctioned Last Year | 0 | Community Construction | 0
| Sub-total of ACRs | 0 |  | 1173.11
6 | Toilet/Urinals (Urban) |  | Community Construction
7 | Separate Girls Toilet |  | Community Construction
8 | Toilet, drinking water, child friendly elements and kitchen sheds for new UPS |  | Community Construction | 0
9 | Drinking Water Facility(Urban) | 0 | Community Construction
10 | Construction of Building of residential schools for specific category of children | 0 | Community Construction | 0
11 | Ramps | 0 | Community Construction | 0
12 | Head Master's Room (Deffered Liability 2014-15) | 0 | Community Construction | 0
13 | Toilet - Boys (Special PAB) |  | Community Construction
14 | Toilet - Girls (Special PAB) |  | Community Construction
15 | Construction of KGBV Buildings |  | Open Tender | 55.32 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| Sub Total | 0 |  | 55.32
TOTAL |  | 0 | 1659.37 | 1714.69
Method of Procurement |  |  |  |  | Procurement Action 2017-18 Aug.: Procurement Actions
Community Construction |  |  |  |  | Procurement Action 2017-18 Aug.: 1. Preparation of Specifications and bids document
Open Tender |  |  |  |  | Procurement Action 2017-18 Aug.: 2. Issue of Invitation to bid
3. Open bids
4. Evaluation of bids
5. Award Contracts
6. Construction 25% complete
7. Construction 50% complete
8. Construction 75% complete
9. Construction 100% complete

## Banka
Typical Procurement Schedule for Civil Works (Spill Over) under SSA for the year 2017-18
Name of District : BANKA
Sl.No. | Description of Goods | Quantity in Numbers | Method of Procurement | Estimated Cost (Rs. In Lakh) | Procurement Action 2017-18
[5 empty] | April | May | June | July | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March
1 | Primary School
| a. Primary School Rural (new) | 0 | Community Construction | 61.29 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| b. Primary schools sanctioned 2006-07 (deferred liability of 2008-09) | 0 | Community Construction | 60.15 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| c. Buildings for Primary Schools sanctioned over and above 15000 primary schools sanctioned in 2006-07 for which land is now available | 0 | Community Construction | 0
| d. New school buildings sanctioned in 2006-07 (deferred liability of 2011-12) | 0 | Community Construction | 2.14 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| e. Building Less (Pry) | 0 | Community Construction | 0
| f. Deffered Liability of NSB 2014-15 | 0 | Community Construction | 0
| g. Funds sanctioned for NSBs of previous years | 0 | Community Construction | 0
| Sub Total of Primary Schools | 0 |  | 123.58
2 | Upper Primary
| a. Upper Primary (new) |  | Community Construction | 0
| b. ACR for new UPS Rural |  | Community Construction | 0 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| c. Building Less (UP) |  | Community Construction | 0
| Sub Total of Upper Primary Schools | 0 |  | 0
3 | Additional Class Room (without stairs) | 0 | Community Construction | 47.22 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
4 | Additional Class Room (with stairs) | 0 | Community Construction | 23.61 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
5 | ACR sanctioned Last Year | 0 | Community Construction | 0
| Sub-total of ACRs | 0 |  | 70.83
6 | Toilet/Urinals (Urban) |  | Community Construction
7 | Separate Girls Toilet |  | Community Construction
8 | Toilet, drinking water, child friendly elements and kitchen sheds for new UPS |  | Community Construction | 0
9 | Drinking Water Facility(Urban) | 0 | Community Construction
10 | Construction of Building of residential schools for specific category of children | 0 | Community Construction | 0
11 | Ramps | 0 | Community Construction | 0
12 | Head Master's Room (Deffered Liability 2014-15) | 0 | Community Construction | 0
13 | Toilet - Boys (Special PAB) |  | Community Construction | 0
14 | Toilet - Girls (Special PAB) |  | Community Construction
15 | Construction of KGBV Buildings |  | Open Tender | 0 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| Sub Total | 0 |  | 0
TOTAL |  | 0 | 194.41 | 194.41
Method of Procurement |  |  |  |  | Procurement Action 2017-18 Aug.: Procurement Actions
Community Construction |  |  |  |  | Procurement Action 2017-18 Aug.: 1. Preparation of Specifications and bids document
Open Tender |  |  |  |  | Procurement Action 2017-18 Aug.: 2. Issue of Invitation to bid
3. Open bids
4. Evaluation of bids
5. Award Contracts
6. Construction 25% complete
7. Construction 50% complete
8. Construction 75% complete
9. Construction 100% complete

## Aurangabad
Typical Procurement Schedule for Civil Works (Spill Over) under SSA for the year 2017-18
Name of District : AURANGABAD
Sl.No. | Description of Goods | Quantity in Numbers | Method of Procurement | Estimated Cost (Rs. In Lakh) | Procurement Action 2017-18
[5 empty] | April | May | June | July | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March
1 | Primary School
| a. Primary School (new) | 0 | Community Construction
| b. Primary schools sanctioned 2006-07 (deferred liability of 2008-09) | 0 | Community Construction | 7.07 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| c. Buildings for Primary Schools sanctioned over and above 15000 primary schools sanctioned in 2006-07 for which land is now available | 0 | Community Construction | 0
| d. New school buildings sanctioned in 2006-07 (deferred liability of 2011-12) | 0 | Community Construction | 142.15 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| e. Building Less (Pry) | 0 | Community Construction | 0
| f. Deffered Liability of NSB 2014-15 | 0 | Community Construction | 0
| g. Funds sanctioned for NSBs of previous years | 0 | Community Construction | 0
| Sub Total of Primary Schools | 0 |  | 149.22
2 | Upper Primary
| a. Upper Primary (new) |  | Community Construction | 0
| b. ACR for new UPS (Rural) |  | Community Construction | 17.2 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| c. Building Less (UP) |  | Community Construction | 0
| Sub Total of Upper Primary Schools | 0 |  | 17.2
3 | Additional Class Room (without stairs) | 0 | Community Construction | 416.54 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
4 | Additional Class Room (with stairs) | 0 | Community Construction | 208.27 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
5 | ACR sanctioned Last Year | 0 | Community Construction | 0
| Sub-total of ACRs | 0 |  | 624.81
6 | Toilet/Urinals (Urban) |  | Community Construction
7 | Separate Girls Toilet |  | Community Construction
8 | Toilet, drinking water, child friendly elements and kitchen sheds for new UPS |  | Community Construction | 0
9 | Drinking Water Facility(Urban) | 0 | Community Construction
10 | Construction of Building of residential schools for specific category of children | 0 | Community Construction | 0
11 | Ramps | 0 | Community Construction | 0
12 | Head Master's Room (Deffered Liability 2014-15) | 0 | Community Construction | 0
13 | Toilet - Boys (Special PAB) |  | Community Construction
14 | Toilet - Girls (Special PAB) |  | Community Construction
15 | Construction of KGBV Buildings |  | Open Tender | 0 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| Sub Total | 0 |  | 0
TOTAL |  | 0 | 791.23 | 791.23
Method of Procurement |  |  |  |  | Procurement Action 2017-18 Aug.: Procurement Actions
Community Construction |  |  |  |  | Procurement Action 2017-18 Aug.: 1. Preparation of Specifications and bids document
Open Tender |  |  |  |  | Procurement Action 2017-18 Aug.: 2. Issue of Invitation to bid
3. Open bids
4. Evaluation of bids
5. Award Contracts
6. Construction 25% complete
7. Construction 50% complete
8. Construction 75% complete
9. Construction 100% complete

## Arwal
Typical Procurement Schedule for Civil Works (Spill Over) under SSA for the year 2017-18
Name of District : ARWAL
Sl.No. | Description of Goods | Quantity in Numbers | Method of Procurement | Estimated Cost (Rs. In Lakh) | Procurement Action 2017-18
[5 empty] | April | May | June | July | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March
1 | Primary School
1.1 | a. Primary School Rural (new) | 0 | Community Construction | 1.62 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| b. Primary schools sanctioned 2006-07 (deferred liability of 2008-09) | 0 | Community Construction | 1.11 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| c. Buildings for Primary Schools sanctioned over and above 15000 primary schools sanctioned in 2006-07 for which land is now available | 0 | Community Construction | 0
| d. New school buildings sanctioned in 2006-07 (deferred liability of 2011-12) | 0 | Community Construction | 0
| e. Building Less (Pry) | 0 | Community Construction | 0
| f. Deffered Liability of NSB 2014-15 | 0 | Community Construction | 0
| g. Funds sanctioned for NSBs of previous years | 0 | Community Construction | 0
| Sub Total of Primary Schools | 0 |  | 2.73
2 | Upper Primary
| a. Upper Primary (new) |  | Community Construction
| b. ACR for new UPS (Rural) |  | Community Construction | 6.53 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| c. Building Less (UP) |  | Community Construction | 0
| Sub Total of Upper Primary Schools | 0 |  | 6.53
3 | Additional Class Room (without stairs) | 0 | Community Construction | 4.36 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
4 | Additional Class Room (with stairs) | 0 | Community Construction | 7.25 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
5 | ACR sanctioned Last Year | 0 | Community Construction | 0
| Sub-total of ACRs | 0 |  | 11.61
6 | Toilet/Urinals (Urban) | 0 | Community Construction
7 | Separate Girls Toilet |  | Community Construction
8 | Toilet, drinking water, child friendly elements and kitchen sheds for new UPS |  | Community Construction | 0
9 | Drinking Water Facility(Urban) | 0 | Community Construction
10 | Construction of Building of residential schools for specific category of children | 0 | Community Construction | 0
11 | Ramps | 0 | Community Construction | 0
12 | Head Master's Room (Deffered Liability 2014-15) | 0 | Community Construction | 0
13 | Toilet - Boys (Special PAB) |  | Community Construction
14 | Toilet - Girls (Special PAB) |  | Community Construction
15 | Construction of KGBV Buildings |  | Community Construction/ Open Tender | 0 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| Sub Total | 0 |  | 0
TOTAL |  | 0 | 20.87 | 20.87
Method of Procurement |  |  |  |  | Procurement Action 2017-18 Aug.: Procurement Actions
Community Construction |  |  |  |  | Procurement Action 2017-18 Aug.: 1. Preparation of Specifications and bids document
Open Tender |  |  |  |  | Procurement Action 2017-18 Aug.: 2. Issue of Invitation to bid
3. Open bids
4. Evaluation of bids
5. Award Contracts
6. Construction 25% complete
7. Construction 50% complete
8. Construction 75% complete
9. Construction 100% complete

## Araria
Typical Procurement Schedule for Civil Works (Spill Over) under SSA for the year 2017-18
Name of District : Araria
Sl.No. | Description of Goods | Quantity in Numbers | Method of Procurement | Estimated Cost (Rs. In Lakh) | Procurement Action 2017-18
[5 empty] | April | May | June | July | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March
1 | Primary School
| a. Primary School (new) Rural | 0 | Community Construction | 0
| b. Primary schools sanctioned 2006-07 (deferred liability of 2008-09) | 0 | Community Construction | 36.74 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| c. Buildings for Primary Schools sanctioned over and above 15000 primary schools sanctioned in 2006-07 for which land is now available | 0 | Community Construction | 0
| d. New school buildings sanctioned in 2006-07 (deferred liability of 2011-12) | 0 | Community Construction | 5.49 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| e. Building Less (Pry) | 0 | Community Construction | 0
| f. Deffered Liability of NSB 2014-15 | 0 | Community Construction | 0
| g. Funds sanctioned for NSBs of previous years | 0 | Community Construction | 0
| Sub Total of Primary Schools | 0 |  | 42.23
2 | Upper Primary
| a. Upper Primary (new) |  | Community Construction
| b. ACR for new UPS (Rural) |  | Community Construction | 8.07 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| c. Building Less (UP) |  | Community Construction | 5.21 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| Sub Total of Upper Primary Schools | 0 |  | 13.28
3 | Additional Class Room (without stairs) | 0 | Community Construction | 613.33 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
4 | Additional Class Room (with stairs) | 0 | Community Construction | 884.98 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
5 | ACR sanctioned Last Year | 0 | Community Construction | 0
| Sub-total of ACRs | 0 |  | 1498.31
6 | Toilet/Urinals (Urban) |  | Community Construction | 0
7 | Separate Girls Toilet |  | Community Construction | 0
8 | Toilet, drinking water, child friendly elements and kitchen sheds for new UPS | 0 | Community Construction | 0
9 | Drinking Water Facility(Urban) | 0 | Community Construction | 0
10 | Construction of Building of residential schools for specific category of children | 0 | Community Construction | 0
11 | Ramps | 0 | Community Construction | 0
12 | Head Master's Room (Deffered Liability 2014-15) | 0 | Community Construction | 0
13 | Toilet - Boys (Special PAB) | 0 | Community Construction
14 | Toilet - Girls (Special PAB) | 0 | Community Construction
15 | Construction of KGBV Buildings |  | Community Construction | 0 | 1-6 | 1-6 | 1-6 | 1-7 | 1-7 | 1-7 | 1-7 | 1-8 | 1-8 | 1-8 | 1-8 | 1-9
| Sub Total | 0 |  | 0
TOTAL |  | 0 | 1553.82 | 1553.82
Method of Procurement |  |  |  |  | Procurement Action 2017-18 Aug.: Procurement Actions
Community Construction |  |  |  |  | Procurement Action 2017-18 Aug.: 1. Preparation of Specifications and bids document
Open Tender |  |  |  |  | Procurement Action 2017-18 Aug.: 2. Issue of Invitation to bid
3. Open bids
4. Evaluation of bids
5. Award Contracts
6. Construction 25% complete
7. Construction 50% complete
8. Construction 75% complete
9. Construction 100% complete