## State Compiled
Typical Procurement Schedule for Civil Works under SSA for the year 2014-15
Name of District : State All District (Bihar)
Sl.No. | Description of Goods | Quantity in Numbers | Method of Procurement | Estimated Cost (Rs. In Lakh) | Procurement Action 2014-15
[5 empty] | April | May | June | July | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March
1 | Primary School (new) | 134 | Community Construction | 1909.196 | Procurement Action 2014-15 April: Please Refer relevant Districts Sheet for Procurement Action
2 | Additional Class Room (without stairs) | 17020 | Community Construction | 78979.1145
3 | Additional Class Room (with stairs) | 8509 | Community Construction | 47733.555
4 | Toilet/Urinals (Urban) | 845 | Community Construction | 747.8
5 | Separate Girls Toilet | 1347 | Community Construction | 841.8
6 | Drinking Water Facility(Urban) | 535 | Community Construction | 93.625
7 | Disabled Friendly Toilet | 160 | Community Construction | 24
TOTAL |  | 28550 |  | 130329.0905
Method of Procurement |  |  |  |  | Procurement Action 2014-15 Aug.: Procurement Actions
Community Construction |  |  |  |  | Procurement Action 2014-15 Aug.: 1. Preparation of Specifications and bids document
Open Tender |  |  |  |  | Procurement Action 2014-15 Aug.: 2. Issue of Invitation to bid
3. Open bids
4. Evaluation of bids
5. Award Contracts
6. Construction 25% complete
7. Construction 50% complete
8. Construction 75% complete
9. Construction 100% complete

## West Champaran
Typical Procurement Schedule for Civil Works under SSA for the year 2014-15
Name of District : WEST CHAMPARAN
Sl.No. | Description of Goods | Quantity in Numbers | Method of Procurement | Estimated Cost (Rs. In Lakh) | Procurement Action 2014-15
[5 empty] | April | May | June | July | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March
1 | Primary School (new) | 0 | Community Construction | 0
2 | Additional Class Room (without stairs) | 346 | Community Construction | 1700.936 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
3 | Additional Class Room (with stairs) | 173 | Community Construction | 1020.873 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
4 | Toilet/Urinals (Urban) | 65 | Community Construction | 79.3 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
5 | Separate Girls Toilet | 42 | Community Construction | 25.62 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
6 | Drinking Water Facility(Urban) | 0 | Community Construction | 0
TOTAL |  | 107 |  | 104.92
Method of Procurement |  |  |  |  | Procurement Action 2014-15 Aug.: Procurement Actions
Community Construction |  |  |  |  | Procurement Action 2014-15 Aug.: 1. Preparation of Specifications and bids document
Open Tender |  |  |  |  | Procurement Action 2014-15 Aug.: 2. Issue of Invitation to bid
3. Open bids
4. Evaluation of bids
5. Award Contracts
6. Construction 25% complete
7. Construction 50% complete
8. Construction 75% complete
9. Construction 100% complete

## Vaishali
Typical Procurement Schedule for Civil Works under SSA for the year 2014-15
Name of District : VAISHALI
Sl.No. | Description of Goods | Quantity in Numbers | Method of Procurement | Estimated Cost (Rs. In Lakh) | Procurement Action 2014-15
[5 empty] | April | May | June | July | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March
1 | Primary School (new) | 0 | Community Construction | 0
2 | Additional Class Room (without stairs) | 589 | Community Construction | 2895.524 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
3 | Additional Class Room (with stairs) | 294 | Community Construction | 1734.894 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
4 | Toilet/Urinals (Urban) | 0 | Community Construction | 0
5 | Separate Girls Toilet | 0 | Community Construction | 0
6 | Drinking Water Facility(Urban) | 0 | Community Construction | 0
TOTAL |  | 883 |  | 4630.418
Method of Procurement |  |  |  |  | Procurement Action 2014-15 Aug.: Procurement Actions
Community Construction |  |  |  |  | Procurement Action 2014-15 Aug.: 1. Preparation of Specifications and bids document
Open Tender |  |  |  |  | Procurement Action 2014-15 Aug.: 2. Issue of Invitation to bid
3. Open bids
4. Evaluation of bids
5. Award Contracts
6. Construction 25% complete
7. Construction 50% complete
8. Construction 75% complete
9. Construction 100% complete

## Supaul
Typical Procurement Schedule for Civil Works under SSA for the year 2014-15
Name of District : SUPAUL
Sl.No. | Description of Goods | Quantity in Numbers | Method of Procurement | Estimated Cost (Rs. In Lakh) | Procurement Action 2014-15
[5 empty] | April | May | June | July | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March
1 | Primary School (new) | 0 | Community Construction | 0 | bar: Procurement Action 2014-15 April to Procurement Action 2014-15 March
2 | Additional Class Room (without stairs) | 521 | Community Construction | 2581.56 | - | - |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
3 | Additional Class Room (with stairs) | 261 | Community Construction | 1552.689 | - | - |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
4 | Toilet/Urinals (Urban) | 0 | Community Construction | 0 | bar: Procurement Action 2014-15 April to Procurement Action 2014-15 March
5 | Separate Girls Toilet | 0 | Community Construction | 0 | bar: Procurement Action 2014-15 April to Procurement Action 2014-15 March
6 | Drinking Water Facility(Urban) | 0 | Community Construction | 0 | bar: Procurement Action 2014-15 April to Procurement Action 2014-15 March
TOTAL |  | 0 |  | 0
Method of Procurement |  |  |  |  | Procurement Action 2014-15 Aug.: Procurement Actions
Community Construction |  |  |  |  | Procurement Action 2014-15 Aug.: 1. Preparation of Specifications and bids document
Open Tender |  |  |  |  | Procurement Action 2014-15 Aug.: 2. Issue of Invitation to bid
3. Open bids
4. Evaluation of bids
5. Award Contracts
6. Construction 25% complete
7. Construction 50% complete
8. Construction 75% complete
9. Construction 100% complete

## Siwan
Typical Procurement Schedule for Civil Works under SSA for the year 2014-15
Name of District : SIWAN
Sl.No. | Description of Goods | Quantity in Numbers | Method of Procurement | Estimated Cost (Rs. In Lakh) | Procurement Action 2014-15
[5 empty] | April | May | June | July | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March
1 | Primary School (new) | 0 | Community Construction | 0
2 | Additional Class Room (without stairs) | 497 | Community Construction | 2482.018 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
3 | Additional Class Room (with stairs) | 249 | Community Construction | 1493.751 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
4 | Toilet/Urinals (Urban) | 0 | Community Construction | 0
5 | Separate Girls Toilet | 0 | Community Construction | 0
6 | Drinking Water Facility(Urban) | 0 | Community Construction | 0
TOTAL |  | 0 |  | 0
Method of Procurement |  |  |  |  | Procurement Action 2014-15 Aug.: Procurement Actions
Community Construction |  |  |  |  | Procurement Action 2014-15 Aug.: 1. Preparation of Specifications and bids document
Open Tender |  |  |  |  | Procurement Action 2014-15 Aug.: 2. Issue of Invitation to bid
3. Open bids
4. Evaluation of bids
5. Award Contracts
6. Construction 25% complete
7. Construction 50% complete
8. Construction 75% complete
9. Construction 100% complete

## Sitamarhi
Typical Procurement Schedule for Civil Works under SSA for the year 2014-15
Name of District : SITAMARHI
Sl.No. | Description of Goods | Quantity in Numbers | Method of Procurement | Estimated Cost (Rs. In Lakh) | Procurement Action 2014-15
[5 empty] | April | May | June | July | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March
1 | Primary School (new) | 0 | Community Construction | 0
2 | Additional Class Room (without stairs) | 593 | Community Construction | 2915.188 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
3 | Additional Class Room (with stairs) | 296 | Community Construction | 1746.696 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
4 | Toilet/Urinals (Urban) | 108 | Community Construction | 131.76 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
5 | Separate Girls Toilet | 0 | Community Construction | 0
6 | Drinking Water Facility(Urban) | 108 | Community Construction | 18.9 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
TOTAL |  | 216 |  | 150.66
Method of Procurement |  |  |  |  | Procurement Action 2014-15 Aug.: Procurement Actions
Community Construction |  |  |  |  | Procurement Action 2014-15 Aug.: 1. Preparation of Specifications and bids document
Open Tender |  |  |  |  | Procurement Action 2014-15 Aug.: 2. Issue of Invitation to bid
3. Open bids
4. Evaluation of bids
5. Award Contracts
6. Construction 25% complete
7. Construction 50% complete
8. Construction 75% complete
9. Construction 100% complete

## Sheohar
Typical Procurement Schedule for Civil Works under SSA for the year 2014-15
Name of District : Sheohar
Sl.No. | Description of Goods | Quantity in Numbers | Method of Procurement | Estimated Cost (Rs. In Lakh) | Procurement Action 2014-15
[5 empty] | April | May | June | July | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March
1 | Primary School (new) | 0 | Community Construction | 0
2 | Additional Class Room (without stairs) | 129 | Community Construction | 634.16 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
3 | Additional Class Room (with stairs) | 64 | Community Construction | 377.66 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
4 | Toilet/Urinals (Urban) | 0 | Community Construction | 0
5 | Separate Girls Toilet | 0 | Community Construction | 0
6 | Drinking Water Facility(Urban) | 0 | Community Construction | 0
TOTAL |  | 193 |  | 1011.82
Method of Procurement |  |  |  |  | Procurement Action 2014-15 Aug.: Procurement Actions
Community Construction |  |  |  |  | Procurement Action 2014-15 Aug.: 1. Preparation of Specifications and bids document
Open Tender |  |  |  |  | Procurement Action 2014-15 Aug.: 2. Issue of Invitation to bid
3. Open bids
4. Evaluation of bids
5. Award Contracts
6. Construction 25% complete
7. Construction 50% complete
8. Construction 75% complete
9. Construction 100% complete

## Sheikhpura
Typical Procurement Schedule for Civil Works under SSA for the year 2014-15
Name of District : Sheikhpura
Sl.No. | Description of Goods | Quantity in Numbers | Method of Procurement | Estimated Cost (Rs. In Lakh) | Procurement Action 2014-15
[5 empty] | April | May | June | July | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March
1 | Primary School (new) | 0 | Community Construction | 0
2 | Additional Class Room (without stairs) | 81 | Community Construction | 367.335 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
3 | Additional Class Room (with stairs) | 40 | Community Construction | 217.6 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
4 | Toilet/Urinals (Urban) | 0 | Community Construction | 0
5 | Separate Girls Toilet | 32 | Community Construction | 19.52 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
6 | Drinking Water Facility(Urban) | 0 | Community Construction | 0
TOTAL |  | 153 |  | 604.455
Method of Procurement |  |  |  |  | Procurement Action 2014-15 Aug.: Procurement Actions
Community Construction |  |  |  |  | Procurement Action 2014-15 Aug.: 1. Preparation of Specifications and bids document
Open Tender |  |  |  |  | Procurement Action 2014-15 Aug.: 2. Issue of Invitation to bid
3. Open bids
4. Evaluation of bids
5. Award Contracts
6. Construction 25% complete
7. Construction 50% complete
8. Construction 75% complete
9. Construction 100% complete

## Saran
Typical Procurement Schedule for Civil Works under SSA for the year 2014-15
Name of District : SARAN
Sl.No. | Description of Goods | Quantity in Numbers | Method of Procurement | Estimated Cost (Rs. In Lakh) | Procurement Action 2014-15
[5 empty] | April | May | June | July | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March
1 | Primary School (new) | 24 | Community Construction | 359.26 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
2 | Additional Class Room (without stairs) | 1145 | Community Construction | 5718.13 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
3 | Additional Class Room (with stairs) | 572 | Community Construction | 3402.83 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
4 | Toilet/Urinals (Urban) | 49 | Community Construction | 72.03 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
5 | Separate Girls Toilet | 93 | Community Construction | 56.73 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
6 | Drinking Water Facility(Urban) | 52 | Community Construction | 9.1 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
TOTAL |  | 218 |  | 9618.08
Method of Procurement |  |  |  |  | Procurement Action 2014-15 Aug.: Procurement Actions
Community Construction |  |  |  |  | Procurement Action 2014-15 Aug.: 1. Preparation of Specifications and bids document
Open Tender |  |  |  |  | Procurement Action 2014-15 Aug.: 2. Issue of Invitation to bid
3. Open bids
4. Evaluation of bids
5. Award Contracts
6. Construction 25% complete
7. Construction 50% complete
8. Construction 75% complete
9. Construction 100% complete

## Samastipur
Typical Procurement Schedule for Civil Works under SSA for the year 2014-15
Name of District : Samastipur
Sl.No. | Description of Goods | Quantity in Numbers | Method of Procurement | Estimated Cost (Rs. In Lakh) | Procurement Action 2014-15
[5 empty] | April | May | June | July | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March
1 | Primary School (new) | 0 | Community Construction | 0
2 | Additional Class Room (without stairs) | 489 | Community Construction | 2336.442 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
3 | Additional Class Room (with stairs) | 245 | Community Construction | 1405.075 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
4 | Toilet/Urinals (Urban) | 0 | Community Construction | 0
5 | Separate Girls Toilet | 0 | Community Construction | 0
6 | Drinking Water Facility(Urban) | 0 | Community Construction | 0
TOTAL |  | 0 |  | 0
Method of Procurement |  |  |  |  | Procurement Action 2014-15 Aug.: Procurement Actions
Community Construction |  |  |  |  | Procurement Action 2014-15 Aug.: 1. Preparation of Specifications and bids document
Open Tender |  |  |  |  | Procurement Action 2014-15 Aug.: 2. Issue of Invitation to bid
3. Open bids
4. Evaluation of bids
5. Award Contracts
6. Construction 25% complete
7. Construction 50% complete
8. Construction 75% complete
9. Construction 100% complete

## Saharsa
Typical Procurement Schedule for Civil Works under SSA for the year 2014-15
Name of District : SAHARSA
Sl.No. | Description of Goods | Quantity in Numbers | Method of Procurement | Estimated Cost (Rs. In Lakh) | Procurement Action 2014-15
[5 empty] | April | May | June | July | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March
1 | Primary School (new) | 0 | Community Construction | 0
2 | Additional Class Room (without stairs) | 97 | Community Construction | 480.635 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
3 | Additional Class Room (with stairs) | 48 | Community Construction | 285.552 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
4 | Toilet/Urinals (Urban) | 0 | Community Construction | 0
5 | Separate Girls Toilet | 0 | Community Construction | 0
6 | Drinking Water Facility(Urban) | 0 | Community Construction | 0
TOTAL |  | 145 |  | 766.187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Method of Procurement |  |  |  |  | Procurement Action 2014-15 Aug.: Procurement Actions
Community Construction |  |  |  |  | Procurement Action 2014-15 Aug.: 1. Preparation of Specifications and bids document
Open Tender |  |  |  |  | Procurement Action 2014-15 Aug.: 2. Issue of Invitation to bid
3. Open bids
4. Evaluation of bids
5. Award Contracts
6. Construction 25% complete
7. Construction 50% complete
8. Construction 75% complete
9. Construction 100% complete

## Rohtas
Typical Procurement Schedule for Civil Works under SSA for the year 2014-15
Name of District : ROHTAS
Sl.No. | Description of Goods | Quantity in Numbers | Method of Procurement | Estimated Cost (Rs. In Lakh) | Procurement Action 2014-15
[5 empty] | April | May | June | July | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March
1 | Primary School (new) | 0 | Community Construction | 0
2 | Additional Class Room (without stairs) | 385 | Community Construction | 1715.175 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
3 | Additional Class Room (with stairs) | 192 | Community Construction | 1026.048 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
4 | Toilet/Urinals (Urban) | 0 | Community Construction | 0
5 | Separate Girls Toilet | 14 | Community Construction | 8.54 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
6 | Drinking Water Facility(Urban) | 0 | Community Construction | 0
TOTAL |  | 591 |  | 2749.763
Method of Procurement |  |  |  |  | Procurement Action 2014-15 Aug.: Procurement Actions
Community Construction |  |  |  |  | Procurement Action 2014-15 Aug.: 1. Preparation of Specifications and bids document
Open Tender |  |  |  |  | Procurement Action 2014-15 Aug.: 2. Issue of Invitation to bid
3. Open bids
4. Evaluation of bids
5. Award Contracts
6. Construction 25% complete
7. Construction 50% complete
8. Construction 75% complete
9. Construction 100% complete

## Purnia
Typical Procurement Schedule for Civil Works under SSA for the year 2014-15
Name of District : Purnea
Sl.No. | Description of Goods | Quantity in Numbers | Method of Procurement | Estimated Cost (Rs. In Lakh) | Procurement Action 2014-15
[5 empty] | April | May | June | July | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March
1 | Primary School (new) | 24 | Community Construction | 340.416 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
2 | Additional Class Room (without stairs) | 751 | Community Construction | 3550.728 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
3 | Additional Class Room (with stairs) | 375 | Community Construction | 2126.25 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
4 | Toilet/Urinals (Urban) | 0 | Community Construction | 0
5 | Separate Girls Toilet | 80 | Community Construction | 48.8 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
6 | Drinking Water Facility(Urban) | 0 | Community Construction | 0
TOTAL |  | 104 |  | 389.216
Method of Procurement |  |  |  |  | Procurement Action 2014-15 Aug.: Procurement Actions
Community Construction |  |  |  |  | Procurement Action 2014-15 Aug.: 1. Preparation of Specifications and bids document
Open Tender |  |  |  |  | Procurement Action 2014-15 Aug.: 2. Issue of Invitation to bid
3. Open bids
4. Evaluation of bids
5. Award Contracts
6. Construction 25% complete
7. Construction 50% complete
8. Construction 75% complete
9. Construction 100% complete

## Patna (U)
Typical Procurement Schedule for Civil Works under SSA for the year 2014-15
Name of District : Patna (Urban)
Sl.No. | Description of Goods | Quantity in Numbers | Method of Procurement | Estimated Cost (Rs. In Lakh) | Procurement Action 2014-15
[5 empty] | April | May | June | July | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March
1 | Primary School (new) | 0 | Community Construction | 0
2 | Additional Class Room (without stairs) | 81 | Community Construction | 360.855 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
3 | Additional Class Room (with stairs) | 27 | Community Construction | 144.288 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
4 | Toilet/Urinals (Urban) | 0 | Community Construction | 0
5 | Separate Girls Toilet | 60 | Community Construction | 36.6 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
6 | Drinking Water Facility(Urban) | 0 | Community Construction | 0
TOTAL |  | 168 |  | 541.743
Method of Procurement |  |  |  |  | Procurement Action 2014-15 Aug.: Procurement Actions
Community Construction |  |  |  |  | Procurement Action 2014-15 Aug.: 1. Preparation of Specifications and bids document
Open Tender |  |  |  |  | Procurement Action 2014-15 Aug.: 2. Issue of Invitation to bid
3. Open bids
4. Evaluation of bids
5. Award Contracts
6. Construction 25% complete
7. Construction 50% complete
8. Construction 75% complete
9. Construction 100% complete

## Patna (R)
Typical Procurement Schedule for Civil Works under SSA for the year 2014-15
Name of District : Patna (Rural)
Sl.No. | Description of Goods | Quantity in Numbers | Method of Procurement | Estimated Cost (Rs. In Lakh) | Procurement Action 2014-15
[5 empty] | April | May | June | July | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March
1 | Primary School (new) |  | Community Construction | 0
2 | Additional Class Room (without stairs) | 902 | Community Construction | 4018.41 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
3 | Additional Class Room (with stairs) | 465 | Community Construction | 2484.96 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
4 | Toilet/Urinals (Urban) | 0 | Community Construction | 0
5 | Separate Girls Toilet | 241 | Community Construction | 147.01 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
6 | Drinking Water Facility(Urban) | 0 | Community Construction | 0
TOTAL |  | 241 |  | 147.01
Method of Procurement |  |  |  |  | Procurement Action 2014-15 Aug.: Procurement Actions
Community Construction |  |  |  |  | Procurement Action 2014-15 Aug.: 1. Preparation of Specifications and bids document
Open Tender |  |  |  |  | Procurement Action 2014-15 Aug.: 2. Issue of Invitation to bid
3. Open bids
4. Evaluation of bids
5. Award Contracts
6. Construction 25% complete
7. Construction 50% complete
8. Construction 75% complete
9. Construction 100% complete

## Nawada
Typical Procurement Schedule for Civil Works under SSA for the year 2014-15
Name of District : Nawada
Sl.No. | Description of Goods | Quantity in Numbers | Method of Procurement | Estimated Cost (Rs. In Lakh) | Procurement Action 2014-15
[5 empty] | April | May | June | July | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March
1 | Primary School (new) | 0 | Community Construction | 0
2 | Additional Class Room (without stairs) | 507 | Community Construction | 2103.543 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
3 | Additional Class Room (with stairs) | 254 | Community Construction | 1357.376 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
4 | Toilet/Urinals (Urban) | 0 | Community Construction | 0
5 | Separate Girls Toilet | 0 | Community Construction | 0
6 | Drinking Water Facility(Urban) | 0 | Community Construction | 0
TOTAL |  | 761 |  | 3460.919
Method of Procurement |  |  |  |  | Procurement Action 2014-15 Aug.: Procurement Actions
Community Construction |  |  |  |  | Procurement Action 2014-15 Aug.: 1. Preparation of Specifications and bids document
Open Tender |  |  |  |  | Procurement Action 2014-15 Aug.: 2. Issue of Invitation to bid
3. Open bids
4. Evaluation of bids
5. Award Contracts
6. Construction 25% complete
7. Construction 50% complete
8. Construction 75% complete
9. Construction 100% complete

## Nalanda
Typical Procurement Schedule for Civil Works under SSA for the year 2014-15
Name of District : Nalanda
Sl.No. | Description of Goods | Quantity in Numbers | Method of Procurement | Estimated Cost (Rs. In Lakh) | Procurement Action 2014-15
[5 empty] | April | May | June | July | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March
1 | Primary School (new) | 0 | Community Construction | 0
2 | Additional Class Room (without stairs) | 1137 | Community Construction | 5065.9035 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
3 | Additional Class Room (with stairs) | 569 | Community Construction | 3040.736 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
4 | Toilet/Urinals (Urban) | 0 | Community Construction | 0
5 | Separate Girls Toilet | 0 | Community Construction | 0
6 | Drinking Water Facility(Urban) | 0 | Community Construction | 0
TOTAL |  | 0 |  | 8106.6395
Method of Procurement |  |  |  |  | Procurement Action 2014-15 Aug.: Procurement Actions
Community Construction |  |  |  |  | Procurement Action 2014-15 Aug.: 1. Preparation of Specifications and bids document
Open Tender |  |  |  |  | Procurement Action 2014-15 Aug.: 2. Issue of Invitation to bid
3. Open bids
4. Evaluation of bids
5. Award Contracts
6. Construction 25% complete
7. Construction 50% complete
8. Construction 75% complete
9. Construction 100% complete

## Muzafferpur
Typical Procurement Schedule for Civil Works under SSA for the year 2014-15
Name of District : Muzaffarpur
Sl.No. | Description of Goods | Quantity in Numbers | Method of Procurement | Estimated Cost (Rs. In Lakh) | Procurement Action 2014-15
[5 empty] | April | May | June | July | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March
1 | Primary School (new) | 0 | Community Construction | 0
2 | Additional Class Room (without stairs) | 333 | Community Construction | 1637.028 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
3 | Additional Class Room (with stairs) | 167 | Community Construction | 985.467 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
4 | Toilet/Urinals (Urban) | 0 | Community Construction | 0
5 | Separate Girls Toilet | 0 | Community Construction | 0
6 | Drinking Water Facility(Urban) | 0 | Community Construction | 0
TOTAL |  | 0 |  | 0
Method of Procurement |  |  |  |  | Procurement Action 2014-15 Aug.: Procurement Actions
Community Construction |  |  |  |  | Procurement Action 2014-15 Aug.: 1. Preparation of Specifications and bids document
Open Tender |  |  |  |  | Procurement Action 2014-15 Aug.: 2. Issue of Invitation to bid
3. Open bids
4. Evaluation of bids
5. Award Contracts
6. Construction 25% complete
7. Construction 50% complete
8. Construction 75% complete
9. Construction 100% complete

## Munger
Bihar Education Project, Munger
Typical Procurement Schedule for Civil Works under SSA for the year 2014-15
Name of District : Munger
Sl.No. | Description of Goods | Quantity in Numbers | Method of Procurement | Estimated Cost (Rs. In Lakh) | Procurement Action 2014-15
[5 empty] | April | May | June | July | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March
1 | Primary School (new) | 0 | Community Construction | 0
2 | Additional Class Room (without stairs) | 373 | Community Construction | 1691.555 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
3 | Additional Class Room (with stairs) | 187 | Community Construction | 1017.28 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
4 | Toilet/Urinals (Urban) | 0 | Community Construction | 0
5 | Separate Girls Toilet | 33 | Community Construction | 40.26 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
6 | Drinking Water Facility(Urban) | 0 | Community Construction | 0
TOTAL |  | 33 |  | 2749.095
Method of Procurement |  |  |  |  | Procurement Action 2014-15 Aug.: Procurement Actions
Community Construction |  |  |  |  | Procurement Action 2014-15 Aug.: 1. Preparation of Specifications and bids document
Open Tender |  |  |  |  | Procurement Action 2014-15 Aug.: 2. Issue of Invitation to bid
3. Open bids
4. Evaluation of bids
5. Award Contracts
6. Construction 25% complete
7. Construction 50% complete
8. Construction 75% complete
9. Construction 100% complete

## Madhubani
Typical Procurement Schedule for Civil Works under SSA for the year 2014-15
Name of District : Madhubani
Sl.No. | Description of Goods | Quantity in Numbers | Method of Procurement | Estimated Cost (Rs. In Lakh) | Procurement Action 2014-15
[5 empty] | April | May | June | July | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March
1 | Primary School (new) | 0 | Community Construction | 0
2 | Additional Class Room (without stairs) | 461 | Community Construction | 2202.658 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
3 | Additional Class Room (with stairs) | 231 | Community Construction | 1324.785 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
4 | Toilet/Urinals (Urban) | 0 | Community Construction | 0
5 | Separate Girls Toilet | 0 | Community Construction | 0
6 | Drinking Water Facility(Urban) | 0 | Community Construction | 0
TOTAL |  | 692 |  | 3527.443
Method of Procurement |  |  |  |  | Procurement Action 2014-15 Aug.: Procurement Actions
Community Construction |  |  |  |  | Procurement Action 2014-15 Aug.: 1. Preparation of Specifications and bids document
Open Tender |  |  |  |  | Procurement Action 2014-15 Aug.: 2. Issue of Invitation to bid
3. Open bids
4. Evaluation of bids
5. Award Contracts
6. Construction 25% complete
7. Construction 50% complete
8. Construction 75% complete
9. Construction 100% complete

## Madhepura
Typical Procurement Schedule for Civil Works under SSA for the year 2014-15
Name of District : MADHEPURA
Sl.No. | Description of Goods | Quantity in Numbers | Method of Procurement | Estimated Cost (Rs. In Lakh) | Procurement Action 2014-15
[5 empty] | April | May | June | July | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March
1 | Primary School (new) | 0 | Community Construction | 0
2 | Additional Class Room (without stairs) | 264 | Community Construction | 1308.12 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
3 | Additional Class Room (with stairs) | 132 | Community Construction | 785.268 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
4 | Toilet/Urinals (Urban) | 0 | Community Construction | 0
5 | Separate Girls Toilet | 0 | Community Construction | 0
6 | Drinking Water Facility(Urban) | 0 | Community Construction | 0
TOTAL |  | 396 |  | 2093.388
Method of Procurement |  |  |  |  | Procurement Action 2014-15 Aug.: Procurement Actions
Community Construction |  |  |  |  | Procurement Action 2014-15 Aug.: 1. Preparation of Specifications and bids document
Open Tender |  |  |  |  | Procurement Action 2014-15 Aug.: 2. Issue of Invitation to bid
3. Open bids
4. Evaluation of bids
5. Award Contracts
6. Construction 25% complete
7. Construction 50% complete
8. Construction 75% complete
9. Construction 100% complete

## Lakhisarai
Typical Procurement Schedule for Civil Works under SSA for the year 2014-15
Name of District : Lakhisarai
Sl.No. | Description of Goods | Quantity in Numbers | Method of Procurement | Estimated Cost (Rs. In Lakh) | Procurement Action 2014-15
[5 empty] | April | May | June | July | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March
1 | Primary School (new) | 0 | Community Construction | 0
2 | Additional Class Room (without stairs) | 358 | Community Construction | 1623.53 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
3 | Additional Class Room (with stairs) | 179 | Community Construction | 973.76 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
4 | Toilet/Urinals (Urban) | 78 | Community Construction | 94.38 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
5 | Separate Girls Toilet | 78 | Community Construction | 47.58 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
6 | Drinking Water Facility(Urban) | 78 | Community Construction | 13.65 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
TOTAL |  | 234 |  | 155.61
Method of Procurement |  |  |  |  | Procurement Action 2014-15 Aug.: Procurement Actions
Community Construction |  |  |  |  | Procurement Action 2014-15 Aug.: 1. Preparation of Specifications and bids document
Open Tender |  |  |  |  | Procurement Action 2014-15 Aug.: 2. Issue of Invitation to bid
3. Open bids
4. Evaluation of bids
5. Award Contracts
6. Construction 25% complete
7. Construction 50% complete
8. Construction 75% complete
9. Construction 100% complete

## Kishanganj
Typical Procurement Schedule for Civil Works under SSA for the year 2014-15
Name of District : Kishanganj
Sl.No. | Description of Goods | Quantity in Numbers | Method of Procurement | Estimated Cost (Rs. In Lakh) | Procurement Action 2014-15
[5 empty] | April | May | June | July | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March
1 | Primary School (new) | 80 | Community Construction | 1134.72 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
2 | Additional Class Room (without stairs) | 565 | Community Construction | 2671.32 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
3 | Additional Class Room (with stairs) | 282 | Community Construction | 1598.94 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
4 | Toilet/Urinals (Urban) | 144 | Community Construction | 87.84 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
5 | Separate Girls Toilet | 144 | Community Construction | 87.84 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
6 | Drinking Water Facility(Urban) | 114 | Community Construction | 19.95 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
TOTAL |  | 482 |  | 5600.61
Method of Procurement |  |  |  |  | Procurement Action 2014-15 Aug.: Procurement Actions
Community Construction |  |  |  |  | Procurement Action 2014-15 Aug.: 1. Preparation of Specifications and bids document
Open Tender |  |  |  |  | Procurement Action 2014-15 Aug.: 2. Issue of Invitation to bid
3. Open bids
4. Evaluation of bids
5. Award Contracts
6. Construction 25% complete
7. Construction 50% complete
8. Construction 75% complete
9. Construction 100% complete

## Khagaria
Typical Procurement Schedule for Civil Works under SSA for the year 2014-15
Name of District : KHAGARIA
Sl.No. | Description of Goods | Quantity in Numbers | Method of Procurement | Estimated Cost (Rs. In Lakh) | Procurement Action 2014-15
[5 empty] | April | May | June | July | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March
1 | Primary School (new) | 0 | Community Construction | 0
2 | Additional Class Room (without stairs) | 228 | Community Construction | 1033.98 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
3 | Additional Class Room (with stairs) | 114 | Community Construction | 620.16 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
4 | Toilet/Urinals (Urban) | 10 | Community Construction | 6.1 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
5 | Separate Girls Toilet | 20 | Community Construction | 12.2 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
6 | Drinking Water Facility(Urban) | 0 | Community Construction | 0
TOTAL |  | 30 |  | 18.3
Method of Procurement |  |  |  |  | Procurement Action 2014-15 Aug.: Procurement Actions
Community Construction |  |  |  |  | Procurement Action 2014-15 Aug.: 1. Preparation of Specifications and bids document
Open Tender |  |  |  |  | Procurement Action 2014-15 Aug.: 2. Issue of Invitation to bid
3. Open bids
4. Evaluation of bids
5. Award Contracts
6. Construction 25% complete
7. Construction 50% complete
8. Construction 75% complete
9. Construction 100% complete

## Katihar
Typical Procurement Schedule for Civil Works under SSA for the year 2014-15
Name of District : KATIHAR
Sl.No. | Description of Goods | Quantity in Numbers | Method of Procurement | Estimated Cost (Rs. In Lakh) | Procurement Action 2014-15
[5 empty] | April | May | June | July | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March
1 | Primary School (new) | 0 | Community Construction | 0
2 | Additional Class Room (without stairs) | 503 | Community Construction | 2378.18 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
3 | Additional Class Room (with stairs) | 252 | Community Construction | 1428.84 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
4 | Toilet/Urinals (Urban) | 0 | Community Construction | 0
5 | Separate Girls Toilet | 0 | Community Construction | 0
6 | Drinking Water Facility(Urban) | 0 | Community Construction | 0
TOTAL |  | 755 |  | 3807.02
Method of Procurement |  |  |  |  | Procurement Action 2014-15 Aug.: Procurement Actions
Community Construction |  |  |  |  | Procurement Action 2014-15 Aug.: 1. Preparation of Specifications and bids document
Open Tender |  |  |  |  | Procurement Action 2014-15 Aug.: 2. Issue of Invitation to bid
3. Open bids
4. Evaluation of bids
5. Award Contracts
6. Construction 25% complete
7. Construction 50% complete
8. Construction 75% complete
9. Construction 100% complete

## Kaimur
Typical Procurement Schedule of Kaimur for Civil Works under SSA for the year 2014-15
Name of District : Kaimur
Sl.No. | Description of Goods | Quantity in Numbers | Method of Procurement | Estimated Cost (Rs. In Lakh) | Procurement Action 2014-15
[5 empty] | April | May | June | July | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March
1 | Primary School (new) |  | Community Construction | 0
2 | Additional Class Room (without stairs) | 120 | Community Construction | 534.6 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
3 | Additional Class Room (with stairs) | 60 | Community Construction | 320.64 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
4 | Toilet/Urinals (Urban) | 37 | Community Construction | 54.39 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
5 | Separate Girls Toilet | 0 | Community Construction | 0
6 | Drinking Water Facility(Urban) | 37 | Community Construction | 6.475 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
TOTAL |  | 74 |  | 60.865
Method of Procurement |  |  |  |  | Procurement Action 2014-15 Aug.: Procurement Actions
Community Construction |  |  |  |  | Procurement Action 2014-15 Aug.: 1. Preparation of Specifications and bids document
Open Tender |  |  |  |  | Procurement Action 2014-15 Aug.: 2. Issue of Invitation to bid
3. Open bids
4. Evaluation of bids
5. Award Contracts
6. Construction 25% complete
7. Construction 50% complete
8. Construction 75% complete
9. Construction 100% complete

## Jehanabad
Typical Procurement Schedule for Civil Works under SSA for the year 2014-15
Name of District : Jehanabad
Sl.No. | Description of Goods | Quantity in Numbers | Method of Procurement | Estimated Cost (Rs. In Lakh) | Procurement Action 2014-15
[5 empty] | April | May | June | July | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March
1 | Primary School (new) | 0 | Community Construction | 0
2 | Additional Class Room (without stairs) | 487 | Community Construction | 2020.56 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
3 | Additional Class Room (with stairs) | 244 | Community Construction | 1303.936 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
4 | Toilet/Urinals (Urban) | 0 | Community Construction | 0
5 | Separate Girls Toilet | 0 | Community Construction | 0
6 | Drinking Water Facility(Urban) | 0 | Community Construction | 0
TOTAL |  | 731 |  | 3324.496
Method of Procurement |  |  |  |  | Procurement Action 2014-15 Aug.: Procurement Actions
Community Construction |  |  |  |  | Procurement Action 2014-15 Aug.: 1. Preparation of Specifications and bids document
Open Tender |  |  |  |  | Procurement Action 2014-15 Aug.: 2. Issue of Invitation to bid
3. Open bids
4. Evaluation of bids
5. Award Contracts
6. Construction 25% complete
7. Construction 50% complete
8. Construction 75% complete
9. Construction 100% complete

## Jamui
Typical Procurement Schedule for Civil Works under SSA for the year 2014-15
Name of District : JAMUI
Sl.No. | Description of Goods | Quantity in Numbers | Method of Procurement | Estimated Cost (Rs. In Lakh) | Procurement Action 2014-15
[5 empty] | April | May | June | July | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March
1 | Primary School (new) | 0 | Community Construction | 0
2 | Additional Class Room (without stairs) | 135 | Community Construction | 612.225 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
3 | Additional Class Room (with stairs) | 67 | Community Construction | 364.48 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
4 | Toilet/Urinals (Urban) | 0 | Community Construction | 0
5 | Separate Girls Toilet | 0 | Community Construction | 0
6 | Drinking Water Facility(Urban) | 0 | Community Construction | 0
TOTAL |  | 202 |  | 976.705
Method of Procurement |  |  |  |  | Procurement Action 2014-15 Aug.: Procurement Actions
Community Construction |  |  |  |  | Procurement Action 2014-15 Aug.: 1. Preparation of Specifications and bids document
Open Tender |  |  |  |  | Procurement Action 2014-15 Aug.: 2. Issue of Invitation to bid
3. Open bids
4. Evaluation of bids
5. Award Contracts
6. Construction 25% complete
7. Construction 50% complete
8. Construction 75% complete
9. Construction 100% complete

## Gopalganj
Typical Procurement Schedule for Civil Works under SSA for the year 2014-15
Name of District : GOPALGANJ
Sl.No. | Description of Goods | Quantity in Numbers | Method of Procurement | Estimated Cost (Rs. In Lakh) | Procurement Action 2014-15
[5 empty] | April | May | June | July | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March
1 | Primary School (new) | 0 | Community Construction | 0
2 | Additional Class Room (without stairs) | 1005 | Community Construction | 5018.97 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
3 | Additional Class Room (with stairs) | 503 | Community Construction | 3017.497 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
4 | Toilet/Urinals (Urban) | 0 | Community Construction | 0
5 | Separate Girls Toilet | 0 | Community Construction | 0
6 | Drinking Water Facility(Urban) | 0 | Community Construction | 0
TOTAL |  | 1508 |  | 8036.467
Method of Procurement |  |  |  |  | Procurement Action 2014-15 Aug.: Procurement Actions
Community Construction |  |  |  |  | Procurement Action 2014-15 Aug.: 1. Preparation of Specifications and bids document
Open Tender |  |  |  |  | Procurement Action 2014-15 Aug.: 2. Issue of Invitation to bid
3. Open bids
4. Evaluation of bids
5. Award Contracts
6. Construction 25% complete
7. Construction 50% complete
8. Construction 75% complete
9. Construction 100% complete

## Gaya
Typical Procurement Schedule for Civil Works under SSA for the year 2014-15
Name of District : GAYA
Sl.No. | Description of Goods | Quantity in Numbers | Method of Procurement | Estimated Cost (Rs. In Lakh) | Procurement Action 2014-15
[5 empty] | April | May | June | July | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March
1 | Primary School (new) | 0 | Community Construction | 0
2 | Additional Class Room (without stairs) | 231 | Community Construction | 958.419 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
3 | Additional Class Room (with stairs) | 116 | Community Construction | 619.904 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
4 | Toilet/Urinals (Urban) | 0 | Community Construction | 0
5 | Separate Girls Toilet | 0 | Community Construction | 0
6 | Drinking Water Facility(Urban) | 0 | Community Construction | 0
TOTAL |  | 347 | 0 | 1578.323
Method of Procurement |  |  |  |  | Procurement Action 2014-15 Aug.: Procurement Actions
Community Construction |  |  |  |  | Procurement Action 2014-15 Aug.: 1. Preparation of Specifications and bids document
Open Tender |  |  |  |  | Procurement Action 2014-15 Aug.: 2. Issue of Invitation to bid
3. Open bids
4. Evaluation of bids
5. Award Contracts
6. Construction 25% complete
7. Construction 50% complete
8. Construction 75% complete
9. Construction 100% complete

## East Champaran
Typical Procurement Schedule for Civil Works under SSA for the year 2014-15
Name of District : East Champaran
Sl.No. | Description of Goods | Quantity in Numbers | Method of Procurement | Estimated Cost (Rs. In Lakh) | Procurement Action 2014-15
[5 empty] | April | May | June | July | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March
1 | Primary School (new) | 0 | Community Construction | 0
2 | Additional Class Room (without stairs) | 72 | Community Construction | 353.95 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
3 | Additional Class Room (with stairs) | 36 | Community Construction | 212.436 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
4 | Toilet/Urinals (Urban) | 0 | Community Construction | 0
5 | Separate Girls Toilet | 0 | Community Construction | 0
6 | Drinking Water Facility(Urban) | 0 | Community Construction | 0
TOTAL |  | 108 |  | 566.386
Method of Procurement |  |  |  |  | Procurement Action 2014-15 Aug.: Procurement Actions
Community Construction |  |  |  |  | Procurement Action 2014-15 Aug.: 1. Preparation of Specifications and bids document
Open Tender |  |  |  |  | Procurement Action 2014-15 Aug.: 2. Issue of Invitation to bid
3. Open bids
4. Evaluation of bids
5. Award Contracts
6. Construction 25% complete
7. Construction 50% complete
8. Construction 75% complete
9. Construction 100% complete

## Darbhanga
Typical Procurement Schedule for Civil Works under SSA for the year 2014-15
Name of District : Darbhanga
Sl.No. | Description of Goods | Quantity in Numbers | Method of Procurement | Estimated Cost (Rs. In Lakh) | Procurement Action 2014-15
[5 empty] | April | May | June | July | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March
1 | Primary School (new) | 0 | Community Construction | 0
2 | Additional Class Room (without stairs) | 306 | Community Construction | 1462.07 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
3 | Additional Class Room (with stairs) | 153 | Community Construction | 877.455 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
4 | Toilet/Urinals (Urban) | 0 | Community Construction | 0
5 | Separate Girls Toilet | 0 | Community Construction | 0
6 | Drinking Water Facility(Urban) | 0 | Community Construction | 0
TOTAL |  | 459 |  | 2339.525
Method of Procurement |  |  |  |  | Procurement Action 2014-15 Aug.: Procurement Actions
Community Construction |  |  |  |  | Procurement Action 2014-15 Aug.: 1. Preparation of Specifications and bids document
Open Tender |  |  |  |  | Procurement Action 2014-15 Aug.: 2. Issue of Invitation to bid
3. Open bids
4. Evaluation of bids
5. Award Contracts
6. Construction 25% complete
7. Construction 50% complete
8. Construction 75% complete
9. Construction 100% complete

## Buxer
Typical Procurement Schedule for Civil Works under SSA for the year 2014-15
Name of District : Buxar
Sl.No. | Description of Goods | Quantity in Numbers | Method of Procurement | Estimated Cost (Rs. In Lakh) | Procurement Action 2014-15
[5 empty] | April | May | June | July | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March
1 | Primary School (new) | 0 | Community Construction | 0
2 | Additional Class Room (without stairs) | 388 | Community Construction | 1728.54 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
3 | Additional Class Room (with stairs) | 194 | Community Construction | 1036.736 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
4 | Toilet/Urinals (Urban) | 0 | Community Construction | 0
5 | Separate Girls Toilet | 120 | Community Construction | 73.2 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
6 | Drinking Water Facility(Urban) | 0 | Community Construction | 0
7 | Disabled friendly Toilet | 160 | Community Construction | 24 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
TOTAL |  | 862 | 0 | 2862.476
Method of Procurement |  |  |  |  | Procurement Action 2014-15 Aug.: Procurement Actions
Community Construction |  |  |  |  | Procurement Action 2014-15 Aug.: 1. Preparation of Specifications and bids document
Open Tender |  |  |  |  | Procurement Action 2014-15 Aug.: 2. Issue of Invitation to bid
3. Open bids
4. Evaluation of bids
5. Award Contracts
6. Construction 25% complete
7. Construction 50% complete
8. Construction 75% complete
9. Construction 100% complete

## Bhojpur
Typical Procurement Schedule for Civil Works under SSA for the year 2014-15
Name of District : Bhojpur
Sl.No. | Description of Goods | Quantity in Numbers | Method of Procurement | Estimated Cost (Rs. In Lakh) | Procurement Action 2014-15
[5 empty] | April | May | June | July | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March
1 | Primary School (new) | 0 | Community Construction | 0
2 | Additional Class Room (without stairs) | 476 | Community Construction | 2120.58 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
3 | Additional Class Room (with stairs) | 238 | Community Construction | 1271.872 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
4 | Toilet/Urinals (Urban) | 4 | Community Construction | 4.84 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
5 | Separate Girls Toilet | 133 | Community Construction | 81.13 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
6 | Drinking Water Facility(Urban) | 0 | Community Construction | 0
TOTAL |  | 137 |  | 3478.422
Method of Procurement |  |  |  |  | Procurement Action 2014-15 Aug.: Procurement Actions
Community Construction |  |  |  |  | Procurement Action 2014-15 Aug.: 1. Preparation of Specifications and bids document
Open Tender |  |  |  |  | Procurement Action 2014-15 Aug.: 2. Issue of Invitation to bid
3. Open bids
4. Evaluation of bids
5. Award Contracts
6. Construction 25% complete
7. Construction 50% complete
8. Construction 75% complete
9. Construction 100% complete

## Bhagalpur
Typical Procurement Schedule for Civil Works under SSA for the year 2014-15
Name of District : Bhagalpur
Sl.No. | Description of Goods | Quantity in Numbers | Method of Procurement | Estimated Cost (Rs. In Lakh) | Procurement Action 2014-15
[5 empty] | April | May | June | July | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March
1 | Primary School (new) | 0 | Community Construction | 0
2 | Additional Class Room (without stairs) | 725 | Community Construction | 3105.9 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
3 | Additional Class Room (with stairs) | 362 | Community Construction | 1879.142 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
4 | Toilet/Urinals (Urban) | 0 | Community Construction | 0
5 | Separate Girls Toilet | 0 | Community Construction | 0
6 | Drinking Water Facility(Urban) | 0 | Community Construction | 0
TOTAL |  | 1087 |  | 4985.042
Method of Procurement |  |  |  |  | Procurement Action 2014-15 Aug.: Procurement Actions
Community Construction |  |  |  |  | Procurement Action 2014-15 Aug.: 1. Preparation of Specifications and bids document
Open Tender |  |  |  |  | Procurement Action 2014-15 Aug.: 2. Issue of Invitation to bid
3. Open bids
4. Evaluation of bids
5. Award Contracts
6. Construction 25% complete
7. Construction 50% complete
8. Construction 75% complete
9. Construction 100% complete

## Begusarai
Typical Procurement Schedule for Civil Works under SSA for the year 2014-15
Name of District :Begusarai
Sl.No. | Description of Goods | Quantity in Numbers | Method of Procurement | Estimated Cost (Rs. In Lakh) | Procurement Action 2014-15
[5 empty] | April | May | June | July | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March
1 | Primary School (new) | 0 | Community Construction | 0
2 | Additional Class Room (without stairs) | 315 | Community Construction | 1428.53 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
3 | Additional Class Room (with stairs) | 157 | Community Construction | 854.08 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
4 | Toilet/Urinals (Urban) | 140 | Community Construction | 85.4 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
5 | Separate Girls Toilet | 140 | Community Construction | 85.4 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
6 | Drinking Water Facility(Urban) | 140 | Community Construction | 24.5 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
TOTAL |  | 420 |  | 195.3
Method of Procurement |  |  |  |  | Procurement Action 2014-15 Aug.: Procurement Actions
Community Construction |  |  |  |  | Procurement Action 2014-15 Aug.: 1. Preparation of Specifications and bids document
Open Tender |  |  |  |  | Procurement Action 2014-15 Aug.: 2. Issue of Invitation to bid
3. Open bids
4. Evaluation of bids
5. Award Contracts
6. Construction 25% complete
7. Construction 50% complete
8. Construction 75% complete
9. Construction 100% complete

## Banka
Typical Procurement Schedule for Civil Works under SSA for the year 2014-15
Name of District : BANKA
Sl.No. | Description of Goods | Quantity in Numbers | Method of Procurement | Estimated Cost (Rs. In Lakh) | Procurement Action 2014-15
[5 empty] | April | May | June | July | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March
1 | Primary School (new) | 0 | Community Construction | 0
2 | Additional Class Room (without stairs) | 403 | Community Construction | 1726.452 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
3 | Additional Class Room (with stairs) | 201 | Community Construction | 1043.391 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
4 | Toilet/Urinals (Urban) | 204 | Community Construction | 124.44 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
5 | Separate Girls Toilet | 117 | Community Construction | 71.37 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
6 | Drinking Water Facility(Urban) | 0 | Community Construction | 0
TOTAL |  | 321 |  | 195.81
Method of Procurement |  |  |  |  | Procurement Action 2014-15 Aug.: Procurement Actions
Community Construction |  |  |  |  | Procurement Action 2014-15 Aug.: 1. Preparation of Specifications and bids document
Open Tender |  |  |  |  | Procurement Action 2014-15 Aug.: 2. Issue of Invitation to bid
3. Open bids
4. Evaluation of bids
5. Award Contracts
6. Construction 25% complete
7. Construction 50% complete
8. Construction 75% complete
9. Construction 100% complete

## Aurangabad
Typical Procurement Schedule for Civil Works under SSA for the year 2014-15
Name of District : AURANGABAD
Sl.No. | Description of Goods | Quantity in Numbers | Method of Procurement | Estimated Cost (Rs. In Lakh) | Procurement Action 2014-15
[5 empty] | April | May | June | July | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March
1 | Primary School (new) | 0 | Community Construction | 0
2 | Additional Class Room (without stairs) | 571 | Community Construction | 2369.079 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
3 | Additional Class Room (with stairs) | 285 | Community Construction | 1523.04 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
4 | Toilet/Urinals (Urban) | 0 | Community Construction | 0
5 | Separate Girls Toilet | 0 | Community Construction | 0
6 | Drinking Water Facility(Urban) | 0 | Community Construction | 0
TOTAL |  | 856 |  | 3892.119
Method of Procurement |  |  |  |  | Procurement Action 2014-15 Aug.: Procurement Actions
Community Construction |  |  |  |  | Procurement Action 2014-15 Aug.: 1. Preparation of Specifications and bids document
Open Tender |  |  |  |  | Procurement Action 2014-15 Aug.: 2. Issue of Invitation to bid
3. Open bids
4. Evaluation of bids
5. Award Contracts
6. Construction 25% complete
7. Construction 50% complete
8. Construction 75% complete
9. Construction 100% complete

## Arwal
Typical Procurement Schedule for Civil Works under SSA for the year 2014-15
Name of District : Arwal
Sl.No. | Description of Goods | Quantity in Numbers | Method of Procurement | Estimated Cost (Rs. In Lakh) | Procurement Action 2014-15
[5 empty] | April | May | June | July | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March
1 | Primary School (new) | 6 | Community Construction | 74.8 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
2 | Additional Class Room (without stairs) | 114 | Community Construction | 472.99 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
3 | Additional Class Room (with stairs) | 57 | Community Construction | 304.608 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
4 | Toilet/Urinals (Urban) | 6 | Community Construction | 7.32 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
5 | Separate Girls Toilet | 0 | Community Construction | 0
6 | Drinking Water Facility(Urban) | 6 | Community Construction | 1.05 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
TOTAL |  | 189 |  | 860.768
Method of Procurement |  |  |  |  | Procurement Action 2014-15 Aug.: Procurement Actions
Community Construction |  |  |  |  | Procurement Action 2014-15 Aug.: 1. Preparation of Specifications and bids document
Open Tender |  |  |  |  | Procurement Action 2014-15 Aug.: 2. Issue of Invitation to bid
3. Open bids
4. Evaluation of bids
5. Award Contracts
6. Construction 25% complete
7. Construction 50% complete
8. Construction 75% complete
9. Construction 100% complete
Primary School
a. Primary School (new)
b. Primary schools sanctioned 2006-07 (deferred liability of 2008-09)
c. New school buildings sanctioned in 2006-07 (deferred liability of 2010-11)
d. New school buildings sanctioned in 2006-07 (deferred liability of 201-12)
c. Building Less (Pry)
Sub Total of Primary Schools
Upper Primary
a. Upper Primary (new)
b. ACR for new UPS
c. Building Less (UP)
Sub Total of Upper Primary Schools
Additional Class Room (without stairs)
Additional Class Room (with stairs)
ACR sanctioned Last Year
Sub-total of ACRs
Toilet/Urinals (Urban)
Separate Girls Toilet
Disabled friendly toilet
Drinking Water Facility(Urban)
Toilets , drinking water, kitchen sheds etc for new UPS
Construction of Building of residential schools for specific category of children
Ramps
Total

## Araria
Typical Procurement Schedule for Civil Works under SSA for the year 2014-15
Name of District : Araria
Sl.No. | Description of Goods | Quantity in Numbers | Method of Procurement | Estimated Cost (Rs. In Lakh) | Procurement Action 2014-15
[5 empty] | April | May | June | July | Aug. | Sept. | Oct. | Nov. | Dec. | Jan. | Feb. | March
1 | Primary School (new) | 0 | Community Construction | 0
2 | Additional Class Room (without stairs) | 337 | Community Construction | 1593.336 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
3 | Additional Class Room (with stairs) | 168 | Community Construction | 952.56 |  |  |  | 1-2 | 3-4 | 5 | 6 | 6 | 7 | 7 | 8 | 9
4 | Toilet/Urinals (Urban) | 0 | Community Construction | 0
5 | Separate Girls Toilet | 0 | Community Construction | 0
6 | Drinking Water Facility(Urban) | 0 | Community Construction | 0
TOTAL |  | 505 |  | 2545.896
Method of Procurement |  |  |  |  | Procurement Action 2014-15 Aug.: Procurement Actions
Community Construction |  |  |  |  | Procurement Action 2014-15 Aug.: 1. Preparation of Specifications and bids document
Open Tender |  |  |  |  | Procurement Action 2014-15 Aug.: 2. Issue of Invitation to bid
3. Open bids
4. Evaluation of bids
5. Award Contracts
6. Construction 25% complete
7. Construction 50% complete
8. Construction 75% complete
9. Construction 100% complete