## State Compiled
Typical List of Service Contracts to be hired under SSA for the year 2014-15
Name of District : State All District (Bihar)
Sl.No. | Name of Consultancy | Estimated Man Months for each Consultancy | No. of Consultancy | Total Estimated Cost (Rs. In Lakh) | Quarterwise Procurement 2014-15 | [7 empty] | Remarks on Proposed method of Procurement
[5 empty] | I |  | II |  | III |  | IV
[5 empty] | Number | Cost | Number | Cost | Number | Cost | Number | Cost
1 | Experts for various functional units at District Level | 0 | 0 | 0 | [8 empty] | As per Service rules of State Implementation Society
2 | Technical Support for SSA through Ed. CIL. | 0 | 0 | 0 | [8 empty] | As per rule of Ed.CIL for hiring of consultants and procurement.
3 | Technical Support on Quality related issues by NCERT | 0 | 0 | 0 | [8 empty] | Apex GOI institutions to provide specialised services to MHRD as per requirement
4 | Technical Support on Educational Planning and Administration related issues by NUEPA | 350 | 0 | 5.8 | 0 | 0 | 0 | 2.9 | 0 | 1.45 | 0 | 1.45
5 | Technical Support on Distance Education by DEP, IGNOU | 0 | 0 | 0
6 | Teachers Training (un trained Teachers) | 62031 | 0 | 1860.93 | 0 | 0 | 0 | 930.465 | 0 | 465.2325 | 0 | 465.2325 | Single Source - Distance Mode
7 | Capacity Building of Project Staff | 0 | 1 | 100 | 1 | 25 | 1 | 25 | 1 | 25 | 1 | 25 | Short listing as per expertise & objective criteria laid down in financial/procurement manual of Govt. of India
8 | CA firm for External Audit | 0 | 39 | 200 | 0 | 0 | 39 | 66.66 | 39 | 66.66 | 39 | 66.66 | Short listing as per expertise & objective criteria laid down in financial/procurement manual of Govt. of India
9 | Concurrent Evaluation through CA Firms | 0 | 3 | 50 | 3 | 12.5 | 3 | 12.5 | 3 | 12.5 | 3 | 12.5
10 | Institutional Monitoring | 0 | 10 | 213 | 0 | 0 | 1 | 21.03 | 6 | 127.8 | 3 | 63.9 | Short listing as per expertise and objective criteria drawn up Dept. of EE&L.
| Grand Total: | 62381 | 53 | 2429.73 | 4 | 37.5 | 44 | 1058.555 | 49 | 698.6425 | 46 | 634.7425

## SLO
Typical List of Service Contracts to be hired under SSA for the year 2014-15
Name of District : SLO
Sl.No. | Name of Consultancy | Estimated Man Months for each Consultancy | No. of Consultancy | Total Estimated Cost (Rs. In Lakh) | Quarterwise Procurement 2014-15 | [7 empty] | Remarks on Proposed method of Procurement
[5 empty] | I |  | II |  | III |  | IV
[5 empty] | Number | Cost | Number | Cost | Number | Cost | Number | Cost
1 | Experts for various functional units at District Level | 0 | 0 | 0 | [8 empty] | As per Service rules of State Implementation Society
2 | Technical Support for SSA through Ed. CIL. | 0 | 0 | 0 | [8 empty] | As per rule of Ed.CIL for hiring of consultants and procurement.
3 | Technical Support on Quality related issues by NCERT | 0 | 0 | 0 | [8 empty] | Apex GOI institutions to provide specialised services to MHRD as per requirement
4 | Technical Support on Educational Planning and Administration related issues by NUEPA | 0 | 0 | 0
5 | Technical Support on Distance Education by DEP, IGNOU | 0 | 0 | 0
6 | Teachers Training (un trained Teachers) | 0 | 0 | 0 | [8 empty] | Single Source - Distance Mode
7 | Capacity Building of Project Staff | 0 | 1 | 100 | 1 | 25 | 1 | 25 | 1 | 25 | 1 | 25 | In-House
8 | CA firm for External Audit | 0 | 39 | 200 | 0 | 0 | 39 | 66.66 | 39 | 66.66 | 39 | 66.66 | Short listing as per expertise & objective criteria laid down in financial/procurement manual of Govt. of India
9 | Concurrent Evaluation through CA Firms | 0 | 3 | 50 | 3 | 12.5 | 3 | 12.5 | 3 | 12.5 | 3 | 12.5
10 | Institutional Monitoring | 0 | 10 | 213 |  |  | 1 | 21.03 | 6 | 127.8 | 3 | 63.9 | Short listing as per expertise and objective criteria drawn up Dept. of EE&L.
| Grand Total: | 0 | 53 | 563 | 4 | 37.5 | 44 | 125.19 | 49 | 231.96 | 46 | 168.06

## West Champaran
Typical List of Service Contracts to be hired under SSA for the year 2014-15
Name of District : WEST CHAMPARAN
Sl.No. | Name of Consultancy | Estimated Man Months for each Consultancy | No. of Consultancy | Total Estimated Cost (Rs. In Lakh) | Quarterwise Procurement 2014-15 | [7 empty] | Remarks on Proposed method of Procurement
[5 empty] | I |  | II |  | III |  | IV
[5 empty] | Number | Cost | Number | Cost | Number | Cost | Number | Cost
1 | Experts for various functional units at District Level | [11 empty] | As per Service rules of State Implementation Society
2 | Technical Support for SSA through Ed. CIL. | [11 empty] | As per rule of Ed.CIL for hiring of consultants and procurement.
3 | Technical Support on Quality related issues by NCERT | [11 empty] | Apex GOI institutions to provide specialised services to MHRD as per requirement
4 | Technical Support on Educational Planning and Administration related issues by NUEPA | 20 |  | 0.328 |  |  |  | 0.164 |  | 0.082 |  | 0.082
5 | Technical Support on Distance Education by DEP, IGNOU
6 | Teachers Training (un trained Teachers) | 1916 |  | 57.48 |  |  |  | 28.74 |  | 14.37 |  | 14.37 | Single Source - Distance Mode
7 | Capacity Building of Project Staff | [11 empty] | Short listing as per expertise & objective criteria laid down in financial/procurement manual of Govt. of India
8 | CA firm for External Audit |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Short listing as per expertise & objective criteria laid down in financial/procurement manual of Govt. of India
9 | Concurrent Evaluation through CA Firms
10 | Institutional Monitoring | [11 empty] | Short listing as per expertise and objective criteria drawn up Dept. of EE&L.
| Grand Total: | 1936 | 0 | 57.808 | 0 | 0 | 0 | 28.904 | 0 | 14.452 | 0 | 14.452

## Vaishali
Typical List of Service Contracts to be hired under SSA for the year 2014-15
Name of District : VAISHALI
Sl.No. | Name of Consultancy | Estimated Man Months for each Consultancy | No. of Consultancy | Total Estimated Cost (Rs. In Lakh) | Quarterwise Procurement 2014-15 | [7 empty] | Remarks on Proposed method of Procurement
[5 empty] | I |  | II |  | III |  | IV
[5 empty] | Number | Cost | Number | Cost | Number | Cost | Number | Cost
1 | Experts for various functional units at District Level | [11 empty] | As per Service rules of State Implementation Society
2 | Technical Support for SSA through Ed. CIL. | [11 empty] | As per rule of Ed.CIL for hiring of consultants and procurement.
3 | Technical Support on Quality related issues by NCERT | [11 empty] | Apex GOI institutions to provide specialised services to MHRD as per requirement
4 | Technical Support on Educational Planning and Administration related issues by NUEPA | 5 |  | 0.084 |  |  |  | 0.042 |  | 0.021 |  | 0.021
5 | Technical Support on Distance Education by DEP, IGNOU
6 | Teachers Training (un trained Teachers) | 2343 |  | 70.29 |  |  |  | 35.145 |  | 17.5725 |  | 17.5725 | Single Source - Distance Mode
7 | Capacity Building of Project Staff | [11 empty] | Short listing as per expertise & objective criteria laid down in financial/procurement manual of Govt. of India
8 | CA firm for External Audit |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Short listing as per expertise & objective criteria laid down in financial/procurement manual of Govt. of India
9 | Concurrent Evaluation through CA Firms
10 | Institutional Monitoring | [11 empty] | Short listing as per expertise and objective criteria drawn up Dept. of EE&L.
| Grand Total: | 2348 | 0 | 70.374 | 0 | 0 | 0 | 35.187 | 0 | 17.5935 | 0 | 17.5935

## Supaul
Typical List of Service Contracts to be hired under SSA for the year 2014-15
Name of District : Supaul
Sl.No. | Name of Consultancy | Estimated Man Months for each Consultancy | No. of Consultancy | Total Estimated Cost (Rs. In Lakh) | Quarterwise Procurement 2014-15 | [7 empty] | Remarks on Proposed method of Procurement
[5 empty] | I |  | II |  | III |  | IV
[5 empty] | Number | Cost | Number | Cost | Number | Cost | Number | Cost
1 | Experts for various functional units at District Level | [11 empty] | As per Service rules of State Implementation Society
2 | Technical Support for SSA through Ed. CIL. | [11 empty] | As per rule of Ed.CIL for hiring of consultants and procurement.
3 | Technical Support on Quality related issues by NCERT | [11 empty] | Apex GOI institutions to provide specialised services to MHRD as per requirement
4 | Technical Support on Educational Planning and Administration related issues by NUEPA | 13 |  | 0.216 |  |  |  | 0.108 |  | 0.054 |  | 0.054
5 | Technical Support on Distance Education by DEP, IGNOU
6 | Teachers Training (un trained Teachers) | 1304 |  | 39.12 |  |  |  | 19.56 |  | 9.78 |  | 9.78 | Single Source - Distance Mode
7 | Capacity Building of Project Staff | [11 empty] | Short listing as per expertise & objective criteria laid down in financial/procurement manual of Govt. of India
8 | CA firm for External Audit |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Short listing as per expertise & objective criteria laid down in financial/procurement manual of Govt. of India
9 | Concurrent Evaluation through CA Firms
10 | Institutional Monitoring | [11 empty] | Short listing as per expertise and objective criteria drawn up Dept. of EE&L.
| Grand Total: | 1317 | 0 | 39.336 | 0 | 0 | 0 | 19.668 | 0 | 9.834 | 0 | 9.834

## Siwan
Typical List of Service Contracts to be hired under SSA for the year 2014-15
Name of District :
Sl.No. | Name of Consultancy | Estimated Man Months for each Consultancy | No. of Consultancy | Total Estimated Cost (Rs. In Lakh) | Quarterwise Procurement 2014-15 | [7 empty] | Remarks on Proposed method of Procurement
[5 empty] | I |  | II |  | III |  | IV
[5 empty] | Number | Cost | Number | Cost | Number | Cost | Number | Cost
1 | Experts for various functional units at District Level | [11 empty] | As per Service rules of State Implementation Society
2 | Technical Support for SSA through Ed. CIL. | [11 empty] | As per rule of Ed.CIL for hiring of consultants and procurement.
3 | Technical Support on Quality related issues by NCERT | [11 empty] | Apex GOI institutions to provide specialised services to MHRD as per requirement
4 | Technical Support on Educational Planning and Administration related issues by NUEPA | 5 |  | 0.084 |  |  |  | 0.042 |  | 0.021 |  | 0.021
5 | Technical Support on Distance Education by DEP, IGNOU
6 | Teachers Training (un trained Teachers) | 1793 |  | 53.79 |  |  |  | 26.895 |  | 13.4475 |  | 13.4475 | Single Source - Distance Mode
7 | Capacity Building of Project Staff | [11 empty] | Short listing as per expertise & objective criteria laid down in financial/procurement manual of Govt. of India
8 | CA firm for External Audit |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Short listing as per expertise & objective criteria laid down in financial/procurement manual of Govt. of India
9 | Concurrent Evaluation through CA Firms
10 | Institutional Monitoring | [11 empty] | Short listing as per expertise and objective criteria drawn up Dept. of EE&L.
| Grand Total: | 1798 | 0 | 53.874 | 0 | 0 | 0 | 26.937 | 0 | 13.4685 | 0 | 13.4685

## Sitamarhi
Typical List of Service Contracts to be hired under SSA for the year 2014-15
Name of District : SITAMARHI
Sl.No. | Name of Consultancy | Estimated Man Months for each Consultancy | No. of Consultancy | Total Estimated Cost (Rs. In Lakh) | Quarterwise Procurement 2014-15 | [7 empty] | Remarks on Proposed method of Procurement
[5 empty] | I |  | II |  | III |  | IV
[5 empty] | Number | Cost | Number | Cost | Number | Cost | Number | Cost
1 | Experts for various functional units at District Level | [11 empty] | As per Service rules of State Implementation Society
2 | Technical Support for SSA through Ed. CIL. | [11 empty] | As per rule of Ed.CIL for hiring of consultants and procurement.
3 | Technical Support on Quality related issues by NCERT | [11 empty] | Apex GOI institutions to provide specialised services to MHRD as per requirement
4 | Technical Support on Educational Planning and Administration related issues by NUEPA | 4 |  | 0.068 |  |  |  | 0.034 |  | 0.017 |  | 0.017
5 | Technical Support on Distance Education by DEP, IGNOU
6 | Teachers Training (un trained Teachers) | 1583 |  | 47.49 |  |  |  | 23.745 |  | 11.8725 |  | 11.8725 | Single Source - Distance Mode
7 | Capacity Building of Project Staff | [11 empty] | Short listing as per expertise & objective criteria laid down in financial/procurement manual of Govt. of India
8 | CA firm for External Audit |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Short listing as per expertise & objective criteria laid down in financial/procurement manual of Govt. of India
9 | Concurrent Evaluation through CA Firms
10 | Institutional Monitoring | [11 empty] | Short listing as per expertise and objective criteria drawn up Dept. of EE&L.
| Grand Total: | 1587 | 0 | 47.558 | 0 | 0 | 0 | 23.779 | 0 | 11.8895 | 0 | 11.8895

## Sheohar
Typical List of Service Contracts to be hired under SSA for the year 2014-15
Name of District : Sheohar
Sl.No. | Name of Consultancy | Estimated Man Months for each Consultancy | No. of Consultancy | Total Estimated Cost (Rs. In Lakh) | Quarterwise Procurement 2014-15 | [7 empty] | Remarks on Proposed method of Procurement
[5 empty] | I |  | II |  | III |  | IV
[5 empty] | Number | Cost | Number | Cost | Number | Cost | Number | Cost
1 | Experts for various functional units at District Level | [11 empty] | As per Service rules of State Implementation Society
2 | Technical Support for SSA through Ed. CIL. | [11 empty] | As per rule of Ed.CIL for hiring of consultants and procurement.
3 | Technical Support on Quality related issues by NCERT | [11 empty] | Apex GOI institutions to provide specialised services to MHRD as per requirement
4 | Technical Support on Educational Planning and Administration related issues by NUEPA | 4 |  | 0.068 |  |  |  | 0.034 |  | 0.017 |  | 0.017
5 | Technical Support on Distance Education by DEP, IGNOU
6 | Teachers Training (un trained Teachers) | 21 |  | 0.63 |  |  |  | 0.315 |  | 0.1575 |  | 0.1575 | Single Source - Distance Mode
7 | Capacity Building of Project Staff | [11 empty] | Short listing as per expertise & objective criteria laid down in financial/procurement manual of Govt. of India
8 | CA firm for External Audit |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Short listing as per expertise & objective criteria laid down in financial/procurement manual of Govt. of India
9 | Concurrent Evaluation through CA Firms
10 | Institutional Monitoring | [11 empty] | Short listing as per expertise and objective criteria drawn up Dept. of EE&L.
| Grand Total: | 25 | 0 | 0.698 | 0 | 0 | 0 | 0.349 | 0 | 0.1745 | 0 | 0.1745

## Sheikhpura
Typical List of Service Contracts to be hired under SSA for the year 2014-15
Name of District : Sheikhpura
Sl.No. | Name of Consultancy | Estimated Man Months for each Consultancy | No. of Consultancy | Total Estimated Cost (Rs. In Lakh) | Quarterwise Procurement 2014-15 | [7 empty] | Remarks on Proposed method of Procurement
[5 empty] | I |  | II |  | III |  | IV
[5 empty] | Number | Cost | Number | Cost | Number | Cost | Number | Cost
1 | Experts for various functional units at District Level | [11 empty] | As per Service rules of State Implementation Society
2 | Technical Support for SSA through Ed. CIL. | [11 empty] | As per rule of Ed.CIL for hiring of consultants and procurement.
3 | Technical Support on Quality related issues by NCERT | [11 empty] | Apex GOI institutions to provide specialised services to MHRD as per requirement
4 | Technical Support on Educational Planning and Administration related issues by NUEPA | 4 |  | 0.068 |  |  |  | 0.034 |  | 0.017 |  | 0.017
5 | Technical Support on Distance Education by DEP, IGNOU
6 | Teachers Training (un trained Teachers) | 364 |  | 10.92 |  |  |  | 5.46 |  | 2.73 |  | 2.73 | Single Source - Distance Mode
7 | Capacity Building of Project Staff | [11 empty] | Short listing as per expertise & objective criteria laid down in financial/procurement manual of Govt. of India
8 | CA firm for External Audit |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Short listing as per expertise & objective criteria laid down in financial/procurement manual of Govt. of India
9 | Concurrent Evaluation through CA Firms
10 | Institutional Monitoring | [11 empty] | Short listing as per expertise and objective criteria drawn up Dept. of EE&L.
| Grand Total: | 368 | 0 | 10.988 | 0 | 0 | 0 | 5.494 | 0 | 2.747 | 0 | 2.747

## Saran
Typical List of Service Contracts to be hired under SSA for the year 2014-15
Name of District : Saran
Sl.No. | Name of Consultancy | Estimated Man Months for each Consultancy | No. of Consultancy | Total Estimated Cost (Rs. In Lakh) | Quarterwise Procurement 2014-15 | [7 empty] | Remarks on Proposed method of Procurement
[5 empty] | I |  | II |  | III |  | IV
[5 empty] | Number | Cost | Number | Cost | Number | Cost | Number | Cost
1 | Experts for various functional units at District Level | [11 empty] | As per Service rules of State Implementation Society
2 | Technical Support for SSA through Ed. CIL. | [11 empty] | As per rule of Ed.CIL for hiring of consultants and procurement.
3 | Technical Support on Quality related issues by NCERT | [11 empty] | Apex GOI institutions to provide specialised services to MHRD as per requirement
4 | Technical Support on Educational Planning and Administration related issues by NUEPA | 6 |  | 0.1 |  |  |  | 0.05 |  | 0.025 |  | 0.025
5 | Technical Support on Distance Education by DEP, IGNOU
6 | Teachers Training (un trained Teachers) | 1234 |  | 37.02 |  |  |  | 18.51 |  | 9.255 |  | 9.255 | Single Source - Distance Mode
7 | Capacity Building of Project Staff | [11 empty] | Short listing as per expertise & objective criteria laid down in financial/procurement manual of Govt. of India
8 | CA firm for External Audit |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Short listing as per expertise & objective criteria laid down in financial/procurement manual of Govt. of India
9 | Concurrent Evaluation through CA Firms
10 | Institutional Monitoring | [11 empty] | Short listing as per expertise and objective criteria drawn up Dept. of EE&L.
| Grand Total: | 1240 | 0 | 37.12 | 0 | 0 | 0 | 18.56 | 0 | 9.28 | 0 | 9.28

## Samastipur
Typical List of Service Contracts to be hired under SSA for the year 2014-15
Name of District : Samastipur
Sl.No. | Name of Consultancy | Estimated Man Months for each Consultancy | No. of Consultancy | Total Estimated Cost (Rs. In Lakh) | Quarterwise Procurement 2014-15 | [7 empty] | Remarks on Proposed method of Procurement
[5 empty] | I |  | II |  | III |  | IV
[5 empty] | Number | Cost | Number | Cost | Number | Cost | Number | Cost
1 | Experts for various functional units at District Level | [11 empty] | As per Service rules of State Implementation Society
2 | Technical Support for SSA through Ed. CIL. | [11 empty] | As per rule of Ed.CIL for hiring of consultants and procurement.
3 | Technical Support on Quality related issues by NCERT | [11 empty] | Apex GOI institutions to provide specialised services to MHRD as per requirement
4 | Technical Support on Educational Planning and Administration related issues by NUEPA | 6 |  | 0.1 |  |  |  | 0.05 |  | 0.025 |  | 0.025
5 | Technical Support on Distance Education by DEP, IGNOU
6 | Teachers Training (un trained Teachers) | 2175 |  | 65.25 |  |  |  | 32.625 |  | 16.3125 |  | 16.3125 | Single Source - Distance Mode
7 | Capacity Building of Project Staff | [11 empty] | Short listing as per expertise & objective criteria laid down in financial/procurement manual of Govt. of India
8 | CA firm for External Audit |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Short listing as per expertise & objective criteria laid down in financial/procurement manual of Govt. of India
9 | Concurrent Evaluation through CA Firms
10 | Institutional Monitoring | [11 empty] | Short listing as per expertise and objective criteria drawn up Dept. of EE&L.
| Grand Total: | 2181 | 0 | 65.35 | 0 | 0 | 0 | 32.675 | 0 | 16.3375 | 0 | 16.3375

## Saharsa
Typical List of Service Contracts to be hired under SSA for the year 2014-15
Name of District : SAHARSA
Sl.No. | Name of Consultancy | Estimated Man Months for each Consultancy | No. of Consultancy | Total Estimated Cost (Rs. In Lakh) | Quarterwise Procurement 2014-15 | [7 empty] | Remarks on Proposed method of Procurement
[5 empty] | I |  | II |  | III |  | IV
[5 empty] | Number | Cost | Number | Cost | Number | Cost | Number | Cost
1 | Experts for various functional units at District Level | [11 empty] | As per Service rules of State Implementation Society
2 | Technical Support for SSA through Ed. CIL. | [11 empty] | As per rule of Ed.CIL for hiring of consultants and procurement.
3 | Technical Support on Quality related issues by NCERT | [11 empty] | Apex GOI institutions to provide specialised services to MHRD as per requirement
4 | Technical Support on Educational Planning and Administration related issues by NUEPA | 5 |  | 0.084 |  |  |  | 0.042 |  | 0.021 |  | 0.021
5 | Technical Support on Distance Education by DEP, IGNOU
6 | Teachers Training (un trained Teachers) | 1128 |  | 33.84 |  |  |  | 16.92 |  | 8.46 |  | 8.46 | Single Source - Distance Mode
7 | Capacity Building of Project Staff | [11 empty] | Short listing as per expertise & objective criteria laid down in financial/procurement manual of Govt. of India
8 | CA firm for External Audit |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Short listing as per expertise & objective criteria laid down in financial/procurement manual of Govt. of India
9 | Concurrent Evaluation through CA Firms
10 | Institutional Monitoring | [11 empty] | Short listing as per expertise and objective criteria drawn up Dept. of EE&L.
| Grand Total: | 1133 | 0 | 33.924 | 0 | 0 | 0 | 16.962 | 0 | 8.481 | 0 | 8.481

## Rohtas
Typical List of Service Contracts to be hired under SSA for the year 2014-15
Name of District : Rohtas
Sl.No. | Name of Consultancy | Estimated Man Months for each Consultancy | No. of Consultancy | Total Estimated Cost (Rs. In Lakh) | Quarterwise Procurement 2014-15 | [7 empty] | Remarks on Proposed method of Procurement
[5 empty] | I |  | II |  | III |  | IV
[5 empty] | Number | Cost | Number | Cost | Number | Cost | Number | Cost
1 | Experts for various functional units at District Level | [11 empty] | As per Service rules of State Implementation Society
2 | Technical Support for SSA through Ed. CIL. | [11 empty] | As per rule of Ed.CIL for hiring of consultants and procurement.
3 | Technical Support on Quality related issues by NCERT | [11 empty] | Apex GOI institutions to provide specialised services to MHRD as per requirement
4 | Technical Support on Educational Planning and Administration related issues by NUEPA | 32 |  | 0.528 |  |  |  | 0.264 |  | 0.132 |  | 0.132
5 | Technical Support on Distance Education by DEP, IGNOU
6 | Teachers Training (un trained Teachers) | 1565 |  | 46.95 |  |  |  | 23.475 |  | 11.7375 |  | 11.7375 | Single Source - Distance Mode
7 | Capacity Building of Project Staff | [11 empty] | Short listing as per expertise & objective criteria laid down in financial/procurement manual of Govt. of India
8 | CA firm for External Audit |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Short listing as per expertise & objective criteria laid down in financial/procurement manual of Govt. of India
9 | Concurrent Evaluation through CA Firms
10 | Institutional Monitoring | [11 empty] | Short listing as per expertise and objective criteria drawn up Dept. of EE&L.
| Grand Total: | 1597 | 0 | 47.478 | 0 | 0 | 0 | 23.739 | 0 | 11.8695 | 0 | 11.8695

## Purnia
Typical List of Service Contracts to be hired under SSA for the year 2014-15
Name of District :
Sl.No. | Name of Consultancy | Estimated Man Months for each Consultancy | No. of Consultancy | Total Estimated Cost (Rs. In Lakh) | Quarterwise Procurement 2014-15 | [7 empty] | Remarks on Proposed method of Procurement
[5 empty] | I |  | II |  | III |  | IV
[5 empty] | Number | Cost | Number | Cost | Number | Cost | Number | Cost
1 | Experts for various functional units at District Level | [11 empty] | As per Service rules of State Implementation Society
2 | Technical Support for SSA through Ed. CIL. | [11 empty] | As per rule of Ed.CIL for hiring of consultants and procurement.
3 | Technical Support on Quality related issues by NCERT | [11 empty] | Apex GOI institutions to provide specialised services to MHRD as per requirement
4 | Technical Support on Educational Planning and Administration related issues by NUEPA | 4 |  | 0.068 |  |  |  | 0.034 |  | 0.017 |  | 0.017
5 | Technical Support on Distance Education by DEP, IGNOU
6 | Teachers Training (un trained Teachers) | 1923 |  | 57.69 |  |  |  | 28.845 |  | 14.4225 |  | 14.4225 | Single Source - Distance Mode
7 | Capacity Building of Project Staff | [11 empty] | Short listing as per expertise & objective criteria laid down in financial/procurement manual of Govt. of India
8 | CA firm for External Audit |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Short listing as per expertise & objective criteria laid down in financial/procurement manual of Govt. of India
9 | Concurrent Evaluation through CA Firms
10 | Institutional Monitoring | [11 empty] | Short listing as per expertise and objective criteria drawn up Dept. of EE&L.
| Grand Total: | 1927 | 0 | 57.758 | 0 | 0 | 0 | 28.879 | 0 | 14.4395 | 0 | 14.4395

## Patna (U)
Typical List of Service Contracts to be hired under SSA for the year 2014-15
Name of District : Patna (Urban)
Sl.No. | Name of Consultancy | Estimated Man Months for each Consultancy | No. of Consultancy | Total Estimated Cost (Rs. In Lakh) | Quarterwise Procurement 2014-15 | [7 empty] | Remarks on Proposed method of Procurement
[5 empty] | I |  | II |  | III |  | IV
[5 empty] | Number | Cost | Number | Cost | Number | Cost | Number | Cost
1 | Experts for various functional units at District Level | [11 empty] | As per Service rules of State Implementation Society
2 | Technical Support for SSA through Ed. CIL. | [11 empty] | As per rule of Ed.CIL for hiring of consultants and procurement.
3 | Technical Support on Quality related issues by NCERT | [11 empty] | Apex GOI institutions to provide specialised services to MHRD as per requirement
4 | Technical Support on Educational Planning and Administration related issues by NUEPA | 4 |  | 0.068 |  |  |  | 0.034 |  | 0.017 |  | 0.017
5 | Technical Support on Distance Education by DEP, IGNOU
6 | Teachers Training (un trained Teachers) | 253 |  | 7.59 |  |  |  | 3.795 |  | 1.8975 |  | 1.8975 | Single Source - Distance Mode
7 | Capacity Building of Project Staff | [11 empty] | Short listing as per expertise & objective criteria laid down in financial/procurement manual of Govt. of India
8 | CA firm for External Audit |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Short listing as per expertise & objective criteria laid down in financial/procurement manual of Govt. of India
9 | Concurrent Evaluation through CA Firms
10 | Institutional Monitoring | [11 empty] | Short listing as per expertise and objective criteria drawn up Dept. of EE&L.
| Grand Total: | 257 | 0 | 7.658 | 0 | 0 | 0 | 3.829 | 0 | 1.9145 | 0 | 1.9145

## Patna (R)
Typical List of Service Contracts to be hired under SSA for the year 2014-15
Name of District : Patna (Rural)
Sl.No. | Name of Consultancy | Estimated Man Months for each Consultancy | No. of Consultancy | Total Estimated Cost (Rs. In Lakh) | Quarterwise Procurement 2014-15 | [7 empty] | Remarks on Proposed method of Procurement
[5 empty] | I |  | II |  | III |  | IV
[5 empty] | Number | Cost | Number | Cost | Number | Cost | Number | Cost
1 | Experts for various functional units at District Level | [11 empty] | As per Service rules of State Implementation Society
2 | Technical Support for SSA through Ed. CIL. | [11 empty] | As per rule of Ed.CIL for hiring of consultants and procurement.
3 | Technical Support on Quality related issues by NCERT | [11 empty] | Apex GOI institutions to provide specialised services to MHRD as per requirement
4 | Technical Support on Educational Planning and Administration related issues by NUEPA | 7 |  | 0.116 |  |  |  | 0.058 |  | 0.029 |  | 0.029
5 | Technical Support on Distance Education by DEP, IGNOU
6 | Teachers Training (un trained Teachers) | 3927 |  | 117.81 |  |  |  | 58.905 |  | 29.4525 |  | 29.4525 | Single Source - Distance Mode
7 | Capacity Building of Project Staff | [11 empty] | Short listing as per expertise & objective criteria laid down in financial/procurement manual of Govt. of India
8 | CA firm for External Audit |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Short listing as per expertise & objective criteria laid down in financial/procurement manual of Govt. of India
9 | Concurrent Evaluation through CA Firms
10 | Institutional Monitoring | [11 empty] | Short listing as per expertise and objective criteria drawn up Dept. of EE&L.
| Grand Total: | 3934 | 0 | 117.926 | 0 | 0 | 0 | 58.963 | 0 | 29.4815 | 0 | 29.4815

## Nawada
Typical List of Service Contracts to be hired under SSA for the year 2014-15
Name of District : Nawada
Sl.No. | Name of Consultancy | Estimated Man Months for each Consultancy | No. of Consultancy | Total Estimated Cost (Rs. In Lakh) | Quarterwise Procurement 2014-15 | [7 empty] | Remarks on Proposed method of Procurement
[5 empty] | I |  | II |  | III |  | IV
[5 empty] | Number | Cost | Number | Cost | Number | Cost | Number | Cost
1 | Experts for various functional units at District Level | [11 empty] | As per Service rules of State Implementation Society
2 | Technical Support for SSA through Ed. CIL. | [11 empty] | As per rule of Ed.CIL for hiring of consultants and procurement.
3 | Technical Support on Quality related issues by NCERT | [11 empty] | Apex GOI institutions to provide specialised services to MHRD as per requirement
4 | Technical Support on Educational Planning and Administration related issues by NUEPA | 19 |  | 0.312 |  |  |  | 0.156 |  | 0.078 |  | 0.078
5 | Technical Support on Distance Education by DEP, IGNOU
6 | Teachers Training (un trained Teachers) | 1012 |  | 30.36 |  |  |  | 15.18 |  | 7.59 |  | 7.59 | Single Source - Distance Mode
7 | Capacity Building of Project Staff | [11 empty] | Short listing as per expertise & objective criteria laid down in financial/procurement manual of Govt. of India
8 | CA firm for External Audit |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Short listing as per expertise & objective criteria laid down in financial/procurement manual of Govt. of India
9 | Concurrent Evaluation through CA Firms
10 | Institutional Monitoring | [11 empty] | Short listing as per expertise and objective criteria drawn up Dept. of EE&L.
| Grand Total: | 1031 | 0 | 30.672 | 0 | 0 | 0 | 15.336 | 0 | 7.668 | 0 | 7.668

## Nalanda
Typical List of Service Contracts to be hired under SSA for the year 2014-15
Name of District : Nalanda
Sl.No. | Name of Consultancy | Estimated Man Months for each Consultancy | No. of Consultancy | Total Estimated Cost (Rs. In Lakh) | Quarterwise Procurement 2014-15 | [7 empty] | Remarks on Proposed method of Procurement
[5 empty] | I |  | II |  | III |  | IV
[5 empty] | Number | Cost | Number | Cost | Number | Cost | Number | Cost
1 | Experts for various functional units at District Level | [11 empty] | As per Service rules of State Implementation Society
2 | Technical Support for SSA through Ed. CIL. | [11 empty] | As per rule of Ed.CIL for hiring of consultants and procurement.
3 | Technical Support on Quality related issues by NCERT | [11 empty] | Apex GOI institutions to provide specialised services to MHRD as per requirement
4 | Technical Support on Educational Planning and Administration related issues by NUEPA | 6 |  | 0.1 |  |  |  | 0.05 |  | 0.025 |  | 0.025
5 | Technical Support on Distance Education by DEP, IGNOU
6 | Teachers Training (un trained Teachers) | 2878 |  | 86.34 |  |  |  | 43.17 |  | 21.585 |  | 21.585 | Single Source - Distance Mode
7 | Capacity Building of Project Staff | [11 empty] | Short listing as per expertise & objective criteria laid down in financial/procurement manual of Govt. of India
8 | CA firm for External Audit |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Short listing as per expertise & objective criteria laid down in financial/procurement manual of Govt. of India
9 | Concurrent Evaluation through CA Firms
10 | Institutional Monitoring | [11 empty] | Short listing as per expertise and objective criteria drawn up Dept. of EE&L.
| Grand Total: | 2884 | 0 | 86.44 | 0 | 0 | 0 | 43.22 | 0 | 21.61 | 0 | 21.61

## Muzafferpur
Typical List of Service Contracts to be hired under SSA for the year 2014-15
Name of District : Muzaffarpur
Sl.No. | Name of Consultancy | Estimated Man Months for each Consultancy | No. of Consultancy | Total Estimated Cost (Rs. In Lakh) | Quarterwise Procurement 2014-15 | [7 empty] | Remarks on Proposed method of Procurement
[5 empty] | I |  | II |  | III |  | IV
[5 empty] | Number | Cost | Number | Cost | Number | Cost | Number | Cost
1 | Experts for various functional units at District Level | [11 empty] | As per Service rules of State Implementation Society
2 | Technical Support for SSA through Ed. CIL. | [11 empty] | As per rule of Ed.CIL for hiring of consultants and procurement.
3 | Technical Support on Quality related issues by NCERT | [11 empty] | Apex GOI institutions to provide specialised services to MHRD as per requirement
4 | Technical Support on Educational Planning and Administration related issues by NUEPA | 31 |  | 0.508 |  |  |  | 0.254 |  | 0.127 |  | 0.127
5 | Technical Support on Distance Education by DEP, IGNOU
6 | Teachers Training (un trained Teachers) | 2753 |  | 82.59 |  |  |  | 41.295 |  | 20.6475 |  | 20.6475 | Single Source - Distance Mode
7 | Capacity Building of Project Staff | [11 empty] | Short listing as per expertise & objective criteria laid down in financial/procurement manual of Govt. of India
8 | CA firm for External Audit |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Short listing as per expertise & objective criteria laid down in financial/procurement manual of Govt. of India
9 | Concurrent Evaluation through CA Firms
10 | Institutional Monitoring | [11 empty] | Short listing as per expertise and objective criteria drawn up Dept. of EE&L.
| Grand Total: | 2784 | 0 | 83.098 | 0 | 0 | 0 | 41.549 | 0 | 20.7745 | 0 | 20.7745

## Munger
Typical List of Service Contracts to be hired under SSA for the year 2014-15
Name of District : Munger
Sl.No. | Name of Consultancy | Estimated Man Months for each Consultancy | No. of Consultancy | Total Estimated Cost (Rs. In Lakh) | Quarterwise Procurement 2014-15 | [7 empty] | Remarks on Proposed method of Procurement
[5 empty] | I |  | II |  | III |  | IV
[5 empty] | Number | Cost | Number | Cost | Number | Cost | Number | Cost
1 | Experts for various functional units at District Level | [11 empty] | As per Service rules of State Implementation Society
2 | Technical Support for SSA through Ed. CIL. | [11 empty] | As per rule of Ed.CIL for hiring of consultants and procurement.
3 | Technical Support on Quality related issues by NCERT | [11 empty] | Apex GOI institutions to provide specialised services to MHRD as per requirement
4 | Technical Support on Educational Planning and Administration related issues by NUEPA | 10 |  | 0.164 |  |  |  | 0.082 |  | 0.041 |  | 0.041
5 | Technical Support on Distance Education by DEP, IGNOU
6 | Teachers Training (un trained Teachers) | 1352 |  | 40.56 |  |  |  | 20.28 |  | 10.14 |  | 10.14 | Single Source - Distance Mode
7 | Capacity Building of Project Staff | [11 empty] | Short listing as per expertise & objective criteria laid down in financial/procurement manual of Govt. of India
8 | CA firm for External Audit |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Short listing as per expertise & objective criteria laid down in financial/procurement manual of Govt. of India
9 | Concurrent Evaluation through CA Firms
10 | Institutional Monitoring | [11 empty] | Short listing as per expertise and objective criteria drawn up Dept. of EE&L.
| Grand Total: | 1362 | 0 | 40.724 | 0 | 0 | 0 | 20.362 | 0 | 10.181 | 0 | 10.181

## Madhubani
Typical List of Service Contracts to be hired under SSA for the year 2014-15
Name of District : Madhubani
Sl.No. | Name of Consultancy | Estimated Man Months for each Consultancy | No. of Consultancy | Total Estimated Cost (Rs. In Lakh) | Quarterwise Procurement 2014-15 | [7 empty] | Remarks on Proposed method of Procurement
[5 empty] | I |  | II |  | III |  | IV
[5 empty] | Number | Cost | Number | Cost | Number | Cost | Number | Cost
1 | Experts for various functional units at District Level | [11 empty] | As per Service rules of State Implementation Society
2 | Technical Support for SSA through Ed. CIL. | [11 empty] | As per rule of Ed.CIL for hiring of consultants and procurement.
3 | Technical Support on Quality related issues by NCERT | [11 empty] | Apex GOI institutions to provide specialised services to MHRD as per requirement
4 | Technical Support on Educational Planning and Administration related issues by NUEPA | 6 |  | 0.1 |  |  |  | 0.05 |  | 0.025 |  | 0.025
5 | Technical Support on Distance Education by DEP, IGNOU
6 | Teachers Training (un trained Teachers) | 2424 |  | 72.72 |  |  |  | 36.36 |  | 18.18 |  | 18.18 | Single Source - Distance Mode
7 | Capacity Building of Project Staff | [11 empty] | Short listing as per expertise & objective criteria laid down in financial/procurement manual of Govt. of India
8 | CA firm for External Audit |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Short listing as per expertise & objective criteria laid down in financial/procurement manual of Govt. of India
9 | Concurrent Evaluation through CA Firms
10 | Institutional Monitoring | [11 empty] | Short listing as per expertise and objective criteria drawn up Dept. of EE&L.
| Grand Total: | 2430 | 0 | 72.82 | 0 | 0 | 0 | 36.41 | 0 | 18.205 | 0 | 18.205

## Madhepura
Typical List of Service Contracts to be hired under SSA for the year 2014-15
Name of District : Madhepura
Sl.No. | Name of Consultancy | Estimated Man Months for each Consultancy | No. of Consultancy | Total Estimated Cost (Rs. In Lakh) | Quarterwise Procurement 2014-15 | [7 empty] | Remarks on Proposed method of Procurement
[5 empty] | I |  | II |  | III |  | IV
[5 empty] | Number | Cost | Number | Cost | Number | Cost | Number | Cost
1 | Experts for various functional units at District Level | 0 | 0 | 0 | [8 empty] | As per Service rules of State Implementation Society
2 | Technical Support for SSA through Ed. CIL. | 0 | 0 | 0 | [8 empty] | As per rule of Ed.CIL for hiring of consultants and procurement.
3 | Technical Support on Quality related issues by NCERT | 0 | 0 | 0 | [8 empty] | Apex GOI institutions to provide specialised services to MHRD as per requirement
4 | Technical Support on Educational Planning and Administration related issues by NUEPA | 5 | 0 | 0.084 |  |  |  | 0.042 |  | 0.021 |  | 0.021
5 | Technical Support on Distance Education by DEP, IGNOU | 0 | 0 | 0
6 | Teachers Training (un trained Teachers) | 1684 | 0 | 50.52 |  |  |  | 25.26 |  | 12.63 |  | 12.63 | Single Source - Distance Mode
7 | Capacity Building of Project Staff | 0 | 0 | 0 | [8 empty] | Short listing as per expertise & objective criteria laid down in financial/procurement manual of Govt. of India
8 | CA firm for External Audit | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Short listing as per expertise & objective criteria laid down in financial/procurement manual of Govt. of India
9 | Concurrent Evaluation through CA Firms | 0 | 0 | 0
10 | Institutional Monitoring | 0 | 0 | 0 | [8 empty] | Short listing as per expertise and objective criteria drawn up Dept. of EE&L.
| Grand Total: | 1689 | 0 | 50.604 | 0 | 0 | 0 | 25.302 | 0 | 12.651 | 0 | 12.651

## Lakhisarai
Typical List of Service Contracts to be hired under SSA for the year 2014-15
Name of District : Lakhisarai
Sl.No. | Name of Consultancy | Estimated Man Months for each Consultancy | No. of Consultancy | Total Estimated Cost (Rs. In Lakh) | Quarterwise Procurement 2014-15 | [7 empty] | Remarks on Proposed method of Procurement
[5 empty] | I |  | II |  | III |  | IV
[5 empty] | Number | Cost | Number | Cost | Number | Cost | Number | Cost
1 | Experts for various functional units at District Level | [11 empty] | As per Service rules of State Implementation Society
2 | Technical Support for SSA through Ed. CIL. | [11 empty] | As per rule of Ed.CIL for hiring of consultants and procurement.
3 | Technical Support on Quality related issues by NCERT | [11 empty] | Apex GOI institutions to provide specialised services to MHRD as per requirement
4 | Technical Support on Educational Planning and Administration related issues by NUEPA | 4 |  | 0.068 |  |  |  | 0.034 |  | 0.017 |  | 0.017
5 | Technical Support on Distance Education by DEP, IGNOU
6 | Teachers Training (un trained Teachers) | 428 |  | 12.84 |  |  |  | 6.42 |  | 3.21 |  | 3.21 | Single Source - Distance Mode
7 | Capacity Building of Project Staff | [11 empty] | Short listing as per expertise & objective criteria laid down in financial/procurement manual of Govt. of India
8 | CA firm for External Audit |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Short listing as per expertise & objective criteria laid down in financial/procurement manual of Govt. of India
9 | Concurrent Evaluation through CA Firms
10 | Institutional Monitoring | [11 empty] | Short listing as per expertise and objective criteria drawn up Dept. of EE&L.
| Grand Total: | 432 | 0 | 12.908 | 0 | 0 | 0 | 6.454 | 0 | 3.227 | 0 | 3.227

## Kishanganj
Typical List of Service Contracts to be hired under SSA for the year 2014-15
Name of District : KISHANGANJ
Sl.No. | Name of Consultancy | Estimated Man Months for each Consultancy | No. of Consultancy | Total Estimated Cost (Rs. In Lakh) | Quarterwise Procurement 2014-15 | [7 empty] | Remarks on Proposed method of Procurement
[5 empty] | I |  | II |  | III |  | IV
[5 empty] | Number | Cost | Number | Cost | Number | Cost | Number | Cost
1 | Experts for various functional units at District Level | [11 empty] | As per Service rules of State Implementation Society
2 | Technical Support for SSA through Ed. CIL. | [11 empty] | As per rule of Ed.CIL for hiring of consultants and procurement.
3 | Technical Support on Quality related issues by NCERT | [11 empty] | Apex GOI institutions to provide specialised services to MHRD as per requirement
4 | Technical Support on Educational Planning and Administration related issues by NUEPA | 4 |  | 0.068 |  |  |  | 0.034 |  | 0.017 |  | 0.017
5 | Technical Support on Distance Education by DEP, IGNOU
6 | Teachers Training (un trained Teachers) | 617 |  | 18.51 |  |  |  | 9.255 |  | 4.6275 |  | 4.6275 | Single Source - Distance Mode
7 | Capacity Building of Project Staff | [11 empty] | Short listing as per expertise & objective criteria laid down in financial/procurement manual of Govt. of India
8 | CA firm for External Audit |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Short listing as per expertise & objective criteria laid down in financial/procurement manual of Govt. of India
9 | Concurrent Evaluation through CA Firms
10 | Institutional Monitoring | [11 empty] | Short listing as per expertise and objective criteria drawn up Dept. of EE&L.
| Grand Total: | 621 | 0 | 18.578 | 0 | 0 | 0 | 9.289 | 0 | 4.6445 | 0 | 4.6445

## Khagaria
Typical List of Service Contracts to be hired under SSA for the year 2014-15
Name of District : Khagaria
Sl.No. | Name of Consultancy | Estimated Man Months for each Consultancy | No. of Consultancy | Total Estimated Cost (Rs. In Lakh) | Quarterwise Procurement 2014-15 | [7 empty] | Remarks on Proposed method of Procurement
[5 empty] | I |  | II |  | III |  | IV
[5 empty] | Number | Cost | Number | Cost | Number | Cost | Number | Cost
1 | Experts for various functional units at District Level | [11 empty] | As per Service rules of State Implementation Society
2 | Technical Support for SSA through Ed. CIL. | [11 empty] | As per rule of Ed.CIL for hiring of consultants and procurement.
3 | Technical Support on Quality related issues by NCERT | [11 empty] | Apex GOI institutions to provide specialised services to MHRD as per requirement
4 | Technical Support on Educational Planning and Administration related issues by NUEPA | 22 |  | 0.36 |  |  |  | 0.18 |  | 0.09 |  | 0.09
5 | Technical Support on Distance Education by DEP, IGNOU
6 | Teachers Training (un trained Teachers) | 1264 |  | 37.92 |  |  |  | 18.96 |  | 9.48 |  | 9.48 | Single Source - Distance Mode
7 | Capacity Building of Project Staff | [11 empty] | Short listing as per expertise & objective criteria laid down in financial/procurement manual of Govt. of India
8 | CA firm for External Audit |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Short listing as per expertise & objective criteria laid down in financial/procurement manual of Govt. of India
9 | Concurrent Evaluation through CA Firms
10 | Institutional Monitoring | [11 empty] | Short listing as per expertise and objective criteria drawn up Dept. of EE&L.
| Grand Total: | 1286 | 0 | 38.28 | 0 | 0 | 0 | 19.14 | 0 | 9.57 | 0 | 9.57

## Katihar
Typical List of Service Contracts to be hired under SSA for the year 2014-15
Name of District : KATIHAR
Sl.No. | Name of Consultancy | Estimated Man Months for each Consultancy | No. of Consultancy | Total Estimated Cost (Rs. In Lakh) | Quarterwise Procurement 2014-15 | [7 empty] | Remarks on Proposed method of Procurement
[5 empty] | I |  | II |  | III |  | IV
[5 empty] | Number | Cost | Number | Cost | Number | Cost | Number | Cost
1 | Experts for various functional units at District Level | [11 empty] | As per Service rules of State Implementation Society
2 | Technical Support for SSA through Ed. CIL. | [11 empty] | As per rule of Ed.CIL for hiring of consultants and procurement.
3 | Technical Support on Quality related issues by NCERT | [11 empty] | Apex GOI institutions to provide specialised services to MHRD as per requirement
4 | Technical Support on Educational Planning and Administration related issues by NUEPA | 4 |  | 0.068 |  |  |  | 0.034 |  | 0.017 |  | 0.017
5 | Technical Support on Distance Education by DEP, IGNOU
6 | Teachers Training (un trained Teachers) | 1081 |  | 32.43 |  |  |  | 16.215 |  | 8.1075 |  | 8.1075 | Single Source - Distance Mode
7 | Capacity Building of Project Staff | [11 empty] | Short listing as per expertise & objective criteria laid down in financial/procurement manual of Govt. of India
8 | CA firm for External Audit |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Short listing as per expertise & objective criteria laid down in financial/procurement manual of Govt. of India
9 | Concurrent Evaluation through CA Firms
10 | Institutional Monitoring | [11 empty] | Short listing as per expertise and objective criteria drawn up Dept. of EE&L.
| Grand Total: | 1085 | 0 | 32.498 | 0 | 0 | 0 | 16.249 | 0 | 8.1245 | 0 | 8.1245

## Kaimur
Typical List of Service Contracts to be hired under SSA for the year 2014-15
Name of District : Kaimur
Sl.No. | Name of Consultancy | Estimated Man Months for each Consultancy | No. of Consultancy | Total Estimated Cost (Rs. In Lakh) | Quarterwise Procurement 2014-15 | [7 empty] | Remarks on Proposed method of Procurement
[5 empty] | I |  | II |  | III |  | IV
[5 empty] | Number | Cost | Number | Cost | Number | Cost | Number | Cost
1 | Experts for various functional units at District Level | [11 empty] | As per Service rules of State Implementation Society
2 | Technical Support for SSA through Ed. CIL. | [11 empty] | As per rule of Ed.CIL for hiring of consultants and procurement.
3 | Technical Support on Quality related issues by NCERT | [11 empty] | Apex GOI institutions to provide specialised services to MHRD as per requirement
4 | Technical Support on Educational Planning and Administration related issues by NUEPA | 19 |  | 0.312 |  |  |  | 0.156 |  | 0.078 |  | 0.078
5 | Technical Support on Distance Education by DEP, IGNOU
6 | Teachers Training (un trained Teachers) | 777 |  | 23.31 |  |  |  | 11.655 |  | 5.8275 |  | 5.8275 | Single Source - Distance Mode
7 | Capacity Building of Project Staff | [11 empty] | Short listing as per expertise & objective criteria laid down in financial/procurement manual of Govt. of India
8 | CA firm for External Audit |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Short listing as per expertise & objective criteria laid down in financial/procurement manual of Govt. of India
9 | Concurrent Evaluation through CA Firms
10 | Institutional Monitoring | [11 empty] | Short listing as per expertise and objective criteria drawn up Dept. of EE&L.
| Grand Total: | 796 | 0 | 23.622 | 0 | 0 | 0 | 11.811 | 0 | 5.9055 | 0 | 5.9055

## Jehanabad
Typical List of Service Contracts to be hired under SSA for the year 2014-15
Name of District : Jehanabad
Sl.No. | Name of Consultancy | Estimated Man Months for each Consultancy | No. of Consultancy | Total Estimated Cost (Rs. In Lakh) | Quarterwise Procurement 2014-15 | [7 empty] | Remarks on Proposed method of Procurement
[5 empty] | I |  | II |  | III |  | IV
[5 empty] | Number | Cost | Number | Cost | Number | Cost | Number | Cost
1 | Experts for various functional units at District Level | [11 empty] | As per Service rules of State Implementation Society
2 | Technical Support for SSA through Ed. CIL. | [11 empty] | As per rule of Ed.CIL for hiring of consultants and procurement.
3 | Technical Support on Quality related issues by NCERT | [11 empty] | Apex GOI institutions to provide specialised services to MHRD as per requirement
4 | Technical Support on Educational Planning and Administration related issues by NUEPA | 13 |  | 0.212 |  |  |  | 0.106 |  | 0.053 |  | 0.053
5 | Technical Support on Distance Education by DEP, IGNOU
6 | Teachers Training (un trained Teachers) | 973 |  | 29.19 |  |  |  | 14.595 |  | 7.2975 |  | 7.2975 | Single Source - Distance Mode
7 | Capacity Building of Project Staff | [11 empty] | Short listing as per expertise & objective criteria laid down in financial/procurement manual of Govt. of India
8 | CA firm for External Audit |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Short listing as per expertise & objective criteria laid down in financial/procurement manual of Govt. of India
9 | Concurrent Evaluation through CA Firms
10 | Institutional Monitoring | [11 empty] | Short listing as per expertise and objective criteria drawn up Dept. of EE&L.
| Grand Total: | 986 | 0 | 29.402 | 0 | 0 | 0 | 14.701 | 0 | 7.3505 | 0 | 7.3505

## Jamui
Typical List of Service Contracts to be hired under SSA for the year 2014-15
Name of District :
Sl.No. | Name of Consultancy | Estimated Man Months for each Consultancy | No. of Consultancy | Total Estimated Cost (Rs. In Lakh) | Quarterwise Procurement 2014-15 | [7 empty] | Remarks on Proposed method of Procurement
[5 empty] | I |  | II |  | III |  | IV
[5 empty] | Number | Cost | Number | Cost | Number | Cost | Number | Cost
1 | Experts for various functional units at District Level | [11 empty] | As per Service rules of State Implementation Society
2 | Technical Support for SSA through Ed. CIL. | [11 empty] | As per rule of Ed.CIL for hiring of consultants and procurement.
3 | Technical Support on Quality related issues by NCERT | [11 empty] | Apex GOI institutions to provide specialised services to MHRD as per requirement
4 | Technical Support on Educational Planning and Administration related issues by NUEPA | 10 |  | 0.164 |  |  |  | 0.082 |  | 0.041 |  | 0.041
5 | Technical Support on Distance Education by DEP, IGNOU
6 | Teachers Training (un trained Teachers) | 1927 |  | 57.81 |  |  |  | 28.905 |  | 14.4525 |  | 14.4525 | Single Source - Distance Mode
7 | Capacity Building of Project Staff | [11 empty] | Short listing as per expertise & objective criteria laid down in financial/procurement manual of Govt. of India
8 | CA firm for External Audit |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Short listing as per expertise & objective criteria laid down in financial/procurement manual of Govt. of India
9 | Concurrent Evaluation through CA Firms
10 | Institutional Monitoring | [11 empty] | Short listing as per expertise and objective criteria drawn up Dept. of EE&L.
| Grand Total: | 1937 | 0 | 57.974 | 0 | 0 | 0 | 28.987 | 0 | 14.4935 | 0 | 14.4935

## Gopalganj
Typical List of Service Contracts to be hired under SSA for the year 2014-15
Name of District : Gopalganj
Sl.No. | Name of Consultancy | Estimated Man Months for each Consultancy | No. of Consultancy | Total Estimated Cost (Rs. In Lakh) | Quarterwise Procurement 2014-15 | [7 empty] | Remarks on Proposed method of Procurement
[5 empty] | I |  | II |  | III |  | IV
[5 empty] | Number | Cost | Number | Cost | Number | Cost | Number | Cost
1 | Experts for various functional units at District Level | [11 empty] | As per Service rules of State Implementation Society
2 | Technical Support for SSA through Ed. CIL. | [11 empty] | As per rule of Ed.CIL for hiring of consultants and procurement.
3 | Technical Support on Quality related issues by NCERT | [11 empty] | Apex GOI institutions to provide specialised services to MHRD as per requirement
4 | Technical Support on Educational Planning and Administration related issues by NUEPA | 5 |  | 0.084 |  |  |  | 0.042 |  | 0.021 |  | 0.021
5 | Technical Support on Distance Education by DEP, IGNOU
6 | Teachers Training (un trained Teachers) | 1844 |  | 55.32 |  |  |  | 27.66 |  | 13.83 |  | 13.83 | Single Source - Distance Mode
7 | Capacity Building of Project Staff | [11 empty] | Short listing as per expertise & objective criteria laid down in financial/procurement manual of Govt. of India
8 | CA firm for External Audit |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Short listing as per expertise & objective criteria laid down in financial/procurement manual of Govt. of India
9 | Concurrent Evaluation through CA Firms
10 | Institutional Monitoring | [11 empty] | Short listing as per expertise and objective criteria drawn up Dept. of EE&L.
| Grand Total: | 1849 | 0 | 55.404 | 0 | 0 | 0 | 27.702 | 0 | 13.851 | 0 | 13.851

## Gaya
Typical List of Service Contracts to be hired under SSA for the year 2014-15
Name of District : Gaya
Sl.No. | Name of Consultancy | Estimated Man Months for each Consultancy | No. of Consultancy | Total Estimated Cost (Rs. In Lakh) | Quarterwise Procurement 2014-15 | [7 empty] | Remarks on Proposed method of Procurement
[5 empty] | I |  | II |  | III |  | IV
[5 empty] | Number | Cost | Number | Cost | Number | Cost | Number | Cost
1 | Experts for various functional units at District Level | [11 empty] | As per Service rules of State Implementation Society
2 | Technical Support for SSA through Ed. CIL. | [11 empty] | As per rule of Ed.CIL for hiring of consultants and procurement.
3 | Technical Support on Quality related issues by NCERT | [11 empty] | Apex GOI institutions to provide specialised services to MHRD as per requirement
4 | Technical Support on Educational Planning and Administration related issues by NUEPA | 5 |  | 0.084 |  |  |  | 0.042 |  | 0.021 |  | 0.021
5 | Technical Support on Distance Education by DEP, IGNOU
6 | Teachers Training (un trained Teachers) | 2498 |  | 74.94 |  |  |  | 37.47 |  | 18.735 |  | 18.735 | Single Source - Distance Mode
7 | Capacity Building of Project Staff | [11 empty] | Short listing as per expertise & objective criteria laid down in financial/procurement manual of Govt. of India
8 | CA firm for External Audit |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Short listing as per expertise & objective criteria laid down in financial/procurement manual of Govt. of India
9 | Concurrent Evaluation through CA Firms
10 | Institutional Monitoring | [11 empty] | Short listing as per expertise and objective criteria drawn up Dept. of EE&L.
| Grand Total: | 2503 | 0 | 75.024 | 0 | 0 | 0 | 37.512 | 0 | 18.756 | 0 | 18.756

## East Champaran
Typical List of Service Contracts to be hired under SSA for the year 2014-15
Name of District : East Champaran
Sl.No. | Name of Consultancy | Estimated Man Months for each Consultancy | No. of Consultancy | Total Estimated Cost (Rs. In Lakh) | Quarterwise Procurement 2014-15 | [7 empty] | Remarks on Proposed method of Procurement
[5 empty] | I |  | II |  | III |  | IV
[5 empty] | Number | Cost | Number | Cost | Number | Cost | Number | Cost
1 | Experts for various functional units at District Level | [11 empty] | As per Service rules of State Implementation Society
2 | Technical Support for SSA through Ed. CIL. | [11 empty] | As per rule of Ed.CIL for hiring of consultants and procurement.
3 | Technical Support on Quality related issues by NCERT | [11 empty] | Apex GOI institutions to provide specialised services to MHRD as per requirement
4 | Technical Support on Educational Planning and Administration related issues by NUEPA | 11 |  | 0.18 |  |  |  | 0.09 |  | 0.045 |  | 0.045
5 | Technical Support on Distance Education by DEP, IGNOU
6 | Teachers Training (un trained Teachers) | 1685 |  | 50.55 |  |  |  | 25.275 |  | 12.6375 |  | 12.6375 | Single Source - Distance Mode
7 | Capacity Building of Project Staff | [11 empty] | Short listing as per expertise & objective criteria laid down in financial/procurement manual of Govt. of India
8 | CA firm for External Audit |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Short listing as per expertise & objective criteria laid down in financial/procurement manual of Govt. of India
9 | Concurrent Evaluation through CA Firms
10 | Institutional Monitoring | [11 empty] | Short listing as per expertise and objective criteria drawn up Dept. of EE&L.
| Grand Total: | 1696 | 0 | 50.73 | 0 | 0 | 0 | 25.365 | 0 | 12.6825 | 0 | 12.6825

## Darbhanga
Typical List of Service Contracts to be hired under SSA for the year 2014-15
Name of District : Darbhanga
Sl.No. | Name of Consultancy | Estimated Man Months for each Consultancy | No. of Consultancy | Total Estimated Cost (Rs. In Lakh) | Quarterwise Procurement 2014-15 | [7 empty] | Remarks on Proposed method of Procurement
[5 empty] | I |  | II |  | III |  | IV
[5 empty] | Number | Cost | Number | Cost | Number | Cost | Number | Cost
1 | Experts for various functional units at District Level | [11 empty] | As per Service rules of State Implementation Society
2 | Technical Support for SSA through Ed. CIL. | [11 empty] | As per rule of Ed.CIL for hiring of consultants and procurement.
3 | Technical Support on Quality related issues by NCERT | [11 empty] | Apex GOI institutions to provide specialised services to MHRD as per requirement
4 | Technical Support on Educational Planning and Administration related issues by NUEPA | 5 |  | 0.084 |  |  |  | 0.042 |  | 0.021 |  | 0.021
5 | Technical Support on Distance Education by DEP, IGNOU
6 | Teachers Training (un trained Teachers) | 1615 |  | 48.45 |  |  |  | 24.225 |  | 12.1125 |  | 12.1125 | Single Source - Distance Mode
7 | Capacity Building of Project Staff | [11 empty] | Short listing as per expertise & objective criteria laid down in financial/procurement manual of Govt. of India
8 | CA firm for External Audit |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Short listing as per expertise & objective criteria laid down in financial/procurement manual of Govt. of India
9 | Concurrent Evaluation through CA Firms
10 | Institutional Monitoring | [11 empty] | Short listing as per expertise and objective criteria drawn up Dept. of EE&L.
| Grand Total: | 1620 | 0 | 48.534 | 0 | 0 | 0 | 24.267 | 0 | 12.1335 | 0 | 12.1335

## Buxer
Typical List of Service Contracts to be hired under SSA for the year 2014-15
Name of District : Buxar
Sl.No. | Name of Consultancy | Estimated Man Months for each Consultancy | No. of Consultancy | Total Estimated Cost (Rs. In Lakh) | Quarterwise Procurement 2014-15 | [7 empty] | Remarks on Proposed method of Procurement
[5 empty] | I |  | II |  | III |  | IV
[5 empty] | Number | Cost | Number | Cost | Number | Cost | Number | Cost
1 | Experts for various functional units at District Level |  |  | 0 | [8 empty] | As per Service rules of State Implementation Society
2 | Technical Support for SSA through Ed. CIL. |  |  | 0 | [8 empty] | As per rule of Ed.CIL for hiring of consultants and procurement.
3 | Technical Support on Quality related issues by NCERT |  |  | 0 | [8 empty] | Apex GOI institutions to provide specialised services to MHRD as per requirement
4 | Technical Support on Educational Planning and Administration related issues by NUEPA | 4 |  | 0.068 |  |  |  | 0.034 |  | 0.017 |  | 0.017
5 | Technical Support on Distance Education by DEP, IGNOU |  |  | 0
6 | Teachers Training (un trained Teachers) | 1201 |  | 36.03 |  |  |  | 18.015 |  | 9.0075 |  | 9.0075 | Single Source - Distance Mode
7 | Capacity Building of Project Staff |  |  | 0 | [8 empty] | Short listing as per expertise & objective criteria laid down in financial/procurement manual of Govt. of India
8 | CA firm for External Audit |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Short listing as per expertise & objective criteria laid down in financial/procurement manual of Govt. of India
9 | Concurrent Evaluation through CA Firms |  |  | 0
10 | Institutional Monitoring |  |  | 0 | [8 empty] | Short listing as per expertise and objective criteria drawn up Dept. of EE&L.
| Grand Total: | 1205 | 0 | 36.098 | 0 | 0 | 0 | 18.049 | 0 | 9.0245 | 0 | 9.0245

## Bhojpur
Typical List of Service Contracts to be hired under SSA for the year 2014-15
Name of District : Bhojpur
Sl.No. | Name of Consultancy | Estimated Man Months for each Consultancy | No. of Consultancy | Total Estimated Cost (Rs. In Lakh) | Quarterwise Procurement 2014-15 | [7 empty] | Remarks on Proposed method of Procurement
[5 empty] | I |  | II |  | III |  | IV
[5 empty] | Number | Cost | Number | Cost | Number | Cost | Number | Cost
1 | Experts for various functional units at District Level | [11 empty] | As per Service rules of State Implementation Society
2 | Technical Support for SSA through Ed. CIL. | [11 empty] | As per rule of Ed.CIL for hiring of consultants and procurement.
3 | Technical Support on Quality related issues by NCERT | [11 empty] | Apex GOI institutions to provide specialised services to MHRD as per requirement
4 | Technical Support on Educational Planning and Administration related issues by NUEPA | 5 |  | 0.084 |  |  |  | 0.042 |  | 0.021 |  | 0.021
5 | Technical Support on Distance Education by DEP, IGNOU
6 | Teachers Training (un trained Teachers) | 1897 |  | 56.91 |  |  |  | 28.455 |  | 14.2275 |  | 14.2275 | Single Source - Distance Mode
7 | Capacity Building of Project Staff | [11 empty] | Short listing as per expertise & objective criteria laid down in financial/procurement manual of Govt. of India
8 | CA firm for External Audit |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Short listing as per expertise & objective criteria laid down in financial/procurement manual of Govt. of India
9 | Concurrent Evaluation through CA Firms
10 | Institutional Monitoring | [11 empty] | Short listing as per expertise and objective criteria drawn up Dept. of EE&L.
| Grand Total: | 1902 | 0 | 56.994 | 0 | 0 | 0 | 28.497 | 0 | 14.2485 | 0 | 14.2485

## Bhagalpur
Typical List of Service Contracts to be hired under SSA for the year 2014-15
Name of District :
Sl.No. | Name of Consultancy | Estimated Man Months for each Consultancy | No. of Consultancy | Total Estimated Cost (Rs. In Lakh) | Quarterwise Procurement 2014-15 | [7 empty] | Remarks on Proposed method of Procurement
[5 empty] | I |  | II |  | III |  | IV
[5 empty] | Number | Cost | Number | Cost | Number | Cost | Number | Cost
1 | Experts for various functional units at District Level | [11 empty] | As per Service rules of State Implementation Society
2 | Technical Support for SSA through Ed. CIL. | [11 empty] | As per rule of Ed.CIL for hiring of consultants and procurement.
3 | Technical Support on Quality related issues by NCERT | [11 empty] | Apex GOI institutions to provide specialised services to MHRD as per requirement
4 | Technical Support on Educational Planning and Administration related issues by NUEPA | 4 |  | 0.068 |  |  |  | 0.034 |  | 0.017 |  | 0.017
5 | Technical Support on Distance Education by DEP, IGNOU
6 | Teachers Training (un trained Teachers) | 1651 |  | 49.53 |  |  |  | 24.765 |  | 12.3825 |  | 12.3825 | Single Source - Distance Mode
7 | Capacity Building of Project Staff | [11 empty] | Short listing as per expertise & objective criteria laid down in financial/procurement manual of Govt. of India
8 | CA firm for External Audit |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Short listing as per expertise & objective criteria laid down in financial/procurement manual of Govt. of India
9 | Concurrent Evaluation through CA Firms
10 | Institutional Monitoring | [11 empty] | Short listing as per expertise and objective criteria drawn up Dept. of EE&L.
| Grand Total: | 1655 | 0 | 49.598 | 0 | 0 | 0 | 24.799 | 0 | 12.3995 | 0 | 12.3995

## Begusarai
Typical List of Service Contracts to be hired under SSA for the year 2014-15
Name of District :
Sl.No. | Name of Consultancy | Estimated Man Months for each Consultancy | No. of Consultancy | Total Estimated Cost (Rs. In Lakh) | Quarterwise Procurement 2014-15 | [7 empty] | Remarks on Proposed method of Procurement
[5 empty] | I |  | II |  | III |  | IV
[5 empty] | Number | Cost | Number | Cost | Number | Cost | Number | Cost
1 | Experts for various functional units at District Level | [11 empty] | As per Service rules of State Implementation Society
2 | Technical Support for SSA through Ed. CIL. | [11 empty] | As per rule of Ed.CIL for hiring of consultants and procurement.
3 | Technical Support on Quality related issues by NCERT | [11 empty] | Apex GOI institutions to provide specialised services to MHRD as per requirement
4 | Technical Support on Educational Planning and Administration related issues by NUEPA | 5 |  | 0.084 |  |  |  | 0.042 |  | 0.021 |  | 0.021
5 | Technical Support on Distance Education by DEP, IGNOU
6 | Teachers Training (un trained Teachers) | 1970 |  | 59.1 |  |  |  | 29.55 |  | 14.775 |  | 14.775 | Single Source - Distance Mode
7 | Capacity Building of Project Staff | [11 empty] | Short listing as per expertise & objective criteria laid down in financial/procurement manual of Govt. of India
8 | CA firm for External Audit |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Short listing as per expertise & objective criteria laid down in financial/procurement manual of Govt. of India
9 | Concurrent Evaluation through CA Firms | [6 empty] | 0 |  | 0 |  | 0
10 | Institutional Monitoring | [11 empty] | Short listing as per expertise and objective criteria drawn up Dept. of EE&L.
| Grand Total: | 1975 | 0 | 59.184 | 0 | 0 | 0 | 29.592 | 0 | 14.796 | 0 | 14.796
9 | Concurrent Evaluation through CA Firms
10 | Institutional Monitoring | [11 empty] | Short listing as per expertise and objective criteria drawn up Dept. of EE&L.
| Grand Total: | 3950 | 0 | 118.368 | 0 | 0 | 0 | 59.184 | 0 | 29.592 | 0 | 29.592

## Banka
Typical List of Service Contracts to be hired under SSA for the year 2014-15
Name of District : Banka
Sl.No. | Name of Consultancy | Estimated Man Months for each Consultancy | No. of Consultancy | Total Estimated Cost (Rs. In Lakh) | Quarterwise Procurement 2014-15 | [7 empty] | Remarks on Proposed method of Procurement
[5 empty] | I |  | II |  | III |  | IV
[5 empty] | Number | Cost | Number | Cost | Number | Cost | Number | Cost
1 | Experts for various functional units at District Level | [11 empty] | As per Service rules of State Implementation Society
2 | Technical Support for SSA through Ed. CIL. | [11 empty] | As per rule of Ed.CIL for hiring of consultants and procurement.
3 | Technical Support on Quality related issues by NCERT | [11 empty] | Apex GOI institutions to provide specialised services to MHRD as per requirement
4 | Technical Support on Educational Planning and Administration related issues by NUEPA | 7 |  | 0.116 |  |  |  | 0.058 |  | 0.029 |  | 0.029
5 | Technical Support on Distance Education by DEP, IGNOU
6 | Teachers Training (un trained Teachers) | 2015 |  | 60.45 |  |  |  | 30.225 |  | 15.1125 |  | 15.1125 | Single Source - Distance Mode
7 | Capacity Building of Project Staff | [11 empty] | Short listing as per expertise & objective criteria laid down in financial/procurement manual of Govt. of India
8 | CA firm for External Audit |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Short listing as per expertise & objective criteria laid down in financial/procurement manual of Govt. of India
9 | Concurrent Evaluation through CA Firms
10 | Institutional Monitoring | [11 empty] | Short listing as per expertise and objective criteria drawn up Dept. of EE&L.
| Grand Total: | 2022 | 0 | 60.566 | 0 | 0 | 0 | 30.283 | 0 | 15.1415 | 0 | 15.1415

## Aurangabad
Typical List of Service Contracts to be hired under SSA for the year 2014-15
Name of District : Aurangabad
Sl.No. | Name of Consultancy | Estimated Man Months for each Consultancy | No. of Consultancy | Total Estimated Cost (Rs. In Lakh) | Quarterwise Procurement 2014-15 | [7 empty] | Remarks on Proposed method of Procurement
[5 empty] | I |  | II |  | III |  | IV
[5 empty] | Number | Cost | Number | Cost | Number | Cost | Number | Cost
1 | Experts for various functional units at District Level
2 | Technical Support for SSA through Ed. CIL.
3 | Technical Support on Quality related issues by NCERT
4 | Technical Support on Educational Planning and Administration related issues by NUEPA | 4 |  | 0.068 |  |  |  | 0.034 |  | 0.017 |  | 0.017
5 | Technical Support on Distance Education by DEP, IGNOU
6 | Teachers Training (un trained Teachers) | 2721 |  | 81.63 |  |  |  | 40.815 |  | 20.4075 |  | 20.4075
7 | Capacity Building of Project Staff
8 | CA firm for External Audit |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | Concurrent Evaluation through CA Firms
10 | Institutional Monitoring
| Grand Total: | 2725 | 0 | 81.698 | 0 | 0 | 0 | 40.849 | 0 | 20.4245 | 0 | 20.4245

## Arwal
Typical List of Service Contracts to be hired under SSA for the year 2014-15
Name of District : ARWAL
Sl.No. | Name of Consultancy | Estimated Man Months for each Consultancy | No. of Consultancy | Total Estimated Cost (Rs. In Lakh) | Quarterwise Procurement 2014-15 | [7 empty] | Remarks on Proposed method of Procurement
[5 empty] | I |  | II |  | III |  | IV
[5 empty] | Number | Cost | Number | Cost | Number | Cost | Number | Cost
1 | Experts for various functional units at District Level | [11 empty] | As per Service rules of State Implementation Society
2 | Technical Support for SSA through Ed. CIL. | [11 empty] | As per rule of Ed.CIL for hiring of consultants and procurement.
3 | Technical Support on Quality related issues by NCERT | [11 empty] | Apex GOI institutions to provide specialised services to MHRD as per requirement
4 | Technical Support on Educational Planning and Administration related issues by NUEPA | 4 |  | 0.068 |  |  |  | 0.034 |  | 0.017 |  | 0.017
5 | Technical Support on Distance Education by DEP, IGNOU | 0 |  | 0
6 | Teachers Training (un trained Teachers) | 559 |  | 16.77 |  |  |  | 8.385 |  | 4.1925 |  | 4.1925 | Single Source - Distance Mode
7 | Capacity Building of Project Staff | [11 empty] | Short listing as per expertise & objective criteria laid down in financial/procurement manual of Govt. of India
8 | CA firm for External Audit |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Short listing as per expertise & objective criteria laid down in financial/procurement manual of Govt. of India
9 | Concurrent Evaluation through CA Firms
10 | Institutional Monitoring | [11 empty] | Short listing as per expertise and objective criteria drawn up Dept. of EE&L.
| Grand Total: | 563 | 0 | 16.838 | 0 | 0 | 0 | 8.419 | 0 | 4.2095 | 0 | 4.2095

## Araia
Typical List of Service Contracts to be hired under SSA for the year 2014-15
Name of District : Araria
Sl.No. | Name of Consultancy | Estimated Man Months for each Consultancy | No. of Consultancy | Total Estimated Cost (Rs. In Lakh) | Quarterwise Procurement 2014-15 | [7 empty] | Remarks on Proposed method of Procurement
[5 empty] | I |  | II |  | III |  | IV
[5 empty] | Number | Cost | Number | Cost | Number | Cost | Number | Cost
1 | Experts for various functional units at District Level | [11 empty] | As per Service rules of State Implementation Society
2 | Technical Support for SSA through Ed. CIL. | [11 empty] | As per rule of Ed.CIL for hiring of consultants and procurement.
3 | Technical Support on Quality related issues by NCERT | [11 empty] | Apex GOI institutions to provide specialised services to MHRD as per requirement
4 | Technical Support on Educational Planning and Administration related issues by NUEPA | 19 |  | 0.312 |  |  |  | 0.156 |  | 0.078 |  | 0.078
5 | Technical Support on Distance Education by DEP, IGNOU | 0 |  | 0
6 | Teachers Training (un trained Teachers) | 1676 |  | 50.28 |  |  |  | 25.14 |  | 12.57 |  | 12.57 | Single Source - Distance Mode
7 | Capacity Building of Project Staff | [11 empty] | Short listing as per expertise & objective criteria laid down in financial/procurement manual of Govt. of India
8 | CA firm for External Audit |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Short listing as per expertise & objective criteria laid down in financial/procurement manual of Govt. of India
9 | Concurrent Evaluation through CA Firms
10 | Institutional Monitoring | [11 empty] | Short listing as per expertise and objective criteria drawn up Dept. of EE&L.
| Grand Total: | 1695 | 0 | 50.592 | 0 | 0 | 0 | 25.296 | 0 | 12.648 | 0 | 12.648